**POWER PURCHASE AND SALE AGREEMENT**

**COVER SHEET**

**Seller**: [***Seller name***], [***Entity Type***]

**Buyer**: Peninsula Clean Energy Authority, a California joint powers authority

**Description of Facility**: [***Example: A \_\_\_ MW AC photovoltaic electric generating facility located in \_\_\_\_\_\_\_\_\_ County, California***]

**Guaranteed Commercial Operation Date:** [***Date***]

**Milestones**:

| **Milestone** | **Completion Date** |
| --- | --- |
| **Site Control** | [***Month, Year***] |
| **Conditional Use Permit** | [***Month, Year***] |
| **Phase II Interconnection Study Results** | [***Month, Year***] |
| **Obtain Full Capacity Deliverability Status Allocation** | [***Month, Year***] |
| **Executed Interconnection Agreement** | [***Month, Year***] |
| **Procure Major Equipment** | [***Month, Year***] |
| **Financial Close** | [***Month, Year***] |
| **Construction Start** | [***Month, Year***] |
| **Initial Synchronization** | [***Month, Year***] |
| **Deliverability Network Upgrades completed** | [***Month, Year***] |
| **CAISO Commercial Operation** | **[*Month, Year*]** |
| **Commercial Operation Date** | [***Month, Year***] |

**Delivery Term**: [***Number of years***] Contract Years

**Guaranteed Capacity:** [\_] MW at the Delivery Point

**Delivery Term Expected Energy**: **[*To be based on the P50 value provided by the Facility’s resource study*.]**

| **Contract Year** | **Expected Energy (MWh)** |
| --- | --- |
| 1 | [***\_\_\_\_\_\_\_***] |
| 2 | [***\_\_\_\_\_\_\_***] |
| 3 | [***\_\_\_\_\_\_\_***] |
| 4 | [***\_\_\_\_\_\_\_***] |
| 5 | [***\_\_\_\_\_\_\_***] |
| [***Through N***] | [***\_\_\_\_\_\_\_***] |

**Monthly Expected Energy**:[[1]](#footnote-2)

| **Month** | **Expected Energy (MWh)** |
| --- | --- |
| January | [***\_\_\_\_\_\_\_***] |
| February | [***\_\_\_\_\_\_\_***] |
| March | [***\_\_\_\_\_\_\_***] |
| April | [***\_\_\_\_\_\_\_***] |
| May | [***\_\_\_\_\_\_\_***] |
| June | [***\_\_\_\_\_\_\_***] |
| July | [***\_\_\_\_\_\_\_***] |
| August | [***\_\_\_\_\_\_\_***] |
| September | [***\_\_\_\_\_\_\_***] |
| October | [***\_\_\_\_\_\_\_***] |
| November | [***\_\_\_\_\_\_\_***] |
| December | [***\_\_\_\_\_\_\_***] |

**Contract Price**:

| **Contract Year** | **Contract Price ($/MWh)** |
| --- | --- |
| 1 | [***$\_\_\_\_\_\_\_***] |
| 2 | [***$\_\_\_\_\_\_\_***] |
| 3 | [***$\_\_\_\_\_\_\_***] |
| 4 | [***$\_\_\_\_\_\_\_***] |
| 5 | [***$\_\_\_\_\_\_\_***] |
| [***Through N***] | [***$\_\_\_\_\_\_\_***] |

**Product**:

x Energy

x Green Attributes: Portfolio Content Category 1

x Future Environmental Attributes

x Capacity Attributes

**Scheduling Coordinator**: Buyer or Buyer’s Agent

**Development Security**: [***To equal $100/kW of Guaranteed Capcity.***]

**Performance Security**: [***To equal five percent (5%) of the total term project revenues.*]**

**Damage Payment**: **[*To equal the Development Security amount***]

[*Signatures on following page.*]

IN WITNESS WHEREOF, the Parties have caused this Agreement to be duly executed as of the Effective Date.

|  |  |
| --- | --- |
| SELLER**[*Name of Seller*]**By: Name: Title:  | BUYERPeninsula Clean Energy AuthorityBy:  PCE Executive Officer |

ARTICLE 1 DEFINITIONS 1

1.1 Contract Definitions 1

1.2 Rules of Interpretation 18

ARTICLE 2 TERM; CONDITIONS PRECEDENT 19

2.1 Contract Term 19

2.2 Conditions Precedent 20

2.3 Progress Reports 22

2.4 Remedial Action Plan 22

ARTICLE 3 PURCHASE AND SALE 22

3.1 Sale of Product 22

3.2 Sale of Green Attributes 23

3.3 Compensation 23

3.4 Imbalance Energy 23

3.5 Ownership of Renewable Energy Incentives 24

3.6 Future Environmental Attributes 24

3.7 Test Energy 24

3.8 Capacity Attributes 25

3.9 Resource Adequacy Failure 25

3.10 CEC Certification and Verification 26

3.11 Eligibility 27

3.12 California Renewables Portfolio Standard 27

3.13 Compliance Expenditure Cap 27

ARTICLE 4 OBLIGATIONS AND DELIVERIES 28

4.1 Delivery 28

4.2 Title and Risk of Loss 29

4.3 Scheduling Coordinator Responsibilities 29

4.4 Forecasting 31

4.5 Dispatch Down/Curtailment 32

4.6 Reduction in Delivery Obligation 33

4.7 Expected Energy and Guaranteed Energy Production 33

4.8 WREGIS 34

4.9 Financial Statements 35

4.10 Access to Data and Installation and Maintenance of Weather Station 35

4.11 Ancillary Services 38

4.12 Workforce Agreement 38

4.13 Diverse Business Enterprises. During the Delivery Term, n 38

4.14 Shared Facilities 38

ARTICLE 5 TAXES 39

5.1 Allocation of Taxes and Charges 39

5.2 Cooperation 39

ARTICLE 6 MAINTENANCE OF THE FACILITY 39

6.1 Maintenance of the Facility 39

6.2 Maintenance of Health and Safety. 40

6.3 Permits and Approvals 40

6.4 Energy to Serve Station Use 40

ARTICLE 7 METERING 40

7.1 Metering 40

7.2 Meter Verification 41

ARTICLE 8 INVOICING AND PAYMENT; CREDIT 41

8.1 Invoicing 41

8.2 Payment 41

8.3 Books and Records 42

8.4 Payment Adjustments; Billing Errors 42

8.5 Billing Disputes 42

8.6 Netting of Payments 42

8.7 Seller’s Development Security 43

8.8 Seller’s Performance Security 43

8.9 First Priority Security Interest in Cash or Cash Equivalent Collateral 43

ARTICLE 9 NOTICES 44

9.1 Addresses for the Delivery of Notices 44

9.2 Acceptable Means of Delivering Notice 44

ARTICLE 10 FORCE MAJEURE 44

10.1 Definition 44

10.2 No Liability If a Force Majeure Event Occurs 45

10.3 Notice 46

10.4 Termination Following Force Majeure Event 46

ARTICLE 11 DEFAULTS; REMEDIES; TERMINATION 46

11.1 Events of Default 46

11.2 Remedies; Declaration of Early Termination Date 48

11.3 Termination Payment 49

11.4 Notice of Payment of Termination Payment 49

11.5 Disputes With Respect to Termination Payment 50

11.6 Limitation on Seller’s Ability to Make or Agree to Third-Party Sales from the Facility after Early Termination Date 50

11.7 Rights And Remedies Are Cumulative 50

11.8 Mitigation 50

ARTICLE 12 LIMITATION OF LIABILITY AND EXCLUSION OF WARRANTIES. 50

12.1 No Consequential Damages 50

12.2 Waiver and Exclusion of Other Damages 51

ARTICLE 13 REPRESENTATIONS AND WARRANTIES; AUTHORITY 51

13.1 Seller’s Representations and Warranties 51

13.2 Buyer’s Representations and Warranties 52

13.3 General Covenants 53

13.4 Prohibition Against Forced Labor 53

ARTICLE 14 ASSIGNMENT 54

14.1 General Prohibition on Assignments 54

14.2 Permitted Assignment; Change of Control of Seller 54

14.3 Permitted Assignment; Change of Control of Buyer 54

ARTICLE 15 LENDER ACCOMMODATIONS 54

15.1 Granting of Lender Interest 54

15.2 Rights of Lender 55

15.3 Cure Rights of Lender 55

ARTICLE 16 DISPUTE RESOLUTION 55

16.2 Dispute Resolution 56

16.3 Attorneys’ Fees 56

ARTICLE 17 INDEMNIFICATION 56

17.1 Indemnification 56

17.2 Claims 56

ARTICLE 18 INSURANCE 57

18.1 Insurance 57

ARTICLE 19 CONFIDENTIAL INFORMATION 58

19.1 Definition of Confidential Information 58

19.2 Duty to Maintain Confidentiality 58

19.3 Irreparable Injury; Remedies 58

19.4 Disclosure to Lender 59

19.5 Disclosure to Credit Rating Agency 59

19.6 Public Statements 59

ARTICLE 20 MISCELLANEOUS 59

20.1 Entire Agreement; Integration; Exhibits 59

20.2 Amendments 59

20.3 Time is of the Essence. 59

20.4 No Waiver 59

20.5 No Agency, Partnership, Joint Venture or Lease 59

20.6 Severability 60

20.7 Mobile-Sierra 60

20.8 Counterparts 60

20.9 Facsimile or Electronic Delivery 60

20.10 Binding Effect 60

20.11 No Recourse to Members of Buyer 60

20.12 Change in Electric Market Design 61

ARTICLE 21 CPUC MODIFIABLE STANDARD CONTRACT TERMS 61

21.1 STC 2: Bioenergy Transactions 61

21.2 STC 4: Confidentiality 62

21.3 STC 5: Contract Term 63

21.4 STC 7: Performance Standards/Requirements 63

21.5 STC 8: Product Definitions 1

21.6 STC 9: Non-Performance or Termination Penalties and Default Provisions 1

21.7 STC 12: Credit Terms 5

21.8 STC 15: Contract Modifications 10

21.9 STC 16: Assignment 10

21.10 STC 18: Application of Prevailing Wage 10

**Exhibits:**

Exhibit A Description of Facility

Exhibit B Facility Construction and Commercial Operation

Exhibit C [Intentionally Omitted]

Exhibit D Guaranteed Energy Production Damages Calculation

Exhibit E Progress Reporting Form

Exhibit F Buyout Option

Exhibit G-1 Form of Commercial Operation Date Certificate

Exhibit G-2 Form of Installed Capacity Certificate

Exhibit H Form of Construction Start Date Certificate

Exhibit I Form of Letter of Credit

Exhibit J Insurance

Exhibit K Form of Replacement RA Notice

Exhibit L Annual Energy Forecast and Monthly Expected Available Capacity and Metered Energy

Exhibit M Notices

**POWER PURCHASE AND SALE AGREEMENT**

This Power Purchase and Sale Agreement (“**Agreement**”) is entered into as of **[\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_]** (the “**Effective Date**”), between Seller and Buyer (each also referred to as a “**Party**” and collectively as the “**Parties**”).

**RECITALS**

WHEREAS, Seller intends to develop, design, construct, own or otherwise have control over, and operate the electric generating facility as described in Exhibit A (the “**Facility**”); and

WHEREAS, Seller desires to sell, and Buyer desires to purchase, on the terms and conditions set forth in this Agreement, all Energy generated by the Facility, all Green Attributes related to the generation of such Energy, and all Capacity Attributes;

NOW THEREFORE, in consideration of the mutual covenants and agreements herein contained, and for other good and valuable consideration, the sufficiency and adequacy of which are hereby acknowledged, the Parties agree to the following:

# DEFINITIONS

## Contract Definitions. The following terms, when used herein with initial capitalization, shall have the meanings set forth below:

“**AC**” means alternating current.

“**Accepted Compliance Costs**” has the meaning set forth in Section 3.13.

“**Adjusted Energy Production**” has the meaning set forth in Exhibit D.

“**Affiliate**” means, with respect to any Person, each Person that directly or indirectly Controls, is Controlled by, or is under common Control with such designated Person.

“**Agreement**” has the meaning set forth in the Preamble and includes the Cover Sheet and any exhibits, schedules and any written supplements hereto.

“**Availability Incentive Payment**” has the meaning set forth in the CAISO Tariff.

“**Available Capacity**” means the capacity from the Facility, expressed in whole MWs, that is available at a particular time to generate Product.

“**Bankrupt**” means with respect to any entity, such entity that (a) files a petition or otherwise commences, authorizes or acquiesces in the commencement of a proceeding or cause of action under any bankruptcy, insolvency, reorganization or similar Law, (b) has any such petition filed or commenced against it which remains unstayed or undismissed for a period of ninety (90) days, (c) makes an assignment or any general arrangement for the benefit of creditors, (d) otherwise becomes bankrupt or insolvent (however evidenced), (e) has a liquidator, administrator, receiver, trustee, conservator or similar official appointed with respect to it or any substantial portion of its property or assets, or (f) is generally unable to pay its debts as they fall due.

“**Bid**” has the meaning set forth in the CAISO Tariff.

“**Business Day**” means any day except a Saturday, Sunday, or a Federal Reserve Bank holiday in California. A Business Day begins at 8:00 a.m. and ends at 5:00 p.m. local time for the Party sending a Notice, or payment, or performing a specified action.

“**Buyer**” has the meaning set forth on the Cover Sheet.

“**Buyer Bid Curtailment**” means the occurrence of all of the following:

(a) the CAISO provides notice to a Party or the Scheduling Coordinator for the Facility, requiring the Party to produce less Energy from the Facility for a period of time [***For solar or wind resources:*** than is reflected in the VER Forecast for the Facility] [***For non-solar and non-wind resources:*** than the Facility was able to produce for a period of time, as determined based upon the lesser of (A) the arithmetic average of the Facility’s metered output rate, in MW, for the twenty-four (24) hour periods immediately before and after the related Buyer Curtailment Period, or (B) the Guaranteed Capacity];

(b) for the same time period as referenced in (a), Buyer or the SC for the Facility:

(i) did not submit a Self-Schedule or an Energy Supply Bid for the MW subject to the reduction; or

(ii) submitted an Energy Supply Bid and the CAISO notice referenced in (a) is solely a result of CAISO implementing the Energy Supply Bid; or

(iii) submitted a Self-Schedule for less than the full amount of Energy forecasted to be produced from the Facility; and

(c) no other circumstances exist that constitute a Scheduled Maintenance, Forced Facility Outage, Force Majeure Event and/or a Curtailment Period during the same time period as referenced in (a).

“**Buyer Curtailment Order**” means the instruction from Buyer to Seller to reduce generation from the Facility by the amount, and for the period of time set forth in such order, for reasons unrelated to a Scheduled Maintenance, Forced Facility Outage, Force Majeure Event and/or Curtailment Order, which instruction may be communicated to Seller in writing by electronic notice or other commercially reasonable means.

“**Buyer Curtailment Period**” means the period of time, as measured using current Settlement Intervals, during which Seller reduces generation from the Facility pursuant to a (i) Buyer Bid Curtailment or (ii) Buyer Curtailment Order.

“**Buyer Default**” means a failure by Buyer to perform its obligations hereunder.

“**Buyer’s WREGIS Account**” has the meaning set forth in Section 4.8(a).

“**CAISO**” means the California Independent System Operator Corporation or any successor entity performing similar functions.

 “**CAISO Approved Meter**” means a CAISO approved revenue quality meter or meters, CAISO approved data processing gateway or remote intelligence gateway, telemetering equipment and data acquisition services sufficient for monitoring, recording and reporting, in real time, all Energy produced by the Facility less Electrical Losses and Station Use, in accordance with the CAISO Tariff.

“**CAISO Charges Invoice**” has the meaning set forth in Section 4.3(d).

“**CAISO Commercial Operation**” has the meaning of “Commercial Operation” set forth in the CAISO Tariff.

“**CAISO Grid**” has the same meaning as “CAISO Controlled Grid” as defined in the CAISO Tariff.

“**CAISO Operating Order**” means the “operating order” defined in Section 37.2.1.1 of the CAISO Tariff.

“**CAISO Tariff**” means the California Independent System Operator Corporation Agreement and Tariff, Business Practice Manuals (BPMs), and Operating Procedures, including the rules, protocols, procedures and standards attached thereto, as the same may be amended or modified from time-to-time and approved by FERC.

“**California Renewables Portfolio Standard**” or “**RPS**” means the renewable energy program and policies established by California State Senate Bills 1038 (2002), 1078 (2002), 107 (2008), X-1 2 (2011), 350 (2015) and 100 (2018) codified in, *inter alia*, California Public Utilities Code Sections 399.11 through 399.31 and California Public Resources Code Sections 25740 through 25751, as such provisions are amended or supplemented from time to time.

“**Capacity Attribute**” means any current or future defined characteristic, certificate, tag, credit, or accounting construct associated with the amount of power that the Facility can generate and/or deliver to the CAISO Grid at a particular moment and that can be purchased and sold under CAISO market rules, including Resource Adequacy Benefits. Capacity Attributes shall also include all rights to provide and all benefits related to the provision of Ancillary Services (as defined in the CAISO Tariff) and reactive power.

“**Capacity Damages**” has the meaning set forth in Exhibit B.

“**CEC**” means the California Energy Commission or its successor agency.

“**CEC Final Certification and Verification**” means that the CEC has certified the Facility as an Eligible Renewable Energy Resource for purposes of the California Renewables Portfolio Standard, meeting all applicable requirements for certified facilities set forth in the *RPS Eligibility Guidebook, Ninth Edition* (or its successor), and that all Energy generated by the Facility qualifies as generation from an Eligible Renewable Energy Resource.

“**CAISO-Penalized Shortfall**” has the meaning set forth in Section 3.9(b)(ii).

“**CEC Precertification**” means that the CEC has issued a precertification for the Facility indicating that the planned operations of the Facility would comply with applicable CEC requirements for CEC Final Certification and Verification.

“**Change of Control**”, in the case of Seller, means any circumstance in which Seller’s Ultimate Parent ceases to be the Ultimate Parent or to own, directly or indirectly through one or more intermediate entities, more than fifty percent (50%) of the outstanding equity interests in Seller; provided that in calculating ownership percentages for all purposes of the foregoing:

(a) any ownership interest in Seller held by its Ultimate Parent indirectly through one or more intermediate entities shall not be counted towards the Ultimate Parent’s ownership interest in Seller unless the Ultimate Parent directly or indirectly owns more than fifty percent (50%) of the outstanding equity interests in each such intermediate entity; and

(b) ownership interests in Seller owned directly or indirectly by any Lender (including any tax equity provider) shall be excluded from the total outstanding equity interests in Seller.

Notwithstanding the foregoing, (a) so long as the Ultimate Parent Controls Persons owning at least [\_\_\_] MW of operating renewable electricity generating projects, a change in the Control of the Ultimate Parent, or (b) a change in the Control of Seller resulting from the exercise by Lender of its remedies under its financing agreements for the Facility with Seller or an Affiliate of Seller shall not be a Change of Control hereunder; provided that the entity acquiring Control of the Ultimate Parent or of Seller, directly or indirectly, is a Qualified Transferee and Buyer is given written notice of the Change of Control within five (5) Business Days of its occurrence.

“**Commercial Operation**” has the meaning set forth in Exhibit B.

“**Commercial Operation Date**” has the meaning set forth in Exhibit B.

“**Commercial Operation Delay Damages**” means an amount equal to (a) the Development Security amount required hereunder, divided by (b) ninety (90).

“**Compliance Actions**” has the meaning set forth in Section 3.13.

“**Compliance Expenditure Cap**” has the meaning set forth in Section 3.13.

“**Confidential Information**” has the meaning set forth in Section 19.1.

“**Construction Start**” has the meaning set forth in Exhibit B.

“**Construction Start Date**” has the meaning set forth in Exhibit B.

“**Contract Price**” has the meaning set forth in the Cover Sheet.

“**Contract Term**” has the meaning set forth in Section 2.1.

“**Contract Year**” means a period of twelve (12) consecutive months. The first Contract Year shall commence on the Commercial Operation Date, and each subsequent Contract Year shall commence on the anniversary of the Commercial Operation Date.

“**Control**” (including, with correlative meanings, the terms “Controlled by” and “under common Control with”), as used with respect to any Person, shall mean (a) the direct or indirect right to cast more than fifty percent (50%) of the votes exercisable at an annual general meeting (or its equivalent) of such Person or, if there are no such rights, ownership of more than fifty percent (50%) of the equity or other ownership interest in such Person, or (b) the right to direct the policies or operations of such Person.

“**Costs**” means, with respect to the Non-Defaulting Party, brokerage fees, commissions and other similar third-party transaction costs and expenses reasonably incurred by such Party either in terminating any arrangement pursuant to which it has hedged its obligations or entering into new arrangements which replace this Agreement; and all reasonable attorneys’ fees and expenses incurred by the Non-Defaulting Party in connection with terminating the Agreement.

“**Cover Sheet**” means the cover sheet to this Agreement.

“**CPM Soft Offer Cap**” has the meaning set forth in the CAISO Tariff.

“**CPUC**” means the California Public Utilities Commission, or successor entity.

“**CPUC-Penalized Shortfall**” has the meaning set forth in Section 3.9(b)(i).

“**Credit Rating**” means, with respect to any entity, the rating then assigned to such entity’s unsecured, senior long-term debt obligations (not supported by third party credit enhancements), or if such entity does not have a rating for its senior unsecured long-term debt, then the rating then assigned to such entity as an issuer rating, in either case by S&P or Moody’s. If ratings by S&P and Moody’s are not equivalent, the lower rating shall apply.

“**Curtailment Order**” means any of the following:

1. CAISO orders, directs, alerts, or provides notice to a Party, including a CAISO Operating Order, to curtail Energy deliveries for any reason other than a Buyer Bid Curtailment;
2. a curtailment ordered by the Participating Transmission Owner or distribution operator (if the Facility is interconnected to distribution or sub-transmission system) for reasons including, but not limited to, (i) any situation that affects normal function of the electric system including, but not limited to, any abnormal condition that requires action to prevent circumstances such as equipment damage, loss of load, or abnormal voltage conditions, or (ii) any warning, forecast or anticipation of conditions or situations that jeopardize the Participating Transmission Owner’s or distribution operator’s electric system integrity or the integrity of other systems to which the Participating Transmission Owner is connected;
3. a curtailment ordered by the Participating Transmission Owner due to scheduled or unscheduled maintenance on the Participating Transmission Owner’s transmission facilities that prevents (i) Buyer from receiving or (ii) Seller from delivering Energy to the Delivery Point; or
4. a curtailment in accordance with Seller’s obligations under its Interconnection Agreement with the Participating Transmission Owner or distribution operator.

For the avoidance of doubt, if Buyer or Buyer’s SC submitted a Self-Schedule and/or an Energy Supply Bid in its final CAISO market participation in respect of a given time period that clears, in full, the applicable CAISO market for the full amount of Energy forecasted to be produced from the Facility for such time period, any notice from the CAISO having the effect of requiring a reduction during the same time period is a Curtailment Order, not a Buyer Bid Curtailment.

“**Curtailment Period**” means the period of time, as measured using current Settlement Intervals, during which Seller reduces generation from the Facility pursuant to a Curtailment Order.

“**Daily Delay Damages**” means an amount equal to (a) the Development Security amount required hereunder, divided by (b) one hundred twenty (120).

“**Damage Payment**” means a liquidated damages payment in the amount indicated in the Cover Sheet.

“**Day-Ahead Forecast**” has the meaning set forth in Section 4.4(c).

“**Day-Ahead LMP**” means the LMP for the Day-Ahead Market.

“**Day-Ahead Market**” has the meaning set forth in the CAISO Tariff.

“**Day-Ahead Schedule**” has the meaning set forth in the CAISO Tariff.

“**Deemed Delivered Energy**” means the amount of Energy, expressed in MWh that the Facility would have produced and delivered to the Delivery Point, but that is not produced by the Facility and delivered to the Delivery Point during a Buyer Curtailment Period. [***For a solar or wind resource***: The amount shall be equal to (a) the VER Forecast expressed in MWh, applicable to the Buyer Curtailment Period, or (b) if there is no VER Forecast available or Seller demonstrates to Buyer’s reasonable satisfaction that the VER Forecast does not represent an accurate forecast of generation from the Facility, the amount determined by a third party reasonably acceptable to Buyer using an industry standard forecasting or back-casting methodology to determine the potential generation of the Facility as a function of Available Capacity, [***solar insolation and panel temperature,***][***and wind speed,***] and other pertinent data for the period of time during the Buyer Curtailment Period, in either case less the amount of Metered Energy delivered to the Delivery Point during the Buyer Curtailment Period; *provided that*, if the applicable difference is negative, the Deemed Delivered Energy shall be zero (0)]. [***For a non-solar or non-wind resource:*** The amount shall be calculated as the difference between (a) the product of (i) the lesser of (A) the arithmetic average of the Facility’s metered output rate, in MW, for the twenty-four (24) hour periods immediately before and after such Curtailment Period or other applicable event, or (B) the Guaranteed Capacity, multiplied by (ii) the duration of such Curtailment Period or other applicable event, less (b) the amount of Delivered Energy delivered to the Delivery Point during the Curtailment Period or other applicable event, if any; provided that, if the applicable difference is negative, the Deemed Delivered Energy shall be zero (0).]

“**Defaulting Party**” has the meaning set forth in Section 11.1(a).

“**Deficient Month**” has the meaning set forth in Section 4.8(e).

“**Delivery Point**” means the PNode designated by the CAISO for the Facility.

“**Delivery Term**” shall mean the period of Contract Years specified on the Cover Sheet, beginning on the Commercial Operation Date, unless terminated earlier in accordance with the terms and conditions of this Agreement.

“**Development Cure Period**” has the meaning set forth in Exhibit B.

“**Development Security**” means (i) cash or (ii) a Letter of Credit in the amount specified on the Cover Sheet, deposited with Buyer in conformance with Section 8.7.

“**Diverse Business Enterprises**” means a women, minority, disabled veteran, lesbian, gay, bisexual and /or transgender business enterprise, as more particularly set forth in CPUC General Order 156.

“**Early Termination Date**” has the meaning set forth in Section 11.2.

“**Effective Date**”has the meaning set forth on the Preamble.

“**Electrical Losses**” means all transmission or transformation losses between the Facility and the Delivery Point.

[***For a solar or wind resource***: “**Eligible Intermittent Resources Protocol**” or “**EIRP**” has the meaning set forth in the CAISO Tariff].

“**Eligible Renewable Energy Resource**” has the meaning set forth in California Public Utilities Code Section 399.12(e) and California Public Resources Code Section 25741(a), as either code provision is amended or supplemented from time to time.

“**Energy**” means metered electrical energy, measured in MWh, which is produced by the Facility.

“**Energy Supply Bid**” has the meaning set forth in the CAISO Tariff.

“**Estimated Placed-In-Service Date**” has the meaning set forth in Section 2.1(b).

“**Event of Default**” has the meaning set forth in Section 11.1.

“**Excess MWh**” has the meaning set forth in Section 3.3(c).

“**Expected Energy**” has the meaning set forth in Section 4.7.

“**Facility**” means the facility described more fully in Exhibit A attached hereto.

“**FCDS Deficiency Notice**” has the meaning set forth in Section 2.1(b).

“**FERC**” means the Federal Energy Regulatory Commission or any successor government agency.

“**Flexible Capacity**” has the meaning set forth in the CAISO Tariff.

“**Flexible Capacity Category**” has the definition in Appendix A of the CAISO Tariff.

“**Flexible Resource Adequacy Benefits**” means the attributes, however defined, of a resource that can be used to satisfy the flexible resource adequacy obligations of a load serving entity, including Flexible Capacity.

“**FMM Schedule**” has the meaning set forth in the CAISO Tariff.

“**Force Majeure Event**” has the meaning set forth in Section 10.1.

“**Forced Facility Outage**” means an unexpected failure of one or more components of the Facility or any outage on the Transmission System that prevents Seller from making power available at the Delivery Point and that is not the result of a Force Majeure Event.

“**Forced Labor**” has the meaning set forth in Section 13.3(d).

“**Forward Certificate Transfers**” has the meaning set forth in the WREGIS Operating Rules.

“**Full Capacity Deliverability Status**” or “**FCDS**” has the meaning set forth in the CAISO Tariff.

“**Full Network Model**” has the meaning set forth in the CAISO Tariff.

“**Future Environmental Attributes**” shall mean any and all emissions, air quality or other environmental attributes (other than Green Attributes or Renewable Energy Incentives) under the RPS regulations and/or under any and all other international, federal, regional, state or other law, rule, regulation, bylaw, treaty or other intergovernmental compact, decision, administrative decision, program (including any voluntary compliance or membership program), competitive market or business method (including all credits, certificates, benefits, and emission measurements, reductions, offsets and allowances related thereto) that are attributable, now, or in the future, to the generation of electrical energy by the Facility. Future Environmental Attributes do not include (i) any energy, capacity, reliability or other power attributes from the Facility, (ii) production tax credits associated with the construction or operation of the Facility and other financial incentives in the form of credits, reductions, or allowances associated with the Facility that are applicable to a state or federal income taxation obligation, (iii) fuel-related subsidies or “tipping fees” that may be paid to Seller to accept certain fuels, or local subsidies received by the generator for the destruction of particular preexisting pollutants or the promotion of local environmental benefits, or (iv) emission reduction credits encumbered or used by the Facility for compliance with local, state, or federal operating and/or air quality permits.

“**Gains**” means, with respect to any Party, an amount equal to the present value of the economic benefit to it, if any (exclusive of Costs), resulting from the termination of this Agreement for the remaining Contract Term, determined in a commercially reasonable manner. Factors used in determining the economic benefit to a Party may include, without limitation, reference to information supplied by one or more third parties, which shall exclude Affiliates of the Non-Defaulting Party, including without limitation, quotations (either firm or indicative) of relevant rates, prices, yields, yield curves, volatilities, spreads or other relevant market data in the relevant markets, comparable transactions, forward price curves based on economic analysis of the relevant markets, settlement prices for comparable transactions at liquid trading hubs (e.g., NP-15), all of which should be calculated for the remaining Contract Term, and includes the value of Green Attributes and Capacity Attributes.

“**GHG Regulations**” means Title 17, Division 3 (Air Resources), Chapter 1 (Air Resources Board), Subchapter 10 (Climate Change), Article 5 (Emissions Cap), Sections 95800 to 96023 of the California Code of Regulations, as amended or supplemented from time to time.

“**Governmental Authority**” means any federal, state, provincial, local or municipal government, any political subdivision thereof or any other governmental, congressional or parliamentary, regulatory, or judicial instrumentality, authority, body, agency, department, bureau, or entity with authority to bind a Party at law, including CAISO; *provided*, *however*, that “Governmental Authority” shall not in any event include any Party.

“**Green Attributes**” means any and all credits, benefits, emissions reductions, offsets, and allowances, howsoever entitled, attributable to the generation from the Facility, and its displacement of conventional Energy generation. Green Attributes include but are not limited to Renewable Energy Credits, as well as: (1) any avoided emissions of pollutants to the air, soil or water such as sulfur oxides (SOx), nitrogen oxides (NOx), carbon monoxide (CO) and other pollutants; (2) any avoided emissions of carbon dioxide (CO2), methane (CH4), nitrous oxide, hydrofluorocarbons, perfluorocarbons, sulfur hexafluoride and other greenhouse gases (GHGs) that have been determined by the United Nations Intergovernmental Panel on Climate Change, or otherwise by Law, to contribute to the actual or potential threat of altering the Earth’s climate by trapping heat in the atmosphere; (3) the reporting rights to these avoided emissions, such as Green Tag Reporting Rights. Green Tags are accumulated on a MWh basis and one Green Tag represents the Green Attributes associated with one (1) MWh of Energy. Green Attributes do not include (i) any energy, capacity, reliability or other power attributes from the Facility, (ii) production tax credits associated with the construction or operation of the Facility and other financial incentives in the form of credits, reductions, or allowances associated with the Facility that are applicable to a state or federal income taxation obligation, (iii) fuel-related subsidies or “tipping fees” that may be paid to Seller to accept certain fuels, or local subsidies received by the generator for the destruction of particular preexisting pollutants or the promotion of local environmental benefits, or (iv) emission reduction credits encumbered or used by the Facility for compliance with local, state, or federal operating and/or air quality permits. If the Facility is a biomass or landfill gas facility and Seller receives any tradable Green Attributes based on the greenhouse gas reduction benefits or other emission offsets attributed to its fuel usage, it shall provide Buyer with sufficient Green Attributes to ensure that there are zero net emissions associated with the production of electricity from the Facility.

“**Green Tag Reporting Rights**” means the right of a purchaser of renewable energy to report ownership of accumulated “green tags” in compliance with and to the extent permitted by applicable Law and include, without limitation, rights under Section 1605(b) of the Energy Policy Act of 1992, and any present or future federal, state or local certification program or emissions trading program, including pursuant to the WREGIS Operating Rules.

“**Greenhouse Gas**” or “**GHG**” has the meaning set forth in the GHG Regulations or in any other applicable Laws.

“**Green-e Certified**” means the Green Attributes provided to Buyer pursuant to this Agreement are certified under the Green-e Energy National Standard.

“**Green-e Energy National Standard**” means the Green-e Renewable Energy Standard for Canada and the United States (formerly Green-e Energy National Standard) version 3.5, updated December 15, 2020, as may be further amended from time to time.

“**Guaranteed Capacity**” means **[\_\_\_\_\_]** MW AC capacity measured at the Delivery Point.

“**Guaranteed RA Capacity**” means the Guaranteed Capacity.

“**Guaranteed Commercial Operation Date**” has the meaning set forth in Exhibit B.

“**Guaranteed Construction Start Date**” has the meaning set forth in Exhibit B.

“**Guaranteed Energy Production**” has the meaning set forth in Section 4.7.

“**Imbalance Energy**” means the amount of Energy, in any given Settlement Period or Settlement Interval, by which the amount of Metered Energy deviates from the amount of Scheduled Energy.

“**Indemnified Party**” has the meaning set forth in Section 17.1.

“**Indemnifying Party**” has the meaning set forth in Section 17.1.

“**Initial Synchronization**” means the initial delivery of Energy from the Facility to the interconnection point specified in the Interconnection Agreement.

“**Installed Capacity**” means the actual generating capacity of the Facility, measured at the Facility PNode and adjusted for ambient conditions on the date of the performance test, not to exceed the Guaranteed Capacity, as evidenced by a certificate substantially in the form attached as Exhibit G-2 hereto provided by Seller to Buyer.

“**Inter-SC Trade**” or “**IST**” has the meaning set forth in the CAISO Tariff.

“**Interconnection Agreement**” means the interconnection agreement entered into by Seller pursuant to which the Facility will be interconnected with the Transmission System, and pursuant to which Seller’s Interconnection Facilities and any other Interconnection Facilities will be constructed, operated and maintained during the Contract Term.

“**Interconnection Delay Notice**” has the meaning set forth in Section 2.1(b).

“**Interconnection Facilities**” means the interconnection facilities, control and protective devices and metering facilities required to connect the Facility with the Transmission System (or PTO’s distribution system, as applicable) in accordance with the Interconnection Agreement.

“**Interest Rate**”has the meaning set forth in Section 8.2.

“**Joint Powers Act**” means the Joint Exercise of Powers Act of the State of California (Government Code Section 6500 et seq.).

“**Joint Powers Agreement**” means that certain Joint Powers Agreement dated February 29, 2016 under which Buyer is organized as a Joint Powers Authority in accordance with the Joint Powers Act.

“**Law**” means any applicable law, statute, rule, regulation, decision, writ, order, decree or judgment, permit or any interpretation thereof, promulgated or issued by a Governmental Authority, and includes the CAISO Tariff.

“**Lender**” means, collectively, (A) in the case of Seller, any Person (i) providing senior or subordinated construction, interim or long-term debt, equity or tax equity financing or refinancing for or in connection with the development, construction, purchase, installation or operation of the Facility, whether that financing or refinancing takes the form of private debt, equity, public debt or any other form (including financing or refinancing provided to a member or other direct or indirect owner of Seller), including any equity or tax equity investor directly or indirectly providing financing or refinancing for the Facility or purchasing equity ownership interests of Seller and/or its Affiliates, and any trustee or agent acting on their behalf, (ii) providing interest rate or commodity protection under an agreement hedging or otherwise mitigating the cost of any of the foregoing obligations and/or (iii) participating in a lease financing (including a sale leaseback or leveraged leasing structure) with respect to the Facility, and (B) in the case of Buyer, any Person (i) providing senior or subordinated short-term or long-term debt or equity financing or refinancing for or in connection with the business or operations of Buyer, whether that financing or refinancing takes the form of private debt, equity, public debt or any other form, and any trustee or agent acting on their behalf, and/or (ii) providing interest rate or commodity protection under an agreement hedging or otherwise mitigating the cost of any of the foregoing obligations.

“**Letter(s) of Credit**” means one or more irrevocable, standby letters of credit issued by a U.S. commercial bank or a foreign bank with a U.S. branch with such bank having a Credit Rating of at least A- with an outlook designation of “stable” from S&P or A3 with an outlook designation of “stable” from Moody’s, in a form substantially similar to the letter of credit set forth in Exhibit I.

“**Licensed Professional Engineer**” means an independent, professional engineer (a) reasonably acceptable to Buyer, (b) who has been retained by, or for the benefit of, the Lenders, as their “independent engineer” for the purpose of financing the Facility, or (c) who (i) is licensed to practice engineering in the State of California, (ii) has training and experience in the power industry specific to the technology of the Facility, (iii) is licensed in an appropriate engineering discipline for the required certification being made, and (iv) unless otherwise approved by Buyer, is not a representative of a consultant, engineer, contractor, designer or other individual involved in the development of the Facility or of a manufacturer or supplier of any equipment installed at the Facility.

“**Local Capacity Area**” has the meaning set forth in the CAISO Tariff.

“**Local Capacity Area Resource**” has the meaning set forth in the CAISO Tariff.

“**Local Capacity Area Resource Adequacy Benefits**” means the attributes, however defined, of a Local Capacity Area Resource that can be used to satisfy the local resource adequacy obligations of a load serving entity.

“**Locational Marginal Price**” or “**LMP**” has the meaning set forth in the CAISO Tariff.

“**Losses**” means, with respect to any Party, an amount equal to the present value of the economic loss to it, if any (exclusive of Costs), resulting from termination of this Agreement for the remaining Contract Term, determined in a commercially reasonable manner. Factors used in determining economic loss to a Party may include, without limitation, reference to information supplied by one or more third parties, which shall exclude Affiliates of the Non-Defaulting Party, including without limitation, quotations (either firm or indicative) of relevant rates, prices, yields, yield curves, volatilities, spreads or other relevant market data in the relevant markets, comparable transactions, forward price curves based on economic analysis of the relevant markets, settlement prices for comparable transactions at liquid trading hubs (e.g., NYMEX), all of which should be calculated for the remaining Contract Term and must include the value of Green Attributes, Capacity Attributes, and Renewable Energy Incentives.

“**Lost Output**” has the meaning set forth in Exhibit D.

“**Main Power Transformer**” means the Facility’s main step-up transformer as depicted on the one-line diagram set forth in Exhibit A.

“**Metered Energy**” means the electric energy generated by the Facility, expressed in MWh, as recorded by the CAISO Approved Meter(s) and net of all Electrical Losses and Station Use.

“**Milestones**” means the development activities for significant permitting, interconnection, financing and construction milestones set forth in the Cover Sheet.

“**Moody’s**” means Moody’s Investors Service, Inc., or its successor.

“**MW**” means megawatts measured in alternating current, unless expressly stated in terms of direct current.

“**MWh**” means megawatt-hour measured in alternating current, unless expressly stated in terms of direct current.

“**Negative LMP**” means, in any Settlement Period or Settlement Interval, whether in the Day-Ahead Market or Real-Time Market, the LMP is less than zero dollars ($0).

“**Negative LMP Costs**” has the meaning set forth in Section 3.3(c).

“**Network Upgrades**” has the meaning set forth in the CAISO Tariff.

“**Non-Availability Charge**” has the meaning set forth in the CAISO Tariff.

“**Non-Defaulting Party**” has the meaning set forth in Section 11.2.

“**Notice**” shall, unless otherwise specified in this Agreement, mean written communications by a Party to be delivered by hand delivery, United States mail, overnight courier service, facsimile or electronic messaging (e-mail).

“**Other Facility(ies)**” means the electric generating or energy storage facility(ies), other than the Facility, utilizing any facilities shared with the Facility to enable delivery of energy from each such other generating or storage facility to the Delivery Point, together with all materials, equipment systems, structures, features and improvements necessary to produce electric energy at each such other generating or storage facility, but (i) with respect to the Shared Facilities, excluding Seller’s interests therein and (ii) excluding the real property on which each such other generating or storage facility is, or will be located, land rights and interests in land.

“**Participating Transmission Owner**” or “**PTO**” means an entity that owns, operates and maintains transmission or distribution lines and associated facilities and/or has entitlements to use certain transmission or distribution lines and associated facilities where the Facility is interconnected. For purposes of this Agreement, the Participating Transmission Owner is **[\_\_\_\_\_\_\_\_\_]**.

“**Party**” has the meaning set forth in the Preamble.

“**Performance Measurement Period**” has the meaning set forth in Section 4.7.

“**Performance Security**” means (i) cash, or (ii) a Letter of Credit, in the amount specified on the Cover Sheet, deposited with Buyer in conformance with Section 8.8.

“**Performance Security End Date**” has the meaning set forth in Section 8.8.

“**Person**” means any individual, sole proprietorship, corporation, limited liability company, limited or general partnership, joint venture, association, joint-stock company, trust, incorporated organization, institution, public benefit corporation, unincorporated organization, government entity or other entity.

“**PNode**” has the meaning set forth in the CAISO Tariff.

“**Portfolio Content Category 1**” or “**PCC1**” means any Renewable Energy Credit associated with the generation of electricity from an Eligible Renewable Energy Resource consisting of the portfolio content set forth in California Public Utilities Code Section 399.16(b)(1), as may be amended from time to time or as further defined or supplemented by Law.

“**Product**” has the meaning set forth on the Cover Sheet.

“**Progress Report**” means a progress report including the items set forth in Exhibit E.

“**Project**” has the same meaning as Facility.

“**Prudent Operating Practice**” means the practices, methods and standards of professional care, skill and diligence engaged in or approved by a significant portion of the electric power industry in the Western United States for facilities of similar size, type, and design, that, in the exercise of reasonable judgment, in light of the facts known at the time, would have been expected to accomplish results consistent with Law, reliability, safety, environmental protection, applicable codes, and standards of economy and expedition. Prudent Operating Practices are not necessarily defined as the optimal standard practice method or act to the exclusion of others, but rather refer to a range of actions reasonable under the circumstances.

“**Qualified Reporting Entity**” has the meaning set forth in the WREGIS Operating Rules.

“**Qualified Transferee**” means an entity that (a) has a Tangible Net Worth of one hundred fifty million dollars ($150,000,000) or (b) has (i) a Tangible Net Worth of fifty million dollars ($50,000,000) and (ii) a Credit Rating of A2 or higher by Moody’s or A- or higher by S&P, if rated by only one such entity, or a Credit Rating of A2 or higher by Moody’s and A- or higher by S&P, if rated by both such entities, and, in any case, (c) is not a public utility regulated by the CPUC or an Affiliate thereof, and (d) has, or retains to operate the Facility a Person that has, at least five (5) years of experience operating at two (2) or more electricity generating facilities of the same technology and with at least as much Installed Capacity as the Facility.

“**Qualifying Capacity**” has the meaning set forth in the CAISO Tariff.

“**RA Deficiency Amount**” means the liquidated damages payment that Seller shall pay to Buyer for an applicable RA Shortfall Month as calculated in accordance with Section 3.9(b).

“**RA Guarantee Date**” means the Commercial Operation Date.

“**RA Plan**” has the meaning set forth for “Resource Adequacy Plan” in the CAISO Tariff.

“**RA Shortfall**” means the difference, expressed in kW, of (i) the Facility’s Qualifying Capacity minus (ii) the Resource Adequacy Benefits of the Facility for such month able to be shown on Buyer’s monthly or annual RA Plan to the CAISO and CPUC and counted as Resource Adequacy Benefits.

“**RA Shortfall Month**” means the applicable calendar month following the RA Guarantee Date during which Seller fails to provide Resource Adequacy Benefits in an amount equal to the Facility’s Qualifying Capacity as required hereunder for purposes of calculating an RA Deficiency Amount under Section 3.9(b).

“**RA Substitute Capacity**” has the meaning set forth in the CAISO Tariff.

“**Real-Time Market**” has the meaning set forth in the CAISO Tariff.

“**Remedial Action Plan**” has the meaning set forth in Section 2.4.

“**Renewable Energy Credit**” has the meaning set forth in California Public Utilities Code Section 399.12(h), as may be amended from time to time or as further defined or supplemented by Law.

“**Renewable Energy Incentives**” means: (a) all federal, state, or local Tax credits or other Tax benefits associated with the construction, ownership, or production of electricity from the Facility (including credits under Sections 38, 45, 46 and 48 of the Internal Revenue Code of 1986, as amended); (b) any federal, state, or local grants, subsidies or other like benefits relating in any way to the Facility, including a cash grant available under Section 1603 of Division B of the American Recovery and Reinvestment Act of 2009, provided in lieu of federal Tax credits or any similar or substitute payment available under subsequently enacted federal legislation; and (c) any other form of incentive relating in any way to the Facility that are not a Green Attribute or a Future Environmental Attribute.

“**Replacement RA**” means Resource Adequacy Benefits equivalent to those that would have been provided by the Facility with respect to the applicable month for which a the Replacement RA is being provided. Replacement RA shall (a) include, if applicable, Flexible Resource Adequacy Benefits that are of the same system or local designation, Flexible Capacity Category, and Resource Category as the Facility; (b) be from a resource located in the same Transmission Access Charge Area (as described in the CAISO Tariff) as the Facility, (c) to the extent that the Facility would have qualified as a Local Capacity Area Resource for such month, be located in the same Local Capacity Area as the Facility, and (d) provides Resource Adequacy Benefits in the same hourly periods as the Facility. Replacement RA shall not be provided from any generating facility or unit that utilizes coal or coal materials as a source of fuel.

“**Resource Adequacy Benefits**” means the rights and privileges attached to the Facility that satisfy any entity’s resource adequacy obligations, as those obligations are set forth in CPUC Decisions 04-01-050, 04-10-035, 05-10-042, 06-06-064, 06-07-031, 07-06-029, 08-06-031, 09-06-028, 10-06-036, 11-06-022, 12-06-025, 13-06-024, 14-06-050, 15-06-063, 16-06-045, 17-06-027, 19-10-021, and any subsequent CPUC ruling or decision or by any other entity including CAISO, and shall include System Resource Adequacy Benefits, Flexible Resource Adequacy Benefits and Local Capacity Area Resource Adequacy Benefits associated with the Facility.

“**Resource Category**” means the maximum cumulative capacity and resource categories (commonly known as "MCC buckets") for system and local resource adequacy as well as categories of must-offer for flexible resource adequacy described in the most recent filing guide for system, local, and flexible resource adequacy compliance filings issued or published on the CPUC’s website by the CPUC or its staff specifying the guidelines, requirements, and instructions for load serving entities to demonstrate compliance with the CPUC’s resource adequacy program.

“**S&P**” means the Standard & Poor’s Financial Services, LLC (a subsidiary of The McGraw-Hill Companies, Inc.) or its successor.

“**Schedule**” has the meaning set forth in the CAISO Tariff.

“**Scheduled Energy**” means the Energy reflected in a final Day-Ahead Schedule, FMM Schedule, and/or any other financially binding Schedule, market instruction or dispatch for the Facility for a given period of time.

“**Scheduled Maintenance**” has the meaning set forth in Section 6.1(a).

“**Scheduling Coordinator**” or “**SC**” means an entity certified by the CAISO as qualifying as a Scheduling Coordinator pursuant to the CAISO Tariff for the purposes of undertaking the functions specified in “Responsibilities of a Scheduling Coordinator,” of the CAISO Tariff, as amended from time to time.

“**Security Interest**” has the meaning set forth in Section 8.9.

“**Self-Schedule**” has the meaning set forth in the CAISO Tariff.

“**Seller**” has the meaning set forth on the Cover Sheet.

“**Seller’s WREGIS Account**” has the meaning set forth in Section 4.8(a).

“**Settlement Amount**” means the Non-Defaulting Party’s Costs and Losses, on the one hand, netted against its Gains, on the other. If the Non-Defaulting Party’s Costs and Losses exceed its Gains, then the Settlement Amount shall be an amount owing to the Non-Defaulting Party. If the Non-Defaulting Party’s Gains exceed its Costs and Losses, then the Settlement Amount shall be zero dollars ($0).

“**Settlement Interval**” has the meaning set forth in the CAISO Tariff.

“**Settlement Period**” has the meaning set forth in the CAISO Tariff, which as of the Effective Date is the period beginning at the start of the hour and ending at the end of the hour.

“**Shared Facilities**” means the gen-tie lines, transformers, substations, or other equipment, permits, contract rights, and other assets and property (real or personal), in each case, as necessary to enable delivery of energy to the Delivery Point, including the Interconnection Facilities and the Interconnection Agreement itself, if applicable, that are used in common with third parties or by Seller for electric generation or storage facilities owned by Seller other than the Facility.

**“Showing Deadline”** means the initial deadline that a Scheduling Coordinator must meet to submit its RA Plan, as established by CAISO or any other Governmental Authority. For illustrative purposes only, the CAISO monthly Showing Deadline is approximately 45 days prior to the RA delivery month.

“**Site**” means the real property on which the Facility is or will be located, as further described in Exhibit A, and as shall be updated by Seller at the time Seller provides an executed Construction Start Date Certificate to Buyer, in substantially the form of the Form of Construction Start Date Certificate in Exhibit H.

“**Site Control**” means that Seller: (a) owns or has the option to purchase the Site; (b) is the lessee or has the option to lease the Site; or (c) is the holder of an easement or an option for an easement, right-of-way grant, or similar instrument with respect to the Site.

“**Station Use**” has the meaning given in the tariff of the retail provider of energy for the Facility and reflects:

* 1. the electric energy that is used within the Facility (including to power the lights, motors, control systems, thermal regulation equipment and other electrical loads) and that is necessary for operation of the Facility; and
	2. the electric energy that is consumed within the Facility’s electric energy distribution system as losses (other than any losses that are Electrical Losses).

“**System Emergency**” means any condition that: (a) requires, as determined and declared by CAISO or the PTO, automatic or immediate action to (i) prevent or limit harm to or loss of life or property, (ii) prevent loss of transmission facilities or generation supply in the immediate vicinity of the Facility, or (iii) preserve Transmission System reliability, and (b) directly affects the ability of any Party to perform under any term or condition in this Agreement, in whole or in part.

**“System Resource Adequacy Benefits”** means the attributes, however defined, of a resource that can be used to satisfy the resource adequacy obligations of a load serving entity, other than Flexible Resource Adequacy Benefits and Local Capacity Area Resource Adequacy Benefits.

“**Tangible Net Worth**” means the tangible assets (for example, not including intangibles such as goodwill and rights to patents or royalties) that remain after deducting liabilities as determined in accordance with generally accepted accounting principles.

“**Tax**” or “**Taxes**” means all U.S. federal, state and local and any foreign taxes, levies, assessments, surcharges, duties and other fees and charges of any nature imposed by a Governmental Authority, whether currently in effect or adopted during the Contract Term, including ad valorem, excise, franchise, gross receipts, import/export, license, property, sales and use, stamp, transfer, payroll, unemployment, income, and any and all items of withholding, deficiency, penalty, additions, interest or assessment related thereto.

“**Terminated Transaction**” has the meaning set forth in Section 11.2.

“**Termination Payment**” has the meaning set forth in Section 11.3.

“**Test Energy**” means the Energy delivered (a) commencing on the later of (i) the first date that the CAISO informs Seller in writing that Seller may deliver Energy from the Facility to the CAISO and (ii) the first date that the PTO informs Seller in writing that Seller has conditional or temporary permission to parallel and (b) ending upon the occurrence of the Commercial Operation Date.

“**Transmission System**” means the transmission facilities operated by the CAISO, now or hereafter in existence, which provide energy transmission service downstream from the Delivery Point.

“**Ultimate Parent**” means the entity that Controls, directly or indirectly, Seller and that is not Controlled by any other entity. As of the Effective Date, the Ultimate Parent is \_\_\_\_\_\_\_\_\_.

[***For solar or wind resources***: “**Variable Energy Resource**” or “**VER**” has the meaning set forth in the CAISO Tariff].

[***For solar or wind resources***: “**Variable Energy Resource Forecast**” or “**VER Forecast**” means, for a given period, the final forecast of the Energy to be produced by the Facility prepared by the CAISO in accordance with the Eligible Intermittent Resources Protocol.]

“**WECC**” means the Western Electricity Coordinating Council or its successor.

“**WREGIS**” means the Western Renewable Energy Generation Information System or any successor renewable energy tracking program.

“**WREGIS Certificate Deficit**” has the meaning set forth in Section 4.8(e).

“**WREGIS Certificates**” has the same meaning as “Certificate” as defined by WREGIS in the WREGIS Operating Rules and are designated as eligible for complying with the California Renewables Portfolio Standard.

“**WREGIS Operating Rules**” means those operating rules and requirements adopted by WREGIS as of January 4, 2021, as subsequently amended, supplemented or replaced (in whole or in part) from time to time.

## Rules of Interpretation. In this Agreement, except as expressly stated otherwise or unless the context otherwise requires:

* + 1. headings and the rendering of text in bold and italics are for convenience and reference purposes only and do not affect the meaning or interpretation of this Agreement;
		2. words importing the singular include the plural and vice versa and the masculine, feminine and neuter genders include all genders;
		3. the words “hereof”, “herein”, and “hereunder” and words of similar import shall refer to this Agreement as a whole and not to any particular provision of this Agreement;
		4. a reference to an Article, Section, paragraph, clause, Party, or Exhibit is a reference to that Section, paragraph, clause of, or that Party or Exhibit to, this Agreement unless otherwise specified;
		5. a reference to a document or agreement, including this Agreement shall mean such document, agreement or this Agreement including any amendment or supplement to, or replacement, novation or modification of this Agreement, but disregarding any amendment, supplement, replacement, novation or modification made in breach of such document, agreement or this Agreement;
		6. a reference to a Person includes that Person’s successors and permitted assigns;
		7. the term “including” means “including without limitation” and any list of examples following such term shall in no way restrict or limit the generality of the word or provision in respect of which such examples are provided;
		8. references to any statute, code or statutory provision are to be construed as a reference to the same as it may have been, or may from time to time be, amended, modified or reenacted, and include references to all bylaws, instruments, orders and regulations for the time being made thereunder or deriving validity therefrom unless the context otherwise requires;
		9. in the event of a conflict, a mathematical formula or other precise description of a concept or a term shall prevail over words providing a more general description of a concept or a term;
		10. references to any amount of money shall mean a reference to the amount in United States Dollars, and references to a LMP shall mean the LMP at the Delivery Point unless expressly provided otherwise;
		11. the expression “and/or” when used as a conjunction shall connote “any or all of”;
		12. words, phrases or expressions not otherwise defined herein that (i) have a generally accepted meaning in Prudent Operating Practice shall have such meaning in this Agreement or (ii) do not have well known and generally accepted meaning in Prudent Operating Practice but that have well known and generally accepted technical or trade meanings, shall have such recognized meanings; and
		13. each Party acknowledges that it was represented by counsel in connection with this Agreement and that it or its counsel reviewed this Agreement and that any rule of construction to the effect that ambiguities are to be resolved against the drafting party shall not be employed in the interpretation of this Agreement.

# TERM; CONDITIONS PRECEDENT

## Contract Term.

* + 1. The term of this Agreement shall commence on the Effective Date and shall remain in full force and effect until the conclusion of the Delivery Term, subject to any early termination provisions set forth herein (“**Contract Term**”).
		2. ***[NTD: This Section 2.1(b) is only applicable to Facilities that are part of CAISO interconnection queue cluster 14.]*** Seller shall provide Notice to Buyer within ten (10) Business Days of Seller’s receipt of (x) any interconnection study results or tendered Interconnection Agreement that includes an estimated placed-in-service date (“**Estimated Placed-In-Service Date**”) for Seller’s interconnection facilities that is later than the date of Initial Synchronization as set forth in the Milestone schedule on the Cover Sheet (“**Interconnection Delay Notice**”), or (y) any notice from the CAISO of the results of any Deliverability Allocation Process in 2025 informing Seller of the results of Seller’s application for Full Capacity Deliverability Status that awards Seller FCDS for less than one hundred percent (100%) of the Guaranteed RA Capacity (“**FCDS Deficiency Notice**”).

#### If, despite Seller’s commercially reasonable efforts to have the Estimated Placed-In-Service Date be on or before the estimated date of Initial Synchronization as set forth in the Milestone schedule on the Cover Sheet, such Estimated Placed-In-Service Date is not more than ninety (90) days after the date of Initial Synchronization as set forth in the Milestone schedule on the Cover Sheet, the Initial Synchronization Milestone date and all subsequent Milestone dates shall be extended by the number of days by which the Estimated Placed-In-Service Date is later than the Initial Synchronization Milestone date.

#### If, despite Seller’s commercially reasonable efforts to have the Estimated Placed-In-Service Date be on or before the estimated date of Initial Synchronization as set forth in the Milestone schedule on the Cover Sheet, such Estimated Placed-In-Service Date is more than ninety (90) days after the date of Initial Synchronization as set forth in the Milestone schedule on the Cover Sheet, then Buyer shall have the right to terminate this Agreement by providing Notice to Seller within ninety (90) days after Buyer’s receipt of the Interconnection Delay Notice, and retain fifty percent (50%) of the Development Security as liquidated damages.

#### If, despite Seller’s commercially reasonable efforts to obtain FCDS for one hundred percent (100%) of the Guaranteed RA Capacity, Seller receives FCDS for less than one hundred percent (100%) but for ninety percent (90%) or more of the Guaranteed RA Capacity, then the Parties shall negotiate in good faith to reduce the Guaranteed PV Capacity and/or the Guaranteed Storage Capacity (and the Guaranteed RA Capacity accordingly) in a way that maximizes the amount of Resource Adequacy Benefits the Facility is qualified to provide, with no liability or cost to Seller (including no Capacity Damages).

#### If, despite Seller’s commercially reasonable efforts to obtain FCDS for one hundred percent (100%) of the Guaranteed RA Capacity, Seller receives FCDS for less than ninety percent (90%) of the Guaranteed RA Capacity, then Buyer shall have the right to terminate this Agreement by providing Notice to Seller within ninety (90) days after Buyer’s receipt of the FCDS Deficiency Notice, and retain fifty percent (50%) of the Development Security as liquidated damages.

* + 1. Applicable provisions of this Agreement shall continue in effect after termination, including early termination, to the extent necessary to enforce or complete the duties, obligations or responsibilities of the Parties arising prior to termination. The confidentiality obligations of the Parties under Article 19 shall remain in full force and effect for three (3) years following the termination of this Agreement, and all indemnity and audit rights shall remain in full force and effect for two (2) years following the termination of this Agreement.

## Conditions Precedent. The Delivery Term shall not commence until Seller completes each of the following conditions:

* + 1. Seller shall have delivered to Buyer certificates from a Licensed Professional Engineer substantially in the form of Exhibits G-1 and G-2;
		2. A Participating Generator Agreement and a Meter Service Agreement between Seller and CAISO shall have been executed and delivered and be in full force and effect, and a copy of each such agreement delivered to Buyer;
		3. An Interconnection Agreement between Seller and the PTO shall have been executed and delivered and be in full force and effect and a copy of the Interconnection Agreement, including all modifications and amendments thereto, delivered to Buyer;
		4. Authorization to parallel the Facility was obtained by the Participating Transmission Owner prior to the Delivery Commencement Date.
		5. The Transmission Provider has provided documentation supporting full unrestricted release for Commercial Operation by the Delivery Commencement Date.
		6. The CAISO has provided notification supporting Commercial Operation.
		7. The Facility is providing Resource Adequacy Benefits to Buyer for the month in which Delivery Term commences;
		8. Buyer, or its designee, is the Scheduling Coordinator for the Facility; provided that if this requirement is not met because of Buyer’s (or its designee’s) actions or failure to take actions, and this is the only requirement for Delivery Commencement that has not been met, Seller shall be entitled to a day for day extension of the Guaranteed Delivery Commencement Date for such Buyer (or its designee) actions or failure to act.
		9. Seller shall have delivered to Buyer a copy of all environmental impact reports, studies or assessments prepared by or obtained by Seller or its Affiliates, the conditional use permit or other principal land use approval for the Facility, and a certificate signed by an authorized representative of Seller stating that Seller is in compliance with the requirements of the conditional use permit or other principal land use approval;
		10. Seller has received CEC Precertification;
		11. Seller (with the reasonable participation of Buyer) shall have completed all applicable WREGIS registration requirements, including the completion and submittal of all applicable registration forms and supporting documentation, which may include applicable interconnection agreements, informational surveys related to the Facility, Qualified Reporting Entity service agreements, and other appropriate documentation required to effect Facility registration with WREGIS and to enable Renewable Energy Credit transfers related to the Facility within the WREGIS system;
		12. Seller shall have caused the Facility to be included in the Full Network Model and has ability to offer Bids into CAISO Day-Ahead Markets and Real-Time Markets in respect of the Facility.
		13. Seller shall have completed all necessary steps to provide Ancillary Services from the Facility, including completing the certification requirements in Section 8 and Appendix K of the CAISO Tariff;
		14. Seller has delivered to Buyer a copy of the most recent generation resource report (including as prepared by an independent engineer in connection with the financing of the construction or permanent operation of the Facility);
		15. Seller has delivered the Performance Security to Buyer;
		16. Seller has paid Buyer for all Daily Delay Damages and Commercial Operation Delay Damages owing under this Agreement, if any; and
		17. Seller has delivered to Buyer a plan that is reasonably acceptable to Buyer for the proper recycling and disposal of all project components, equipment, and materials at the end of the useful life of the Facility.

## Progress Reports. Within fifteen (15) days after the close of (i) each calendar quarter from the first calendar quarter following the Effective Date until the Construction Start Date, and (ii) each calendar month from the first calendar month following the Construction Start Date until the Commercial Operation Date, Seller shall provide to Buyer a Progress Report and agree to regularly scheduled meetings between representatives of Buyer and Seller to review such reports and discuss Seller’s construction progress. The form of the Progress Report is set forth in Exhibit E. Seller shall also provide Buyer with any reasonably requested documentation directly related to the achievement of Milestones within ten (10) Business Days of receipt of such request by Seller.

## Remedial Action Plan. If Seller misses two (2) or more Milestones, or misses any one (1) by more than thirty (30) days, Seller shall submit to Buyer, within ten (10) Business Days of such missed Milestone completion date (or the ninetieth (90th) day after the missed Milestone completion date, as applicable), a remedial action plan (“**Remedial Action Plan**”), which will describe in detail any delays (actual or anticipated) beyond the scheduled Milestone dates, including the cause of the delay (e.g., governmental approvals, financing, property acquisition, design activities, equipment procurement, project construction, interconnection, or any other factor), and Seller’s detailed description of its proposed course of action to achieve the missed Milestones and all subsequent Milestones by the Guaranteed Commercial Operation Date; provided, that delivery of any Remedial Action Plan shall not relieve Seller of its obligation to provide Remedial Action Plans with respect to any subsequent Milestones and to achieve the Guaranteed Commercial Operation Date in accordance with the terms of this Agreement. If the missed Milestone(s) is not the Guaranteed Construction Start Date or the Guaranteed Commercial Operation Date, and so long as Seller complies with its obligations under this Section 2.4, then Seller shall not be considered in default of its obligations under this Agreement as a result of missing such Milestone(s).

# PURCHASE AND SALE

## Sale of Product.

Subject to the terms and conditions of this Agreement, during the Delivery Term, Seller shall sell and deliver to Buyer, and Buyer shall purchase and receive from Seller at the Contract Price, all of the Product produced by the Facility. Buyer shall re-sell all of the Energy purchased hereunder, and may, at its sole discretion, re-sell or use for another purpose all or a portion of the remainder of the Product, provided that such resale or use for another purpose will not relieve Buyer of any of its obligations under this Agreement.

Except for Deemed Delivered Energy, Buyer has no obligation to pay Seller for any Product that is not delivered to the Delivery Point as a result of any circumstance, including, an outage of the Facility, a Force Majeure Event, or a Curtailment Order. In no event shall Seller have the right to procure any element of the Product from sources other than the Facility for sale or delivery to Buyer under this Agreement, except with respect to Replacement RA.

## Sale of Green Attributes. Seller shall sell and deliver to Buyer, and Buyer shall purchase and receive from Seller, all of the Green Attributes produced by the Facility during the Delivery Term, and any Green Attributes associated with Test Energy.

## Compensation. Buyer shall compensate Seller for the Product in accordance with this Section 3.3.

* + 1. Buyer shall pay Seller the Contract Price for each MWh of Product, as measured by the amount of Metered Energy that qualifies as PCC1 and is delivered to the Delivery Point, plus Deemed Delivered Energy, if any, up to one hundred ten percent (110%) of the Expected Energy for such Contract Year.
		2. If, at any point in any Contract Year, the amount of Metered Energy plus the amount of Deemed Delivered Energy exceeds one hundred ten percent (110%) of the Expected Energy for such Contract Year, for each additional MWh of Product, as measured by the amount of Metered Energy plus Deemed Delivered Energy, if any, delivered to Buyer in such Contract Year, the price to be paid shall be the lesser of (i) fifty percent (50%) of the Contract Price or (ii) the Day-Ahead LMP for the applicable Settlement Interval. If, at any point in any Contract Year, the amount of Metered Energy delivered to the Delivery Point plus the amount of Deemed Delivered Energy exceeds one hundred and fifteen percent (115%) of the Expected Energy for such Contract Year, no payment shall be owed by Buyer for any additional Metered Energy or Deemed Delivered Energy.
		3. If during any Settlement Interval, Seller delivers Product in amounts, as measured by the amount of Metered Energy, in excess of the product of the Installed Capacity and the duration of the Settlement Interval, expressed in hours (“**Excess MWh**”), then the price applicable to all such Excess MWh in such Settlement Interval shall be zero dollars ($0), and if there is a Negative LMP during such Settlement Interval, Seller shall pay to Buyer an amount equal to the absolute value of the Negative LMP times the number of such Excess MWh (“**Negative LMP Costs**”).

## Imbalance Energy.

* + 1. Buyer and Seller recognize that from time to time the amount of Metered Energy will deviate from the amount of Scheduled Energy. Buyer and Seller shall cooperate to minimize charges and imbalances associated with Imbalance Energy to the extent possible. Subject to Section 3.4(b), to the extent there are such deviations, any CAISO costs or revenues assessed as a result of such Imbalance Energy shall be solely for the account of Buyer.
		2. If Seller is not in compliance with [***For solar or wind resources only***: EIRP or] any applicable provisions of this Agreement, including Section 4.4(d), or if Imbalance Energy results from any outage or reduction in the availability of the Facility that is not communicated to Buyer at least one hour prior to the deadline to submit Schedules to CAISO, then Seller will be responsible for and shall pay directly or promptly reimburse Buyer (and Buyer may offset amounts owed to Seller) for the aggregate Imbalance Energy charges assessed, net of the aggregate Imbalance Energy revenues earned, during such period of noncompliance and reasonably attributable to such noncompliance within the applicable Contract Year. At Buyer’s request, Seller will cooperate with Buyer to develop a written administrative protocol to effectuate the Parties’ agreement with respect to Imbalance Energy and scheduling.

## Ownership of Renewable Energy Incentives. Seller shall have all right, title and interest in and to all Renewable Energy Incentives. Buyer acknowledges that any Renewable Energy Incentives belong to Seller. If any Renewable Energy Incentives, or values representing the same, are initially credited or paid to Buyer, Buyer shall cause such Renewable Energy Incentives or values relating to same to be assigned or transferred to Seller without delay. Buyer shall reasonably cooperate with Seller, at Seller’s sole expense, in Seller’s efforts to meet the requirements for any certification, registration, or reporting program relating to Renewable Energy Incentives.

## Future Environmental Attributes.

* + 1. The Parties acknowledge and agree that as of the Effective Date, Future Environmental Attributes may be created by a Governmental Authority through Laws enacted after the Effective Date. Buyer shall have the right to obtain such Future Environmental Attributes without any adjustment to the Contract Price paid by Buyer under this Agreement. Subject to Section 3.13, Seller shall take all reasonable actions necessary to realize the full value of such Future Environmental Attributes for the benefit of Buyer, and shall cooperate with Buyer in Buyer’s efforts to do the same.
		2. If Buyer elects to receive Future Environmental Attributes pursuant to Section 3.6(a), the Parties agree to negotiate in good faith with respect to the development of further agreements and documentation necessary to effectuate the transfer of such Future Environmental Attributes, including agreement with respect to (i) appropriate transfer, delivery and risk of loss mechanisms, and (ii) appropriate allocation of any incremental expenses incurred by Seller (not including Seller’s overhead costs for administrative tasks) associated with providing such Future Environmental Attributes; *provided*, that the Parties acknowledge and agree that such terms are not intended to alter the other material terms of this Agreement.

## Test Energy. No less than fourteen (14) days prior to the first day on which Test Energy is expected to be available from the Facility, Seller shall notify Buyer of the availability of the Test Energy. If and to the extent the Facility generates Test Energy, Seller shall sell and Buyer shall purchase from Seller all Test Energy and any associated Green Attributes and Capacity Attributes on an as-available basis. As compensation for any such Test Energy, Green Attributes, and Capacity Attributes, Buyer shall pay Seller for each MWh of Test Energy an amount equal to fifty percent (50%) of the Contract Price for the first Contract Year.

## Capacity Attributes. Seller shall request Full Capacity Deliverability Status in the CAISO generator interconnection process. As between Buyer and Seller, Seller shall be responsible for the cost and installation of any Network Upgrades associated with obtaining such Full Capacity Deliverability Status.

* + 1. Subject to Section 3.13, Seller grants, pledges, assigns and otherwise commits to Buyer all of the Capacity Attributes from the Facility throughout the Delivery Term, and any Capacity Attributes associated with any Test Energy.
		2. Subject to Section 3.13, Seller shall use commercially reasonable efforts to maintain eligibility for Full Capacity Deliverability Status for the Facility from the CAISO and shall perform all actions necessary to ensure that the Facility qualifies to provide Resource Adequacy Benefits to Seller. Throughout the Delivery Term, and in connection with any Test Energy, subject to Section 3.13, Seller hereby covenants and agrees to transfer all Resource Adequacy Benefits to Buyer.
		3. Subject to Section 3.13, Seller shall take all commercially reasonable actions, including complying with all applicable registration and reporting requirements, and execute any and all documents or instruments necessary to enable Buyer to use all of the Capacity Attributes committed by Seller to Buyer pursuant to this Agreement.
		4. For the duration of the Delivery Term, Seller shall maintain interconnection capacity under its Interconnection Agreement of at least the amount of the Guaranteed Capacity plus the capacities of any Other Facilities.
		5. If, as a result of Scheduled Maintenance or otherwise, CAISO requires RA Substitute Capacity in connection with Seller’s provision of Resource Adequacy Benefits to Buyer from the Facility, Seller shall provide such RA Substitute Capacity in accordance with applicable CAISO requirements. Seller acknowledges and agrees that any failure by Seller to provide such RA Substitute Capacity may result in CAISO rejecting or cancelling Scheduled Maintenance or other outage of the Facility. Buyer shall notify Seller within three (3) Business Days after becoming aware of an obligation by Seller to provide RA Substitute Capacity. Upon request by Seller, Buyer shall use commercially reasonable efforts to secure, on Seller’s behalf, RA Substitute Capacity; provided that Seller shall reimburse Buyer for all out-of-pocket costs, including broker and outside counsel costs, associated with such RA Substitute Capacity.
		6. If Seller anticipates it will have an RA Shortfall in any month of the Delivery Term, Seller may provide Replacement RA up to the anticipated RA Shortfall, provided (i) Seller provides Buyer with Replacement RA product information in a written notice substantially in the form of Exhibit K at least seventy-five (75) days before the applicable Showing Month, and (ii) Replacement RA shall not exceed twenty-five percent (25%) of the Resource Adequacy Benefits provided during any Contract Year.

## Resource Adequacy Failure.

* + 1. RA Deficiency Determination. Notwithstanding Seller’s obligations set forth in Section 4.3 or anything to the contrary herein, the Parties acknowledge and agree that if Seller has indicated that the Facility will have Full Capacity Deliverability Status on the Cover Sheet, but has failed to obtain such status for the Facility by the RA Guarantee Date, or if Seller otherwise fails to provide Resource Adequacy Benefits in an amount equal to or greater than the Facility’s Qualifying Capacity as required hereunder, then Seller shall pay to Buyer the RA Deficiency Amount for each RA Shortfall Month as liquidated damages due to Buyer for the Capacity Attributes that Seller failed to convey to Buyer.
		2. RA Deficiency Amount Calculation. For each RA Shortfall Month, Seller shall pay to Buyer an amount (the “**RA Deficiency Amount**”) equal to the sum of:
			1. For any portion of the RA Shortfall for which Buyer incurs a CPUC System RA Penalty (“**CPUC-Penalized Shortfall**”), Seller’s pro rata share of the amount of such CPUC System RA Penalty for such month actually incurred by Buyer (which, for the avoidance of doubt, shall be zero (0) if Buyer does not incur any CPUC System RA Penalty), plus
			2. For any portion of the RA Shortfall for which Buyer incurs CAISO costs, charges or penalties associated with such shortfall (“**CAISO-Penalized Shortfall**”) Seller’s pro rata share of the amount of such CAISO costs, charges or penalties associated with the RA Shortfall for such month actually incurred by Buyer (which, for the avoidance of doubt, shall be zero (0) if Buyer does not incur any CAISO costs, charges or penalties associated with the RA Shortfall), plus
			3. For any RA Shortfall which is not CPUC-Penalized Shortfall and/or CAISO-Penalized Shortfall, and for which Buyer purchased replacement Resource Adequacy Benefits, the amount of Buyer’s cost of such replacement Resource Adequacy Benefits, plus
			4. For any RA Shortfall which is not CPUC-Penalized Shortfall and/or CAISO-Penalized Shortfall, and for which Buyer did not purchase replacement Resource Adequacy Benefits, the greater of (A) the product of (1) such portion of the RA Shortfall multiplied by (y) the CPM Soft Offer Cap, and (B) the prevailing market value of such RA Shortfall, as reasonably determined by Buyer.

## CEC Certification and Verification. Subject to Section 3.13, Seller shall take all necessary steps including, but not limited to, making or supporting timely filings with the CEC to obtain and maintain CEC Precertification and CEC Final Certification and Verification for the Facility. Seller shall obtain CEC Precertification by the Commercial Operation Date. Within thirty (30) days after the Commercial Operation Date, Seller shall apply with the CEC for CEC Final Certification and Verification. Within one hundred eighty (180) days after the Commercial Operation Date, Seller shall obtain and maintain throughout the remainder of the Delivery Term the CEC Final Certification and Verification. Seller must promptly notify Buyer and the CEC of any changes to the information included in Seller’s application for CEC Precertification or CEC Final Certification and Verification for the Facility. For the first one hundred eighty (180) days of the Delivery Term, provided that Seller has obtained and maintained CEC Precertification, Buyer shall pay Seller the Contract Price for Product according to Section 3.3 regardless of whether Seller has obtained CEC Final Certification and Verification. If Seller has not obtained CEC Final Certification and Verification within one hundred eighty (180) days after the Commercial Operation Date, Buyer will compensate Seller for the Product at the lower of (i) the Contract Price, as adjusted according to Section 3.3, or (ii) the Day-Ahead LMP, for the remainder of the Delivery Term, or until Seller obtains CEC Final Certification and Verification. If Seller obtains CEC Final Certification and Verification after one hundred eighty (180) days after the Commercial Operation Date, Buyer will thereafter begin paying Seller the Contract Price for Product according to Section 3.3, and, if such CEC Final Certification and Verification relates back to all Energy delivered by Seller during the Delivery Term, will reimburse Seller for the difference between (x) any reduced amounts paid to Seller for Product under this Section 3.10 due to Seller’s failure to obtain CEC Final Certification and Verification within one hundred eighty (180) days after the Commercial Operation Date, and (y) the amount that would have been paid to Seller had Seller timely obtained CEC Final Certification and Verification within one hundred eighty (180) days after the Commercial Operation Date. If Seller has not obtained CEC Final Certification and Verification within one (1) year of the Commercial Operation Date, then an Event of Default shall occur, Buyer shall have all remedies available under this Agreement, including under Section 11.2, and, in the event that Buyer terminates this Agreement under Section 11.2, Seller shall reimburse Buyer, in addition to any other amounts owed, in an amount equal to the difference between (a) the amount paid by Buyer to Seller for Product during the first one hundred eighty (180) days of the Delivery Term, and (b) the amount that would have been paid if the price for energy delivered during the first one hundred eighty (180) days of the Delivery Term were the Day Ahead LMP.

## Eligibility. Seller, and, if applicable, its successors, represents and warrants that throughout the Delivery Term of this Agreement that: (i) the Project qualifies and is certified by the CEC as an Eligible Renewable Energy Resource (“ERR”) as such term is defined in Public Utilities Code Section 399.12 or Section 399.16; and (ii) the Project’s output delivered to Buyer qualifies under the requirements of the California Renewables Portfolio Standard. To the extent a change in law occurs after execution of this Agreement that causes this representation and warranty to be materially false or misleading, it shall not be an Event of Default if Seller has used commercially reasonable efforts to comply with such change in law.

## California Renewables Portfolio Standard. Subject to Section 3.13, Seller shall also take all other actions necessary to ensure that the Energy produced from the Facility is tracked for purposes of satisfying the California Renewables Portfolio Standard requirements, as may be amended or supplemented by California statute or by the CPUC or CEC from time to time.

## Compliance Expenditure Cap. If Seller establishes to Buyer’s reasonable satisfaction that a change in Laws occurring after the Effective Date has increased Seller’s cost above the cost that could reasonably have been contemplated as of the Effective Date to take all actions to comply with Seller’s obligations under the Agreement with respect to obtaining, maintaining, conveying or effectuating Buyer’s use of (as applicable), the items listed in Sections 3.13(a), (b), (c), and (d), then the Parties agree that the maximum amount of costs and expenses Seller shall be required to bear during the Delivery Term shall be capped at twenty five thousand dollars ($25,000.00) per MW of Guaranteed Capacity cumulatively during the Delivery Term (“**Compliance Expenditure Cap**”):

* + 1. CEC Certification and Verification;
		2. Green Attributes;
		3. Future Environmental Attributes; and,
		4. Capacity Attributes.

Any actions required for Seller to comply with its obligations set forth in the first paragraph above, the cost of which will be included in the Compliance Expenditure Cap, shall be referred to collectively as the “**Compliance Actions**.”

If Seller reasonably anticipates the need to incur out-of-pocket expenses in excess of the Compliance Expenditure Cap in order to take any Compliance Action Seller shall provide Notice to Buyer of such anticipated out-of-pocket expenses.

Buyer will have sixty (60) days to evaluate such Notice (during which time period Seller is not obligated to take any Compliance Actions described in the Notice) and shall, within such time, either (1) agree to reimburse Seller for all of the costs that exceed the Compliance Expenditure Cap (such Buyer-agreed upon costs, the “**Accepted Compliance Costs**”), or (2) waive Seller’s obligation to take such Compliance Actions, or any part thereof for which Buyer has not agreed to reimburse Seller. If Buyer does not respond to a Notice given by Seller under this Section 3.13 within sixty (60) days after Buyer’s receipt of same, Buyer shall be deemed to have waived its rights to require Seller to take the Compliance Actions that are the subject of the Notice, and Seller shall have no further obligation to take, and no liability for any failure to take, these Compliance Actions for the remainder of the Contract Term.

If Buyer agrees to reimburse Seller for the Accepted Compliance Costs, then Seller shall take such Compliance Actions covered by the Accepted Compliance Costs as agreed upon by the Parties and Buyer shall reimburse Seller for Seller’s actual costs to effect the Compliance Actions, not to exceed the Accepted Compliance Costs, within sixty (60) days from the time that Buyer receives an invoice and reasonable documentation of such costs from Seller.

## The term “commercially reasonable efforts” as used in Sections 3.11 and 4.8(h) means efforts consistent with and subject to this Section 3.13.

# OBLIGATIONS AND DELIVERIES

## Delivery.

* + 1. Energy. Subject to the terms and conditions of this Agreement, Seller shall make available and Buyer shall accept at the Delivery Point all Metered Energy on an as-generated, instantaneous basis. Each Party shall perform all obligations under this Agreement, including all generation, scheduling, and transmission services in compliance with (i) the CAISO Tariff, (ii) WECC scheduling practices, and (iii) Prudent Operating Practice.

(b) Green Attributes. Seller hereby provides and conveys all Green Attributes associated with the Facility as part of the Product being delivered. Seller represents and warrants that Seller holds the rights to all Green Attributes from the Facility, and Seller agrees to convey and hereby conveys all such Green Attributes to Buyer as included in the delivery of the Product from the Facility. Upon request of Buyer, Seller shall submit a Green-e® Energy Tracking Attestation Form (“**Attestation**”) for Product delivered under this Agreement to the Center for Resource Solutions (“**CRS**”) at https://www.tfaforms.com/4652008 or its successor. The Attestation shall be submitted in accordance with the requirements of CRS and shall be submitted within thirty (30) days of Buyer’s request or the last day of the month in which the applicable Energy was generated, whichever is later.

## Title and Risk of Loss.

* + 1. Energy. Title to and risk of loss related to the Metered Energy shall pass and transfer from Seller to Buyer at the Delivery Point.
		2. Green Attributes. Title to and risk of loss related to the Green Attributes shall pass and transfer from Seller to Buyer upon the transfer of such Green Attributes in accordance with WREGIS.

## Scheduling Coordinator Responsibilities.

### Buyer as Scheduling Coordinator for the Facility. Upon initial synchronization of the Facility to the CAISO Grid, Buyer shall be the Scheduling Coordinator or designate a qualified third party to provide Scheduling Coordinator services with the CAISO for the Facility for both the delivery and the receipt of the Product at the Delivery Point. At least thirty (30) days prior to the initial synchronization of the Facility to the CAISO Grid, (i) Seller shall take all actions and execute and deliver to Buyer and the CAISO all documents necessary to authorize or designate Buyer as Seller’s Scheduling Coordinator for the Facility effective as of the initial synchronization of the Facility to the CAISO Grid, and (ii) Buyer shall, and shall cause its designee to, take all actions and execute and deliver to Seller and the CAISO all documents necessary to authorize or designate Buyer or its designee as the Scheduling Coordinator for the Facility effective as of the initial synchronization of the Facility to the CAISO Grid. On and after initial synchronization of the Facility to the CAISO Grid, Seller shall not authorize or designate any other party to act as Seller’s Scheduling Coordinator, nor shall Seller perform for its own benefit the duties of Scheduling Coordinator, and Seller shall not revoke Buyer’s authorization to act as Seller’s Scheduling Coordinator unless agreed to by Buyer. Buyer (as Seller’s SC) shall submit Schedules to the CAISO in accordance with this Agreement and the applicable CAISO Tariff, protocols and Scheduling practices for Product on a day-ahead, hour-ahead, fifteen-minute market or real time basis, as determined by Buyer.

### Notices. Buyer (as Seller’s SC) shall provide Seller with access to a web based system through which Seller shall submit to Buyer and the CAISO all notices and updates required under the CAISO Tariff regarding the Facility’s status, including, but not limited to, all outage requests, Forced Facility Outages, Forced Facility Outage reports, clearance requests, or must offer waiver forms. Seller will cooperate with Buyer to provide such notices and updates. If the web-based system is not available, Seller shall promptly submit such information to Buyer and the CAISO (in order of preference) telephonically, by electronic mail, or facsimile transmission to the personnel designated to receive such information.

### CAISO Costs and Revenues. Except as otherwise set forth below and in Sections 3.4(b) and 3.7, Buyer (as Scheduling Coordinator for the Facility) shall be responsible for CAISO costs (including penalties, Imbalance Energy costs or revenues, and other charges) and shall be entitled to all CAISO revenues (including credits, Imbalance Energy revenues or costs, and other payments), including revenues associated with CAISO dispatches, bid cost recovery, Inter-SC Trade credits, or other credits in respect of the Product Scheduled or delivered from the Facility. Seller shall be responsible for all CAISO penalties or fees resulting from any failure by Seller to abide by the CAISO Tariff or this Agreement (except to the extent such non-compliance is caused by Buyer’s failure to perform its duties as Scheduling Coordinator for the Facility). The Parties agree that any Availability Incentive Payments are for the benefit of the Seller and for Seller’s account and that any Non-Availability Charges are the responsibility of the Seller and for Seller’s account. In addition, if during the Delivery Term, the CAISO implements or has implemented any sanction or penalty related to scheduling, outage reporting, or generator operation, and any such sanctions or penalties are imposed upon the Facility or to Buyer as Scheduling Coordinator due to the actions or inactions of Seller, the cost of the sanctions or penalties shall be the Seller’s responsibility.

### CAISO Settlements. Buyer (as Seller’s SC) shall be responsible for all settlement functions with the CAISO related to the Facility. Buyer shall render a separate invoice to Seller for any CAISO charges or penalties (“**CAISO Charges Invoice**”) for which Seller is responsible under this Agreement, including Section 3.4(b). CAISO Charges Invoices shall be rendered after settlement information becomes available from the CAISO that identifies any CAISO charges. Notwithstanding the foregoing, Seller acknowledges that the CAISO will issue additional invoices reflecting CAISO adjustments to such CAISO charges. Buyer will review, validate, and if requested by Seller under Section 4.3(e) below, dispute any charges that are the responsibility of Seller in a timely manner and consistent with Buyer’s existing settlement processes for charges that are Buyer’s responsibilities. Subject to Seller’s right to dispute and to have Buyer pursue the dispute of any such invoices, Seller shall pay the amount of CAISO Charges Invoices within ten (10) Business Days of Seller’s receipt of the CAISO Charges Invoice. If Seller fails to pay such CAISO Charges Invoice within that period, Buyer may net or offset any amounts owing to it for these CAISO Charges Invoices against any future amounts it may owe to Seller under this Agreement. The obligations under this section with respect to payment of CAISO Charges Invoices shall survive the expiration or termination of this Agreement.

### Dispute Costs. Buyer (as Seller’s SC) may be required by Seller to dispute CAISO settlements in respect of the Facility. Seller agrees to pay Buyer’s costs and expenses (including reasonable attorneys’ fees) associated with its involvement with such CAISO disputes to the extent they relate to CAISO charges payable by Seller with respect to the Facility that Seller has directed Buyer to dispute.

### Terminating Buyer’s Designation as Scheduling Coordinator. At least thirty (30) days prior to expiration of this Agreement or as soon as reasonably practicable upon an earlier termination of this Agreement, the Parties will take all actions necessary to terminate the designation of Buyer as Scheduling Coordinator for the Facility as of 11:59 p.m. on such expiration date.

### Master Data File and Resource Data Template. Seller shall provide the data to the CAISO (and to Buyer) that is required for the CAISO’s Master Data File and Resource Data Template (or successor data systems) for this Facility consistent with this Agreement. Neither Party shall change such data without the other Party’s prior written consent, not to be unreasonably withheld.

### NERC Reliability Standards.Buyer (as Scheduling Coordinator) shall cooperate reasonably with Seller to the extent necessary to enable Seller to comply, and for Seller to demonstrate Seller’s compliance with, NERC reliability standards. This cooperation shall include the provision of information in Buyer’s possession that Buyer (as Scheduling Coordinator) has provided to the CAISO related to the Facility or actions taken by Buyer (as Scheduling Coordinator) related to Seller’s compliance with NERC reliability standards.

## Forecasting. Seller shall provide the forecasts described below. Seller’s Available Capacity forecasts shall include availability and updated status of key equipment for the Facility. Seller shall use commercially reasonable efforts to forecast the Available Capacity and expected Metered Energy of the Facility accurately and to transmit such information in a format reasonably acceptable to Buyer (or Buyer’s designee).

* + 1. Annual Forecast of Expected Metered Energy. No less than ninety (90) days before (i) the first day of the first Contract Year of the Delivery Term and (ii) the beginning of each calendar year for every subsequent Contract Year during the Delivery Term, Seller shall provide to Buyer a non-binding forecast of expected Metered Energy, by hour, for the following calendar year in the form attached hereto as Exhibit L-1 or as reasonably requested by Buyer.
		2. Monthly Forecast of Available Capacity and Metered Energy. No less than thirty (30) days before the beginning of Commercial Operation, and thereafter ten (10) Business Days before the beginning of each month during the Delivery Term, Seller shall provide to Buyer and Buyer’s designee (if applicable) a non-binding forecast of the hourly expected Available Capacity and expected Metered Energy, for each day of the following month in a forms attached hereto as Exhibits L-2 and L-3, respectively.
		3. Daily Forecast of Available Capacity. By 5:30 AM Pacific Prevailing Time on the Business Day immediately preceding the date of delivery, Seller shall provide Buyer with a non-binding forecast of the Facility’s Available Capacity (or if requested by Buyer, the expected Metered Energy) for each hour of the immediately succeeding day (“**Day-Ahead Forecast**”). A Day-Ahead Forecast provided in a day prior to any non-Business Day(s) shall include non-binding forecasts for the immediate day, each succeeding non-Business Day and the next Business Day. Each Day-Ahead Forecast shall clearly identify, for each hour, Seller’s best estimate of the Facility’s Available Capacity (or if requested by Buyer, the expected Metered Energy).
		4. Real-Time Available Capacity. During the Delivery Term, Seller shall notify Buyer of any changes in Available Capacity of one (1) MW or more, whether due to Forced Facility Outage, Force Majeure or other cause, as soon as reasonably possible, but no later than one (1) hour prior to the deadline for submitting Schedules to the CAISO in accordance with the rules for participation in the Real-Time Market. If the Available Capacity changes by at least one (1) MW as of a time that is less than one (1) hour prior to the Real-Time Market deadline, but before such deadline, then Seller must notify Buyer as soon as reasonably possible. Such Notices shall contain information regarding the beginning date and time of the event resulting in the change in Available Capacity, the expected end date and time of such event, the expected Available Capacity in MW, and any other information required by the CAISO or reasonably requested by Buyer. With respect to any Forced Facility Outage, Seller shall use commercially reasonable efforts to notify Buyer of such outage within ten (10) minutes of the commencement of the Forced Facility Outage. Seller shall inform Buyer of any developments that are reasonably likely to affect either the duration of such outage or the availability of the Facility during or after the end of such outage. These notices and changes to Available Capacity shall be communicated in a method acceptable to Buyer; provided that Buyer specifies the method no later than sixty (60) days prior to the effective date of such requirement. In the event Buyer fails to provide Notice of an acceptable method for communications under this Section 4.4(d), then Seller shall send such communications by telephone and e-mail to Buyer.

## Dispatch Down/Curtailment.

### General. Seller agrees to reduce the Facility’s generation by the amount and for the period set forth in any Curtailment Order, Buyer Curtailment Order, or notice received from CAISO in respect of a Buyer Bid Curtailment. Buyer has no obligation to purchase or pay for any Product delivered in violation of any Curtailment Order, Buyer Curtailment Order, or notice received from CAISO in respect of a Buyer Bid Curtailment, or for any Product that could not be delivered to the Delivery Point due to a Force Majeure Event.

### Buyer Curtailment. Buyer shall have the right to order Seller to curtail deliveries of Energy from the Facility to the Delivery Point for reasons unrelated to Force Majeure Events or Curtailment Orders pursuant to a dispatch notice delivered to Seller, provided that Buyer shall pay Seller for all Deemed Delivered Energy associated with all Buyer Curtailment Periods at the applicable Contract Price.

### Failure to Comply. If Seller fails to comply with a Buyer Curtailment Order, Buyer Bid Curtailment or Curtailment Order, then, for each MWh of Metered Energy that the Facility generated in contradiction to the Buyer Curtailment Order, Buyer Bid Curtailment or Curtailment Order, Seller shall pay Buyer for each such MWh at an amount equal to the sum of (A) + (B) + (C), where: (A) is the amount, if any, paid to Seller by Buyer for delivery of such MWh and, (B) is an amount equal to the absolute value of the Negative LMP, if any, for the Buyer Curtailment Period or Curtailment Period, times the amount of MWh of Metered Energy that the Facility generated in contradiction to the Buyer Curtailment Order, Buyer Bid Curtailment or Curtailment Order, and (C) is any penalties or other charges resulting from Seller’s failure to comply with the Buyer Curtailment Order, Buyer Bid Curtailment or Curtailment Order.

(d) Seller Equipment Required for Operating Instruction Communications. Seller shall acquire, install, and maintain such facilities, communications links and other equipment, and implement such protocols and practices, as necessary to respond to and follow operating instructions from the CAISO and Buyer's SC, including an electronic signal conveying real time and intra-day instructions, to operate the Facility as directed by Buyer from time to time in accordance with this Agreement and/or a Governmental Authority, including to implement a Buyer Curtailment Order, Buyer Bid Curtailment or Curtailment Order in accordance with the methodologies applicable to the Facility and used to transmit such instructions. If at any time during the Delivery Term, Seller’s facilities, communications links or other equipment, protocols or practices are not in compliance with methodologies applicable to the Facility and directed by Buyer, Seller shall take the steps necessary to become compliant as soon as commercially reasonably possible. Seller shall promptly repair and replace as necessary such facilities, communication links or other equipment, and shall notify Buyer as soon as Seller discovers any defect. If Buyer notifies Seller of the need for maintenance, repair, or replacement of any such facilities, communication links or other equipment, Seller shall repair or replace such equipment as necessary within five (5) days of receipt of such Notice; provided that if Seller is unable to do so, then Seller shall make such repair or replacement as soon as reasonably practical. Seller shall be liable pursuant to Section 4.4(c) for failure to comply with a Buyer Curtailment Order, Buyer Bid Curtailment or Curtailment Order, during the time that Seller’s facilities, communications links or other equipment, protocols or practices are not in compliance with applicable methodologies. A Buyer Curtailment Order, Buyer Bid Curtailment or Curtailment Order communication via such systems and facilities shall have the same force and effect on Seller as any other form of communication.

## Reduction in Delivery Obligation.

For the avoidance of doubt, and in no way limiting Section 3.1 or Exhibit D:

* + 1. Facility Maintenance. Seller shall be permitted to reduce deliveries of Product during any period of and to the extent required by Scheduled Maintenance on the Facility previously agreed to between Buyer and Seller.
		2. Forced Facility Outage. Seller shall be permitted to reduce deliveries of Product during and to the extent required by any Forced Facility Outage. Seller shall provide Buyer with Notice and expected duration and extent (if known) of any Forced Facility Outage.
		3. System Emergencies and other Interconnection Events. Seller shall be permitted to reduce deliveries of Product during any period of and to the extent required by System Emergency, Buyer Curtailment Period, or upon Notice of a Curtailment Order, or pursuant to the terms of the Interconnection Agreement or applicable tariff. In the event of a System Emergency, anticipated System Emergency, or other event or circumstance in which CAISO determines that there is or may be an imminent need for Energy supplies on the CAISO Grid, Seller shall use reasonable efforts to make the Product fully available, including by cancelling or deferring any Facility maintenance.
		4. Force Majeure Event. Seller shall be permitted to reduce deliveries of Product during and to the extent required by any Force Majeure Event.
		5. Health and Safety. Seller shall be permitted to reduce deliveries of Product as necessary to maintain health and safety pursuant to Section 6.2.

## Expected Energy and Guaranteed Energy Production. The quantity of Product, as measured by Metered Energy, that Seller expects to be able to deliver to Buyer during each Contract Year is set forth on the Cover Sheet (“**Expected Energy**”). Seller shall be required to deliver to Buyer an amount of Energy, not including any Excess MWh, equal to no less than the Guaranteed Energy Production (as defined below) in [***For intermittent resources***: any period of two (2) consecutive Contract Years during the Delivery Term] [***For non-intermittent resources***: any single Contract Year during the Delivery Term] (“**Performance Measurement Period**”). “**Guaranteed Energy Production**” means an amount of Product, as measured in MWh, equal to [***For intermittent resources:*** one-hundred sixty percent (160%) of the average Expected Energy for the two (2) Contract Years constituting such Performance Measurement Period] [***For non-intermittent resources***: ninety-five percent (95%) of the average Expected Energy for each Contract Year (i.e., Performance Measurement Period)]. Seller shall be excused from achieving the Guaranteed Energy Production during any Performance Measurement Period only to the extent that Seller was unable to deliver Energy as a result of any Force Majeure Events, Buyer Default, Curtailment Periods and Buyer Curtailment Periods; to effectuate the foregoing excuse, Seller shall be deemed to have generated (1) the Deemed Delivered Energy in respect of Buyer Curtailment Periods, and (2) an amount of Energy determined in accordance with Exhibit D in respect of Lost Output. [***For an intermittent resource:*** In addition, for purposes of determining whether Seller has achieved the Guaranteed Energy Production, Seller shall be deemed to have delivered to Buyer, in the first Contract Year of each Performance Measurement Period following a Performance Measurement Period as to which Seller has paid damages calculated in accordance with Exhibit D, the Product in the amount equal to the greater of the amount of Metered Energy actually delivered in such Contract Year, less Excess MWh, or eighty percent (80%) of the Expected Energy for such Contract Year]. If Seller fails to achieve the Guaranteed Energy Production amount in any Performance Measurement Period, Seller shall pay Buyer damages calculated in accordance with Exhibit D.

## WREGIS**.** Seller shall, at its sole expense, but subject to Section 3.13, take all actions and execute all documents or instruments necessary to ensure that all WREGIS Certificates associated with all Renewable Energy Credits corresponding to all Metered Energy are issued and tracked for purposes of satisfying the requirements of the California Renewables Portfolio Standard for Buyer’s sole benefit. Seller shall transfer the Renewable Energy Credits to Buyer. Seller shall comply with all Laws, including the WREGIS Operating Rules, regarding the certification, issuance, and transfer of such WREGIS Certificates to Buyer, and Buyer shall be given sole title to all such WREGIS Certificates. In addition:

* + 1. Prior to the Commercial Operation Date, Seller shall register the Facility with WREGIS and establish an account with WREGIS (**“Seller’s WREGIS Account”**), which Seller shall maintain until the end of the Delivery Term. Seller shall transfer the WREGIS Certificates using “**Forward Certificate Transfers**” (as described in the WREGIS Operating Rules) from Seller’s WREGIS Account to the WREGIS account(s) of Buyer or the accounts of a designee that Buyer identifies by Notice to Seller (“**Buyer’s WREGIS Account**”) Seller shall be responsible for all expenses associated with registering the Facility with WREGIS, establishing and maintaining Seller’s WREGIS Account, paying WREGIS Certificate issuance and transfer fees, and transferring WREGIS Certificates from Seller’s WREGIS Account to Buyer’s WREGIS Account.
		2. Seller shall cause itself or its agent to be designated as the Qualified Reporting Entity for the Facility. Seller shall cause Forward Certificate Transfers to occur on a monthly basis in accordance with the certification procedure established by the WREGIS Operating Rules. Since WREGIS Certificates will only be created for whole MWh amounts of Energy generated, any fractional MWh amounts (i.e., kWh) will be carried forward until sufficient generation is accumulated for creation of a WREGIS Certificate.
		3. Seller shall, at its sole expense, ensure that the WREGIS Certificates for a given calendar month correspond with the Metered Energy for such calendar month as evidenced by the Facility’s metered data.
		4. Due to the ninety (90) day delay in the creation of WREGIS Certificates relative to the timing of invoice payment under Section 8.2, Buyer shall make an invoice payment for a given month in accordance with Section 8.2 before the WREGIS Certificates for such month are formally transferred to Buyer in accordance with the WREGIS Operating Rules and this Section 4.8. Notwithstanding this delay, Buyer shall have all right and title to all such WREGIS Certificates upon payment to Seller in accordance with Section 8.2.
		5. A “**WREGIS Certificate Deficit**”means any deficit or shortfall in WREGIS Certificates issued to Buyer for a calendar month as compared to the Metered Energy for the same calendar month (“**Deficient Month**”). If any WREGIS Certificate Deficit occurs, then the amount of Metered Energy in the Deficient Month shall be reduced by the amount of the WREGIS Certificate Deficit for purposes of calculating Buyer’s payment to Seller under Article 8 and the Guaranteed Energy Production for the applicable Performance Measurement Period; provided, however, that Buyer shall pay Seller for any Metered Energy that is Delivered by Buyer without corresponding WREGIS Certificates at a price equal to the lesser of (i) the Contract Price, or (ii) the weighted average Day-Ahead LMPs for the PV Energy delivered in the corresponding month. Without limiting Seller’s obligations under this Section 4.8, if a WREGIS Certificate Deficit is caused solely by an error or omission of WREGIS, the Parties shall cooperate in good faith to cause WREGIS to correct its error or omission. Seller shall use commercially reasonable efforts to rectify any WREGIS Certificate Deficit as expeditiously as possible.
		6. If WREGIS changes the WREGIS Operating Rules after the Effective Date or applies the WREGIS Operating Rules in a manner inconsistent with this Section 4.8 after the Effective Date, the Parties promptly shall modify this Section 4.8 as reasonably required to cause and enable Seller to transfer to Buyer’s WREGIS Account a quantity of WREGIS Certificates for each given calendar month that corresponds to the Metered Energy in the same calendar month.
		7. STC REC-2. Seller warrants that all necessary steps to allow the Renewable Energy Credits transferred to Buyer to be tracked in the Western Renewable Energy Generation Information System will be taken prior to the first delivery under the contract.
		8. STC REC-1. Transfer of Renewable Energy Credits. Seller and, if applicable, its successors, represents and warrants that throughout the Delivery Term of this Agreement the Renewable Energy Credits transferred to Buyer conform to the definition and attributes required for compliance with the California Renewables Portfolio Standard, as set forth in California Public Utilities Commission Decision 08-08-028, and as may be modified by subsequent decision of the California Public Utilities Commission or by subsequent legislation. To the extent a change in law occurs after execution of this Agreement that causes this representation and warranty to be materially false or misleading, it shall not be an Event of Default if Seller has used commercially reasonable efforts to comply with such change in law.

## Financial Statements. Seller shall provide to Buyer, within 60 days of the end of Seller’s first, second, and third fiscal quarters, and within 120 days of the end of the Seller’s fiscal year, as applicable, unaudited quarterly and annual audited financial statements of the Seller (including a balance sheet and statements of income and cash flows), all prepared in accordance with generally accepted accounting principles in the United States, consistently applied.

## Access to Data and Installation and Maintenance of Weather Station

* + 1. Commencing on the Commercial Operation Date, and continuing throughout the Delivery Term, Seller shall provide to Buyer, in a form reasonably acceptable to Buyer, the data set forth below on a real-time basis; provided that Seller shall agree to make and bear the cost of changes to any of the data delivery provisions below, as requested by Buyer, throughout the Delivery Term, which changes Buyer determines are necessary to forecast output from the Facility, and comply with Law:
			1. real time, read-only access to meteorological measurements, transformer availability, any other facility availability information, and, if applicable, all parameters necessary for use in the equation under item (vii) of this list;
			2. real time, read-only access to energy output information collected by the supervisory control and data acquisition (SCADA) system for the Facility; provided that if Buyer is unable to access the Facility’s SCADA system, then upon written request from Buyer, Seller shall provide energy output information and meteorological measurements to Buyer in 1 minute intervals in the form of a flat file to Buyer through a secure file transport protocol (FTP) system with an e-mail back up for each flat file submittal;
			3. read-only access to the Facility’s CAISO revenue meter and all Facility meter data at the Site;
			4. full, real time access to the Facility’s Scheduling and Logging for the CAISO (OMS) client application, or its successor system;
			5. net plant electrical output at the CAISO revenue meter;
			6. [***For wind and solar facilities only***]instantaneous data measurements at sixty (60) second or increased frequency for the following parameters, which measurements shall be provided by Seller to Buyer in a consolidated data report at least once every five minutes via flat file through a secure file transport protocol (FTP) system with an e-mail backup: [***For solar facilities:*** (i) back panel temperature (ii) global horizontal irradiance, (iii) plane of array irradiance (if the panels are fixed) or direct normal irradiance (if the panels are tracking), (iv) wind speed, (v) peak wind speed (within one minute), (vi) wind direction, (vii) ambient air temperature, (viii) dewpoint air temperature or relative humidity, (ix) horizontal visibility, (x) precipitation (rain rate), (xi) precipitation (running 30 day total), and (xii) barometric pressure] [***For wind facilities:*** (i) wind speed (measured at thirty (30) meters), (ii) peak wind speed (within one minute, measured at thirty (30) meters), (iii) wind direction (measured at thirty (30) meters), (iv) wind speed standard deviation, (v) wind direction standard deviation, (vi) ambient air temperature (measured at thirty (30) meters), and (vii) barometric pressure (measured at thirty (30) meters)]; and
			7. [***For wind and solar facilities only***] an equation, updated on an ongoing basis to reflect the potential generation of the Facility as a function of [***For solar facilities:*** insolation] [***For wind facilities:*** wind speed] (and, if applicable, other weather factors). Such equation shall take into account the expected availability of the Facility. Seller shall reasonably cooperate with any request from Buyer to adjust the equation due to results that are inconsistent with the observed Facility output***.***

For any month in which the above information and access was not available to Buyer for longer than twenty-four (24) continuous hours, Seller shall prepare and provide to Buyer upon Buyer’s request a report with the Facility’s monthly actual available capacity in a form reasonably acceptable to Buyer.

* + 1. Seller shall maintain at least a minimum of one hundred twenty (120) days’ historical data for all data required pursuant to Section 4.10(a), which shall be available on a minimum time interval of one hour basis or an hourly average basis, except with respect to the meteorological measurements which shall be available on a minimum time interval of ten (10) minute basis. Seller shall provide such data to Buyer within five (5) Business Days of Buyer’s request.
		2. Installation, Maintenance and Repair.
			1. Seller, at its own expense, shall install and maintain at least one (1) stand-alone meteorological station at the Site to monitor and report the meteorological data required in Section 4.10(a) of this Agreement. Seller, at its own expense, shall install and maintain a secure communication link in order to provide Buyer with access to the data required in Section 4.10(a) of this Agreement.
			2. Seller shall maintain the meteorological stations, telecommunications path, hardware, and software necessary to provide accurate data to Buyer or Buyer’s designee to enable Buyer to meet current CAISO scheduling requirements. Seller shall promptly repair and replace as necessary such meteorological stations, telecommunications path, hardware and software and shall notify Buyer as soon as Seller learns that any such telecommunications paths, hardware and software are providing faulty or incorrect data.
			3. If Buyer notifies Seller of the need for maintenance, repair or replacement of the meteorological stations, telecommunications path, hardware or software, Seller shall maintain, repair or replace such equipment as necessary within five (5) days of receipt of such Notice; provided that if Seller is unable to repair or replace such equipment within five (5) days, then Seller shall make such repair or replacement as soon as reasonably practical; provided further that Seller shall not be relieved from liability for any Imbalance Energy costs incurred under Section 3.4(b) during this additional period for repair or replacement.
			4. For any occurrence in which Seller’s telecommunications system is not available or does not provide quality data and Buyer notifies Seller of the deficiency or Seller becomes aware of the occurrence, Seller shall transmit data to Buyer through any alternate means of verbal or written communication, including cellular communications from onsite personnel, facsimile, blackberry or equivalent mobile e-mail, or other method mutually agreed upon by the Parties, until the telecommunications link is re-established.
		3. Seller agrees and acknowledges that Buyer may seek and obtain from third parties any information relevant to its duties as Scheduling Coordinator for Seller, including from the Participating Transmission Operator. Seller shall execute within a commercially reasonable timeframe upon request such instruments as are reasonable and necessary to enable Buyer to obtain from the Participating Transmission Operator information concerning Seller and the Facility that may be necessary or useful to Buyer in furtherance of Buyer’s duties as Scheduling Coordinator for the Facility.
		4. No later than ninety (90) days before the Commercial Operation Date, Seller shall provide one (1) year, if available, but no less than six (6) months, of recorded meteorological data to Buyer in a form reasonably acceptable to Buyer from a weather station at the Site. Such weather station shall provide, via remote access to Buyer, all data relating to (i) the parameters [***For solar facilities*** (other than back panel temperature)] identified in Section 4.10(a)(vi) above (all data, except peak values, should be 1-second samples averaged into 10-minute periods); (ii) elevation, latitude and longitude of the weather station; and (iii) any other data reasonably requested by Buyer.

## Ancillary Services. Seller shall maintain compliance with the applicable certification and testing requirements in Section 8.3.4 and Appendix K of the CAISO Tariff and otherwise maintain the ability to provide Ancillary Services.

## Workforce Agreement. The Parties acknowledge that in connection with Buyer’s energy procurement efforts, including entering into this Agreement, Buyer is committed to creating community benefits, which includes engaging a skilled and trained workforce and targeted hires. Accordingly, prior to the Guaranteed Construction Start Date, Seller shall ensure that work performed in connection with construction of the Facility will be conducted using a project labor agreement, or similar agreement, providing for terms and conditions of employment with applicable labor organizations, and shall remain compliant with such agreement in accordance with the terms thereof. Seller shall provide documentation reasonably satisfactory to Buyer demonstrating Seller’s compliance with the requirements of this Section 4.12.

## Diverse Business Enterprises. During the Delivery Term, no later than twenty (20) days after each semi-annual period ending on June 30th or December 31st, Seller shall provide to Buyer a report listing all Diverse Business Enterprises that supplied goods or services to Seller during such period, including any certifications or other documentation of such Diverse Business Enterprises status as such and the aggregate amount paid to Diverse Business Enterprises during such period.

* + 1. Buyer has the right to disclose to the CPUC all such information provided by Seller pursuant to this Section 4.13.
		2. Seller shall make reasonable efforts to accommodate requests by the CPUC (or by Buyer in response to a request by the CPUC) to audit Seller in order to verify data provided by Seller pursuant to this Section 4.13.

## Shared Facilities. The Parties acknowledge and agree that certain of the Shared Facilities may be subject to shared facilities and/or co-tenancy agreements entered into among Seller, the Transmission Provider, Seller’s Affiliates, and/or third parties. If applicable, Seller agrees that any agreements regarding Shared Facilities (i) shall permit Seller to perform or satisfy, and shall not purport to limit, Seller’s obligations hereunder, (ii) shall provide for separate metering of the Facility; (iii) shall not limit Buyer’s ability to charge or discharge the Facility up to the Delivery Term Expected Energy; (iv) shall provide that any other generating or energy storage facilities not included in the Facility but using Shared Facilities shall not be included within the Facility’s CAISO Resource ID; and (iv) shall provide that any curtailment or restriction of Shared Facility capacity not attributable to a specific project or projects shall be allocated to all generating or storage facilities utilizing the Shared Facilities based on their pro rata allocation of the Shared Facility capacity prior to such curtailment or reduction. Seller shall not, and shall not permit any Affiliate to, allocate to other Persons a share of the total interconnection capacity under the Interconnection Agreements in excess of an amount equal to the total interconnection capacity under the Interconnection Agreements minus the Delivery Term Expected Energy.

# TAXES

## Allocation of Taxes and Charges. Seller shall pay or cause to be paid all Taxes on or with respect to the Facility or on or with respect to the sale and making available of Product to Buyer, that are imposed on Product prior to delivery or making available to Buyer, including on Energy prior to the Delivery Point. Buyer shall pay or cause to be paid all Taxes on or with respect to the delivery to and purchase by Buyer of Product that are imposed on Product at and from the Delivery Point (other than withholding or other Taxes imposed on Seller’s income, revenue, receipts or employees). Seller shall be solely responsible for all taxes, charges or fees imposed on the Facility or Seller by a Governmental Authority for Greenhouse Gas emitted by or attributable to the Facility during the Contract Term. If a Party is required to remit or pay Taxes that are the other Party’s responsibility hereunder, such Party shall promptly pay the Taxes due and then seek and receive reimbursement from the other for such Taxes. In the event any sale of Energy or other Product hereunder is exempt from or not subject to any particular Tax, Buyer shall provide Seller with all necessary documentation within thirty (30) days after the Effective Date to evidence such exemption or exclusion. If Buyer does not provide such documentation, then Buyer shall indemnify, defend, and hold Seller harmless from any liability with respect to Taxes from which Buyer claims it is exempt.

## Cooperation. Each Party shall use reasonable efforts to implement the provisions of and administer this Agreement in accordance with the intent of the Parties to minimize all Taxes, so long as no Party is materially adversely affected by such efforts. The Parties shall cooperate to minimize Tax exposure; *provided*, *however*, that neither Party shall be obligated to incur any financial or operational burden to reduce Taxes for which the other Party is responsible hereunder without receiving due compensation therefor from the other Party. All Energy delivered by Seller to Buyer hereunder shall be a sale made at wholesale, with Buyer reselling such Energy.

# MAINTENANCE OF THE FACILITY

## Maintenance of the Facility. Seller shall comply with Law and Prudent Operating Practice relating to the operation and maintenance of the Facility and the generation and sale of Product.

##  (a) Seller shall provide to Buyer no later than ninety (90) days prior to the Commercial Operation Date for the period from the Commercial Operation Date through the end of the then-current calendar year, and no later than September 1 of each calendar year thereafter for the following calendar year, a schedule of all planned outages or derates of the Facility for maintenance purposes (“Scheduled Maintenance”). Seller may perform no more than fifty (50) hours of Scheduled Maintenance that involves a reduction in the Available Capacity of the Facility per Contract Year. Seller shall not conduct Scheduled Maintenance between June 1 and October 31 of each year. Seller shall use commercially reasonable efforts to accommodate reasonable requests of Buyer with respect to adjusting the timing of Scheduled Maintenance. Seller may modify its schedule of Scheduled Maintenance upon reasonable advance notice to Buyer, subject to reasonable requests of Buyer and consistent with Section 4.4 and this Section 6.1.

##  (b) Seller shall use commercially reasonable efforts to perform during periods of Scheduled Maintenance all maintenance that will reduce the Facility’s output or availability. Seller shall arrange for any necessary non-emergency maintenance that is not Scheduled Maintenance and that reduces the Available Capacity of the Facility by more than ten percent (10%) to occur only between November 1 and May 31 of each year, unless (i) such outage is required to avoid damage to the Facility, (ii) such maintenance is necessary to maintain equipment warranties and cannot be scheduled outside the months of June through September, or (iii) the Parties agree otherwise in writing.

##  (c) Seller shall use commercially reasonable efforts to schedule all maintenance outages, including those associated with Scheduled Maintenance (i) within a single month, rather than across multiple months, (ii) during periods in which CAISO does not require resource substitution or replacement, and (iii) otherwise in a manner to avoid reductions in the Resource Adequacy Benefits available from the Facility to Buyer, provided that Seller shall not be required to consolidate preventative maintenance activities into a single month where such consolidation is inconsistent with vendor-recommended maintenance schedules.

## Maintenance of Health and Safety. Seller shall take reasonable safety precautions with respect to the operation, maintenance, repair and replacement of the Facility. If Seller becomes aware of any circumstances relating to the Facility that create an imminent risk of damage or injury to any Person or any Person’s property, Seller shall take prompt, reasonable action to prevent such damage or injury and shall give Buyer’s emergency contact identified on Exhibit M Notice of such condition. Such action may include disconnecting and removing all or a portion of the Facility, or suspending the supply of Energy to Buyer.

## Permits and Approvals. As between Buyer and Seller, Seller shall obtain any required permits and approvals in connection with the development, construction, and operation of the Facility, including without limitation, environmental clearance under the California Environmental Quality Act or other environmental law, from the local jurisdiction where the Facility will be constructed.

## Energy to Serve Station Use. Notwithstanding anything to the contrary in this Agreement, the Parties acknowledge (i) Seller is responsible for providing all Energy to serve Station Use (including paying the cost of any Energy used to serve Station Use and the cost of energy provided by third parties used to serve Station Use); and (ii) Seller may utilize Energy to serve Station Use.

# METERING

## Metering. Seller shall measure the amount of Energy produced by the Facility using a CAISO Approved Meter, using a CAISO-approved methodology. Such meter shall be installed and maintained at Seller’s cost. Metering will be consistent with the Metering Diagram set forth in Exhibit A. The meter shall be kept under seal, such seals to be broken only when the meters are to be tested, adjusted, modified or relocated. In the event that Seller breaks a seal, Seller shall notify Buyer as soon as practicable. In addition, Seller hereby agrees to provide all meter data to Buyer in a form reasonably acceptable to Buyer, and consents to Buyer obtaining from CAISO the CAISO meter data applicable to the Facility and all inspection, testing and calibration data and reports. Seller and Buyer shall cooperate to allow both Parties to retrieve the meter reads from the CAISO Operational Meter Analysis and Reporting (OMAR) web and/or directly from the CAISO meter(s) at the Facility.

## Meter Verification. If Buyer or Seller has reason to believe there may be a meter malfunction, Seller shall test the meter. Annually, upon Buyer’s reasonable request, Seller shall test the meter. The tests shall be conducted by independent third parties qualified to conduct such tests. Buyer shall be notified seven (7) days in advance of such tests and have a right to be present during such tests. If a meter is inaccurate it shall be promptly repaired or replaced. If a meter is inaccurate by more than one percent (1%) and it is not known when the meter inaccuracy commenced (if such evidence exists such date will be used to adjust prior invoices), then the invoices covering the period of time since the last meter test shall be adjusted for the amount of the inaccuracy on the assumption that the inaccuracy persisted during one-half of such period so long as such adjustments are accepted by CAISO and WREGIS; *provided*, such period may not exceed twelve (12) months.

# INVOICING AND PAYMENT; CREDIT

## Invoicing. Seller shall deliver an invoice to Buyer for Product no later than ten (10) days after the end of the prior monthly billing period. Each invoice shall provide Buyer (a) records of metered data, including CAISO metering and transaction data sufficient to document and verify the generation of Product by the Facility for any Settlement Period during the preceding month, the amount of Product in MWh produced by the Facility as read by the CAISO Approved Meter, the amount of Replacement RA delivered to Buyer, the calculation of Deemed Delivered Energy and Adjusted Energy Production, and the Contract Price applicable to such Product; and (b) access to any records, including invoices or settlement data from the CAISO, necessary to verify the accuracy of any amount. Invoices shall be in a format specified by Buyer, covering the services provided in the preceding month determined in accordance with the applicable provisions of this Agreement.

## Payment. Buyer shall make payment to Seller for Product by wire transfer or ACH payment to the bank account provided on each monthly invoice. Buyer shall pay undisputed invoice amounts within forty-five (45) days after receipt of the invoice. If such due date falls on a weekend or legal holiday, such due date shall be the next Business Day. Payments made after the due date will be considered late and will bear interest on the unpaid balance. If the amount due is not paid on or before the due date or if any other payment that is due and owing from one Party to another is not paid on or before its applicable due date, a late payment charge shall be applied to the unpaid balance and shall be added to the next billing statement. Such late payment charge shall be calculated based on an annual interest rate equal to the prime rate published on the date of the invoice in The Wall Street Journal (or, if The Wall Street Journal is not published on that day, the next succeeding date of publication), plus two percent (2%) (the “**Interest Rate**”). If the due date occurs on a day that is not a Business Day, the late payment charge shall begin to accrue on the next succeeding Business Day.

## Books and Records. To facilitate payment and verification, each Party shall maintain all books and records necessary for billing and payments, including copies of all invoices under this Agreement, for a period of at least two (2) years or as otherwise required by Law. Either Party, upon fifteen (15) days written Notice to the other Party, shall be granted reasonable access to the accounting books and records within the possession or control of the other Party pertaining to all invoices generated pursuant to this Agreement.

## Payment Adjustments; Billing Errors. Payment adjustments shall be made if Buyer or Seller discovers there have been good faith inaccuracies in invoicing that are not otherwise disputed under Section 8.5, an adjustment to an amount previously invoiced or paid is required due to a correction of data by the CAISO, or there is determined to have been a meter inaccuracy sufficient to require a payment adjustment. If the required adjustment is in favor of Buyer, Buyer’s next monthly payment shall be credited in an amount equal to the adjustment. If the required adjustment is in favor of Seller, Seller shall add the adjustment amount to Buyer’s next monthly invoice. Adjustments in favor of either Buyer or Seller shall bear interest, until settled in full, in accordance with Section 8.2, accruing from the date on which the adjusted amount should have been due. Except for adjustments required due to a correction of data by the CAISO, any adjustment described in this Section 8.4 is waived if Notice of the adjustment is not provided within twelve (12) months after the invoice is rendered or subsequently adjusted.

## Billing Disputes. A Party may, in good faith, dispute the correctness of any invoice or any adjustment to an invoice rendered under this Agreement, or adjust any invoice for any arithmetic or computational error, within twelve (12) months of the date the invoice, or adjustment to an invoice, was rendered. In the event an invoice or portion thereof, or any other claim or adjustment arising hereunder, is disputed, payment of the undisputed portion of the invoice shall be required to be made when due. Any invoice dispute or invoice adjustment shall be in writing and shall state the basis for the dispute or adjustment. Payment of the disputed amount shall not be required until the dispute is resolved. Upon resolution of the dispute, any required payment shall be made within five (5) Business Days of such resolution along with interest accrued at the Interest Rate from and including the original due date to but excluding the date paid. Inadvertent overpayments shall be returned upon request or deducted by the Party receiving such overpayment from subsequent payments, with interest accrued at the Interest Rate from and including the date of such overpayment to but excluding the date repaid or deducted by the Party receiving such overpayment. Any dispute with respect to an invoice is waived if the other Party is not notified in accordance with this Section 8.5 within twelve (12) months after the invoice is rendered or subsequently adjusted, except to the extent any misinformation was from a party other than the Party seeking the adjustment and such party corrects its information after the twelve-month period. If an invoice is not rendered within twelve (12) months after the close of the month during which performance occurred, the right to payment for such performance is waived.

## Netting of Payments. The Parties hereby agree that they shall discharge mutual debts and payment obligations due and owing to each other on the same date through netting, in which case all amounts owed by each Party to the other Party for the purchase and sale of Product during the monthly billing period under this Agreement, including any related damages calculated pursuant to Exhibits B and D, interest, and payments or credits, shall be netted so that only the excess amount remaining due shall be paid by the Party who owes it.

## Seller’s Development Security. To secure Seller’s obligations under this Agreement, including the obligations of Seller to pay liquidated damages to Buyer as provided in this Agreement, Seller shall deliver Development Security to Buyer within five (5) Business Days after the Effective Date. Buyer will have the right to draw upon the Development Security if Seller fails to pay liquidated damages owed to Buyer pursuant to Exhibit B to this Agreement, or if Seller fails to pay a Damage Payment or Termination Payment owed to Buyer pursuant to Section 11.2. Seller shall maintain the Development Security in full force and effect and Seller shall replenish the Development Security in the event Buyer collects or draws down any portion of the Development Security for any reason permitted under this Agreement other than to satisfy a Damage Payment or a Termination Payment. Following the earlier of (i) Seller’s delivery of the Performance Security, or (ii) sixty (60) days after termination of this Agreement, Buyer shall promptly return the Development Security to Seller, less the amounts drawn in accordance with this Agreement.

## Seller’s Performance Security. To secure its obligations under this Agreement, Seller shall deliver Performance Security to Buyer on or before the Commercial Operation Date. Seller shall maintain the Performance Security in full force and effect and Seller shall replenish the Performance Security in the event Buyer collects or draws down any portion of the Performance Security for any reason permitted under this Agreement within five (5) Business Days after such draw, other than to satisfy a Termination Payment. Seller shall maintain the Performance Security in full force and effect until the date on which the following have occurred (“**Performance Security End Date**”): (A) the Delivery Term has expired or terminated early; and (B) all payment obligations of the Seller arising under this Agreement, including compensation for penalties, Termination Payment, indemnification payments or other damages are paid in full (whether directly or indirectly such as through set-off or netting). Following the occurrence of the Performance Security End Date, Buyer shall promptly return to Seller the unused portion of the Performance Security. Provided that no Event of Default has occurred and is continuing with respect to Seller, Seller may replace or change the form of Performance Security to another form of Performance Security from time to time upon reasonable prior written notice to Buyer.

## First Priority Security Interest in Cash or Cash Equivalent Collateral. To secure its obligations under this Agreement, and until released as provided herein, Seller hereby grants to Buyer a present and continuing first-priority security interest (“**Security Interest**”) in, and lien on (and right to net against), and assignment of the Development Security, Performance Security, any other cash collateral and cash equivalent collateral posted pursuant to Sections 8.7 and 8.8 and any and all interest thereon or proceeds resulting therefrom or from the liquidation thereof, whether now or hereafter held by, on behalf of, or for the benefit of Buyer, and Seller agrees to take all action as Buyer reasonably requires in order to perfect Buyer’s Security Interest in, and lien on (and right to net against), such collateral and any and all proceeds resulting therefrom or from the liquidation thereof.

Upon or any time after the occurrence of an Event of Default caused by Seller, an Early Termination Date resulting from an Event of Default caused by Seller, or an occasion provided for in this Agreement where Buyer is authorized to retain all or a portion of the Development Security or Performance Security, Buyer may do any one or more of the following (in each case subject to the final sentence of this Section 8.9):

1. Exercise any of its rights and remedies with respect to the Development Security and Performance Security, including any such rights and remedies under Law then in effect;
2. Draw on any outstanding Letter of Credit issued for its benefit and retain any cash held by Buyer as Development Security or Performance Security; and
3. Liquidate all Development Security or Performance Security (as applicable) then held by or for the benefit of Buyer free from any claim or right of any nature whatsoever of Seller, including any equity or right of purchase or redemption by Seller.

Buyer shall apply the proceeds of the collateral realized upon the exercise of any such rights or remedies to reduce Seller’s obligations under this Agreement (Seller remains liable for any amounts owing to Buyer after such application), subject to Buyer’s obligation to return any surplus proceeds remaining after these obligations are satisfied in full.

# NOTICES

## Addresses for the Delivery of Notices. Any Notice required, permitted, or contemplated hereunder shall be in writing, shall be addressed to the Party to be notified at the address set forth on Exhibit M or at such other address or addresses as a Party may designate for itself from time to time by Notice hereunder.

## Acceptable Means of Delivering Notice. Each Notice required, permitted, or contemplated hereunder shall be deemed to have been validly served, given or delivered as follows: (a) if sent by United States mail with proper first class postage prepaid, three (3) Business Days following the date of the postmark on the envelope in which such Notice was deposited in the United States mail; (b) if sent by a regularly scheduled overnight delivery carrier with delivery fees either prepaid or an arrangement with such carrier made for the payment of such fees, the next Business Day after the same is delivered by the sending Party to such carrier; (c) if sent by electronic communication (including electronic mail, facsimile, or other electronic means) and either (i) the receiving Party sends a written acknowledgment of receipt, or (ii) concurrently with the transmittal of such electronic communication the sending Party provides a copy of such electronic Notice by hand delivery or express courier, at the time indicated by the time stamp upon delivery; or (d) if delivered in person, upon receipt by the receiving Party. Notwithstanding the foregoing, Notices of outages or other scheduling or dispatch information or requests, may be sent by electronic communication and shall be considered delivered upon successful completion of such transmission.

# FORCE MAJEURE

## Definition.

* + 1. “**Force Majeure Event**” means any act or event that delays or prevents a Party from timely performing all or a portion of its obligations under this Agreement or from complying with all or a portion of the conditions under this Agreement if such act or event, despite the exercise of reasonable efforts, cannot be avoided by and is beyond the reasonable control (whether direct or indirect) of and without the fault or negligence of the Party relying thereon as justification for such delay, nonperformance, or noncompliance.
		2. Without limiting the generality of the foregoing, so long as the following events, despite the exercise of reasonable efforts, cannot be avoided by, and are beyond the reasonable control (whether direct or indirect) of and without the fault or negligence of the Party relying thereon as justification for such delay, nonperformance or noncompliance, a Force Majeure Event may include an act of God or the elements, such as flooding, lightning, hurricanes, tornadoes, or ice storms; explosion; fire; volcanic eruption; flood; epidemic; landslide; mudslide; sabotage; terrorism; earthquake; or other cataclysmic events; an act of public enemy; war; blockade; civil insurrection; riot; civil disturbance; or strikes or other labor difficulties caused or suffered by a Party or any third party except as set forth below.
		3. Notwithstanding the foregoing, the term “**Force Majeure Event**” does not include (i) economic conditions that render a Party’s performance of this Agreement at the Contract Price unprofitable or otherwise uneconomic (including an increase in component or compliance costs for any reason, including foreign or domestic tariffs, Buyer’s ability to buy Energy at a lower price, or Seller’s ability to sell Energy at a higher price, than the Contract Price); (ii) Seller’s inability to obtain permits or approvals of any type for the construction, operation, or maintenance of the Facility; (iii) the inability of a Party to make payments when due under this Agreement, unless the cause of such inability is an event that would otherwise constitute a Force Majeure Event as described above that disables physical or electronic facilities necessary to transfer funds to the payee Party; (iv) a Curtailment Period, except to the extent such Curtailment Period is caused by a Force Majeure Event; (v) Seller’s inability to obtain sufficient labor, equipment, materials, or other resources to build or operate the Facility except to the extent such inability is caused by a Force Majeure Event; (vi) a strike, work stoppage or labor dispute limited only to any one or more of Seller, Seller’s Affiliates, Seller’s contractors, their subcontractors thereof or any other third party employed by Seller to work on the Facility; (vii) any equipment failure except if such equipment failure is caused by a Force Majeure Event; (viii) variations in weather, including wind, rain and insolation, within one in fifty (1 in 50) year occurrence; or (ix) failure to complete the interconnection facilities or network upgrades required to connect the Facility and to deliver Product to the Delivery Point by the Guaranteed Commercial Operation Date except to the extent such inability is caused by a Force Majeure Event; or (x) Seller’s inability to achieve Construction Start of the Facility following the Guaranteed Construction Start Date or achieve Commercial Operation following the Guaranteed Commercial Operation Date; it being understood and agreed, for the avoidance of doubt, that the occurrence of a Force Majeure Event may give rise to a Development Cure Period.

## No Liability If a Force Majeure Event Occurs. Neither Seller nor Buyer shall be liable to the other Party in the event it is prevented from performing its obligations hereunder in whole or in part due to a Force Majeure Event. Buyer shall not be obligated to pay for any Product that Seller was not able to deliver as a result of a Force Majeure Event. The Party rendered unable to fulfill any obligation by reason of a Force Majeure Event shall take reasonable actions necessary to remove such inability with due speed and diligence. Nothing herein shall be construed as permitting that Party to continue to fail to perform after said cause has been removed. The obligation to use due speed and diligence shall not be interpreted to require resolution of labor disputes by acceding to demands of the opposition when such course is inadvisable in the discretion of the Party having such difficulty. Neither Party shall be considered in breach or default of this Agreement if and to the extent that any failure or delay in the Party’s performance of one or more of its obligations hereunder is caused by a Force Majeure Event. The occurrence and continuation of a Force Majeure Event shall not suspend or excuse the obligation of a Party to make any payments due hereunder.

## Notice. In the event of any delay or nonperformance resulting from a Force Majeure Event, the Party suffering the Force Majeure Event shall (a) as soon as practicable, notify the other Party in writing of the nature, cause, estimated date of commencement thereof, and the anticipated extent of any delay or interruption in performance, and (b) notify the other Party in writing of the cessation or termination of such Force Majeure Event, all as known or estimated in good faith by the affected Party; *provided*, *however*, that a Party’s failure to give timely Notice shall not affect such Party’s ability to assert that a Force Majeure Event has occurred unless the delay in giving Notice materially prejudices the other Party.

## Termination Following Force Majeure Event. If a Force Majeure Event has occurred that has caused either Party to be wholly or partially unable to perform its obligations hereunder, and has continued for a consecutive twelve (12) month period, then the non-claiming Party may terminate this Agreement upon written Notice to the other Party with respect to the Facility experiencing the Force Majeure Event. Upon any such termination, neither Party shall have any liability to the other, save and except for those obligations specified in Section 2.1(b), and Buyer shall promptly return to Seller any Development Security or Performance Security then held by Buyer.

# DEFAULTS; REMEDIES; TERMINATION

## Events of Default. An “**Event of Default**” shall mean,

* + 1. with respect to a Party (the “**Defaulting Party**”) that is subject to the Event of Default the occurrence of any of the following:

#### the failure by such Party to make, when due, any payment required pursuant to this Agreement and such failure is not remedied within five (5) Business Days after Notice thereof;

#### any representation or warranty made by such Party herein is false or misleading in any material respect when made or when deemed made or repeated, and such default is not remedied within thirty (30) days after Notice thereof;

#### the failure by such Party to perform any material covenant or obligation set forth in this Agreement (except to the extent constituting a separate Event of Default) and such failure is not remedied within thirty (30) days after Notice thereof;

#### such Party becomes Bankrupt;

#### such Party assigns this Agreement or any of its rights hereunder other than in compliance with Articles 14 or 15, as applicable; or

#### such Party consolidates or amalgamates with, or merges with or into, or transfers all or substantially all of its assets to, another entity and, at the time of such consolidation, amalgamation, merger or transfer, the resulting, surviving or transferee entity fails to assume all the obligations of such Party under this Agreement to which it or its predecessor was a party by operation of Law or pursuant to an agreement reasonably satisfactory to the other Party.

* + 1. with respect to Seller as the Defaulting Party, the occurrence of any of the following:

#### if at any time, Seller delivers or attempts to deliver to the Delivery Point for sale under this Agreement Energy that was not generated by the Facility;

#### the failure by Seller to achieve the Construction Start Date within one hundred twenty (120) days after the Guaranteed Construction Start Date, or the failure by Seller to achieve Commercial Operation within ninety (90) days after the Guaranteed Commercial Operation Date;

#### the failure by Seller to timely obtain CEC Final Certification and Verification in accordance with Section 3.10.

#### if, in the first six (6) months or the second six (6) months of any Contract Year, the Adjusted Energy Production amount is not at least ten percent (10%) of the Expected Energy amount for that Contract Year, and Seller fails to demonstrate to Buyer’s reasonable satisfaction, within ten (10) Business Days after Notice from Buyer, a legitimate reason for the failure to meet the ten percent (10%) minimum;

#### if, [***For intermittent resources:*** in any two (2) consecutive Contract Years, the Adjusted Energy Production amount is not at least sixty-five percent (65%) of the Expected Energy amount in each Contract Year] [***For non-intermittent sources***: in any single Contract Year, the Adjusted Energy Production amount is not at least eighty percent (80%) of the Expected Energy amount]; provided, it will not be an Event of Default under this Section 11.1(b)(v) if (a) the failure to meet the respective standard results from a failure of the Facility’s Main Power Transformer, (b) during the one hundred eighty (180) day period following the date of such Main Power Transformer failure Seller diligently pursues a cure to such Main Power Transformer failure and delivers to Buyer a certificate from a Licensed Professional Engineer within thirty (30) days following the date of the Main Power Transformer failure that cure can be made within such one hundred eighty (180) day period, and (c) Seller completes the cure of such Main Power Transformer failure within such one hundred eighty (180) day period;

#### failure by Seller to satisfy the collateral requirements pursuant to Sections 8.7 or 8.8, including the failure to replenish the Development Security or Performance Security amount in accordance with this Agreement in the event Buyer draws against either for any reason other than to satisfy a Damage Payment or a Termination Payment, if such failure is not remedied within five (5) Business Days after Notice thereof;

#### if at any time Seller owns, operates or manages any equipment, facility, property or other asset, other than the Facility, or engages in any business or activity other than the development, financing, ownership or operation of the Facility;

#### the occurrence of six (6) consecutive months in which a WREGIS Certificate Deficit was caused, or was the result of any action or inaction, by Seller; provided, that if Seller is taking reasonable steps to prevent subsequent WREGIS Certificate Deficits and is reasonably likely to succeed in preventing the occurrence in the seventh (7th) consecutive month, then an Event of Default shall not be deemed to have occurred until the seventh (7th) consecutive month.

#### with respect to any outstanding Letter of Credit provided for the benefit of Buyer that is not then required under this Agreement to be canceled or returned, the failure by Seller to provide for the benefit of Buyer either (1) cash, or (2) a substitute Letter of Credit from a different issuer meeting the criteria set forth in the definition of Letter of Credit, in each case, in the amount required hereunder within five (5) Business Days after Seller receives Notice of the occurrence of any of the following events:

##### the issuer of the outstanding Letter of Credit shall fail to maintain a Credit Rating of at least “A-” by S&P or “A3” by Moody’s;

##### the issuer of such Letter of Credit becomes Bankrupt;

##### the issuer of the outstanding Letter of Credit shall fail to comply with or perform its obligations under such Letter of Credit and such failure shall be continuing after the lapse of any applicable grace period permitted under such Letter of Credit;

##### the issuer of the outstanding Letter of Credit shall fail to honor a properly documented request to draw on such Letter of Credit;

##### the issuer of the outstanding Letter of Credit shall disaffirm, disclaim, repudiate or reject, in whole or in part, or challenge the validity of, such Letter of Credit;

##### such Letter of Credit fails or ceases to be in full force and effect at any time; or

##### Seller shall fail to renew or cause the renewal of each outstanding Letter of Credit on a timely basis as provided in the relevant Letter of Credit and as provided in accordance with this Agreement, and in no event less than sixty (60) days prior to the expiration of the outstanding Letter of Credit.

## Remedies; Declaration of Early Termination Date. If an Event of Default with respect to a Defaulting Party shall have occurred and be continuing, the other Party (“**Non-Defaulting Party**”) shall have the following rights:

* + 1. to send Notice, designating a day, no earlier than the day such Notice is deemed to be received and no later than twenty (20) days after such Notice is deemed to be received, as an early termination date of this Agreement (“**Early Termination Date**”) that terminates this Agreement (the “**Terminated Transaction**”) and ends the Delivery Term effective as of the Early Termination Date;
		2. to accelerate all amounts owing between the Parties, and to collect as liquidated damages (i) the Damage Payment (in the case of an Event of Default by Seller under Section 11.1(b)(ii)) or (ii) the Termination Payment calculated in accordance with Section 11.3 below (in the case of any other Event of Default by either Party);
		3. to withhold any payments due to the Defaulting Party under this Agreement;
		4. to suspend performance; and/or
		5. to exercise any other right or remedy available at law or in equity, including specific performance or injunctive relief, except to the extent such remedies are expressly limited under this Agreement;

provided, that payment by the Defaulting Party of the Damage Payment or Termination Payment, as applicable, shall constitute liquidated damages and the Non-Defaulting Party’s sole and exclusive remedy for any Terminated Transaction and the Event of Default related thereto.

* 1. Termination Payment. The Termination Payment (“**Termination Payment**”) for a Terminated Transaction shall be the Settlement Amount plus any or all other amounts due to or from the Non-Defaulting Party netted into a single amount. If the Non-Defaulting Party’s aggregate Gains exceed its aggregate Losses and Costs, if any, resulting from the termination of this Agreement, the net Settlement Amount shall be zero. The Non-Defaulting Party shall calculate, in a commercially reasonable manner, a Settlement Amount for the Terminated Transaction as of the Early Termination Date. Third parties supplying information for purposes of the calculation of Gains or Losses may include, without limitation, dealers in the relevant markets, end-users of the relevant product, information vendors and other sources of market information. The Settlement Amount shall not include consequential, incidental, punitive, exemplary, indirect or business interruption damages; provided, however, that any lost Capacity Attributes and Green Attributes shall be deemed direct damages covered by this Agreement. Without prejudice to the Non-Defaulting Party’s duty to mitigate, the Non-Defaulting Party shall not have to enter into replacement transactions to establish a Settlement Amount. Each Party agrees and acknowledges that (a) the actual damages that the Non-Defaulting Party would incur in connection with a Terminated Transaction would be difficult or impossible to predict with certainty, (b) the Termination Payment described in this section is a reasonable and appropriate approximation of such damages, and (c) the Termination Payment described in this section is the exclusive remedy of the Non-Defaulting Party in connection with a Terminated Transaction but shall not otherwise act to limit any of the Non-Defaulting Party’s rights or remedies if the Non-Defaulting Party does not elect a Terminated Transaction as its remedy for an Event of Default by the Defaulting Party.

## Notice of Payment of Termination Payment. As soon as practicable after a Terminated Transaction, Notice shall be given by the Non-Defaulting Party to the Defaulting Party of the amount of the Termination Payment and whether the Termination Payment is due to or from the Non-Defaulting Party. The Notice shall include a written statement explaining in reasonable detail the calculation of such amount and the sources for such calculation. The Termination Payment shall be made to or from the Non-Defaulting Party, as applicable, within ten (10) Business Days after such Notice is effective.

## Disputes With Respect to Termination Payment. If the Defaulting Party disputes the Non-Defaulting Party’s calculation of the Termination Payment, in whole or in part, the Defaulting Party shall, within five (5) Business Days of receipt of the Non-Defaulting Party’s calculation of the Termination Payment, provide to the Non-Defaulting Party a detailed written explanation of the basis for such dispute. Disputes regarding the Termination Payment shall be determined in accordance with Article 16.

## Limitation on Seller’s Ability to Make or Agree to Third-Party Sales from the Facility after Early Termination Date. If the Agreement is terminated for any reason prior to the Commercial Operation Date other than a Buyer Event of Default, neither Seller nor Seller’s Affiliates may sell, market or deliver any Product associated with or attributable to the Facility to a party other than Buyer for a period of two (2) years following the early termination date, unless prior to selling, marketing or delivering such Product, or entering into the agreement to sell, market or deliver such Product to a party other than Buyer, Seller or Seller’s Affiliates provide Buyer with a written offer to sell the Product on terms and conditions materially similar to the terms and conditions contained in this Agreement (including price) and Buyer fails to accept such offer within forty-five (45) days of Buyer’s receipt thereof.

Neither Seller nor Seller’s Affiliates may sell or transfer the Facility, or any part thereof, or land rights or interests in the Site (including the interconnection queue position of the Facility) so long as the limitations contained in this Section 11.6 apply, unless the transferee agrees to be bound by the terms set forth in this Section 11.6 pursuant to a written agreement approved by Buyer.

Seller shall indemnify and hold Buyer harmless from all benefits lost and other damages sustained by Buyer as a result of any breach by Seller of its covenants contained within this Section 11.6.

## Rights And Remedies Are Cumulative. Except where liquidated damages are provided as the exclusive remedy, the rights and remedies of a Party pursuant to this Article 11 shall be cumulative and in addition to the rights of the Parties otherwise provided in this Agreement.

## Mitigation. Any Non-Defaulting Party shall be obligated to mitigate its Costs, Losses and damages resulting from any Event of Default of the other Party under this Agreement.

# LIMITATION OF LIABILITY AND EXCLUSION OF WARRANTIES.

## No Consequential Damages. EXCEPT TO THE EXTENT PART OF AN EXPRESS REMEDY, INDEMNITY PROVISION, OR MEASURE OF DAMAGES HEREIN, NEITHER PARTY SHALL BE LIABLE TO THE OTHER OR ITS INDEMNIFIED PERSONS FOR ANY SPECIAL, PUNITIVE, EXEMPLARY, INDIRECT, OR CONSEQUENTIAL DAMAGES, OR LOSSES OR DAMAGES FOR LOST REVENUE OR LOST PROFITS, WHETHER FORESEEABLE OR NOT, ARISING OUT OF, OR IN CONNECTION WITH THIS AGREEMENT, BY STATUTE, IN TORT OR CONTRACT.

## Waiver and Exclusion of Other Damages. EXCEPT AS EXPRESSLY SET FORTH HEREIN, THERE IS NO WARRANTY OF MERCHANTABILITY OR FITNESS FOR A PARTICULAR PURPOSE, AND ANY AND ALL IMPLIED WARRANTIES ARE DISCLAIMED. THE PARTIES CONFIRM THAT THE EXPRESS REMEDIES AND MEASURES OF DAMAGES PROVIDED IN THIS AGREEMENT SATISFY THE ESSENTIAL PURPOSES HEREOF. ALL LIMITATIONS OF LIABILITY CONTAINED IN THIS AGREEMENT, INCLUDING, WITHOUT LIMITATION, THOSE PERTAINING TO SELLER’S LIMITATION OF LIABILITY AND THE PARTIES’ WAIVER OF CONSEQUENTIAL DAMAGES, SHALL APPLY EVEN IF THE REMEDIES FOR BREACH OF WARRANTY PROVIDED IN THIS AGREEMENT ARE DEEMED TO “FAIL OF THEIR ESSENTIAL PURPOSE” OR ARE OTHERWISE HELD TO BE INVALID OR UNENFORCEABLE.

FOR BREACH OF ANY PROVISION FOR WHICH AN EXPRESS AND EXCLUSIVE REMEDY OR MEASURE OF DAMAGES IS PROVIDED, SUCH EXPRESS REMEDY OR MEASURE OF DAMAGES SHALL BE THE SOLE AND EXCLUSIVE REMEDY, THE OBLIGOR’S LIABILITY SHALL BE LIMITED AS SET FORTH IN SUCH PROVISION, AND ALL OTHER REMEDIES OR DAMAGES AT LAW OR IN EQUITY ARE WAIVED.

IF NO REMEDY OR MEASURE OF DAMAGES IS EXPRESSLY PROVIDED HEREIN, THE OBLIGOR’S LIABILITY SHALL BE LIMITED TO DIRECT DAMAGES ONLY. THE VALUE OF ANY TAX BENEFITS, DETERMINED ON AN AFTER-TAX BASIS, LOST DUE TO BUYER’S DEFAULT (WHICH SELLER HAS NOT BEEN ABLE TO MITIGATE AFTER USE OF REASONABLE EFFORTS) AND AMOUNTS DUE IN CONNECTION WITH THE RECAPTURE OF ANY RENEWABLE ENERGY INCENTIVES, IF ANY, SHALL BE DEEMED TO BE DIRECT DAMAGES.

TO THE EXTENT ANY DAMAGES REQUIRED TO BE PAID HEREUNDER ARE LIQUIDATED, INCLUDING THE DAMAGE PAYMENT UNDER SECTION 11.2 AND THE TERMINATION PAYMENT UNDER SECTION 11.3, AND AS PROVIDED IN EXHIBIT B AND EXHIBIT D, THE PARTIES ACKNOWLEDGE THAT THE DAMAGES ARE DIFFICULT OR IMPOSSIBLE TO DETERMINE, THAT OTHERWISE OBTAINING AN ADEQUATE REMEDY IS INCONVENIENT, AND THAT THE LIQUIDATED DAMAGES CONSTITUTE A REASONABLE APPROXIMATION OF THE ANTICIPATED HARM OR LOSS, AND (UNLESS EXPRESSLY STATED TO THE CONTRARY) AN EXCLUSIVE REMEDY. IT IS THE INTENT OF THE PARTIES THAT THE LIMITATIONS HEREIN IMPOSED ON REMEDIES AND THE MEASURE OF DAMAGES BE WITHOUT REGARD TO THE CAUSE OR CAUSES RELATED THERETO, INCLUDING THE NEGLIGENCE OF ANY PARTY, WHETHER SUCH NEGLIGENCE BE SOLE, JOINT OR CONCURRENT, OR ACTIVE OR PASSIVE. THE PARTIES HEREBY WAIVE ANY RIGHT TO CONTEST SUCH PAYMENTS AS AN UNREASONABLE PENALTY.

# REPRESENTATIONS AND WARRANTIES; AUTHORITY

## Seller’s Representations and Warranties. As of the Effective Date, Seller represents and warrants as follows:

* + 1. Seller is a **[\_\_\_\_\_\_\_]** company, duly organized, validly existing and in good standing under the laws of the State of **[\_\_\_\_\_\_\_]**, and is qualified to conduct business in each jurisdiction where the failure to so qualify would have a material adverse effect on the business or financial condition of Seller.
		2. Seller has the power and authority to enter into and perform this Agreement and is not prohibited from entering into this Agreement or discharging and performing all covenants and obligations on its part to be performed under and pursuant to this Agreement, except where such failure does not have a material adverse effect on Seller’s performance under this Agreement. The execution, delivery and performance of this Agreement by Seller has been duly authorized by all necessary corporate action on the part of Seller and does not and will not require the consent of any trustee or holder of any indebtedness or other obligation of Seller or any other party to any other agreement with Seller.
		3. The execution and delivery of this Agreement, consummation of the transactions contemplated herein, and fulfillment of and compliance by Seller with the provisions of this Agreement will not conflict with or constitute a breach of or a default under any Law presently in effect having applicability to Seller, subject to any permits that have not yet been obtained by Seller, the documents of formation of Seller or any outstanding trust indenture, deed of trust, mortgage, loan agreement or other evidence of indebtedness or any other agreement or instrument to which Seller is a party or by which any of its property is bound.
		4. This Agreement has been duly executed and delivered by Seller. This Agreement is a legal, valid and binding obligation of Seller enforceable in accordance with its terms, except as limited by Laws of general applicability limiting the enforcement of creditors’ rights or by the exercise of judicial discretion in accordance with general principles of equity.
		5. The Facility is located in the State of **[\_\_\_\_\_\_\_\_\_\_]**.

(f) All Energy and associated Green Attributes sold and delivered to Buyer hereunder, qualify as PCC1.

## Buyer’s Representations and Warranties. As of the Effective Date, Buyer represents and warrants as follows:

* + 1. Buyer is a joint powers authority and a validly existing community choice aggregator, duly organized, validly existing and in good standing under the laws of the State of California and the rules, regulations and orders of the California Public Utilities Commission, and is qualified to conduct business in each jurisdiction of the Joint Powers Agreement members. All persons making up the governing body of Buyer are the elected or appointed incumbents in their positions and hold their positions in good standing in accordance with the Joint Powers Agreement and other Law.
		2. Buyer has the power and authority to enter into and perform this Agreement and is not prohibited from entering into this Agreement or discharging and performing all covenants and obligations on its part to be performed under and pursuant to this Agreement, except where such failure does not have a material adverse effect on Buyer’s performance under this Agreement. The execution, delivery and performance of this Agreement by Buyer has been duly authorized by all necessary action on the part of Buyer and does not and will not require the consent of any trustee or holder of any indebtedness or other obligation of Buyer or any other party to any other agreement with Buyer.
		3. The execution and delivery of this Agreement, consummation of the transactions contemplated herein, and fulfillment of and compliance by Buyer with the provisions of this Agreement will not conflict with or constitute a breach of or a default under any Law presently in effect having applicability to Buyer, including but not limited to community choice aggregation, the Joint Powers Act, competitive bidding, public notice, open meetings, election, referendum, or prior appropriation requirements, the documents of formation of Buyer or any outstanding trust indenture, deed of trust, mortgage, loan agreement or other evidence of indebtedness or any other agreement or instrument to which Buyer is a party or by which any of its property is bound.
		4. This Agreement has been duly executed and delivered by Buyer. This Agreement is a legal, valid and binding obligation of Buyer enforceable in accordance with its terms, except as limited by Laws of general applicability limiting the enforcement of creditors’ rights or by the exercise of judicial discretion in accordance with general principles of equity.
		5. Buyer warrants and covenants that with respect to its contractual obligations under this Agreement, it will not claim immunity on the grounds of sovereignty or similar grounds with respect to itself or its revenues or assets from (1) suit, (2) jurisdiction of court, (3) relief by way of injunction, order for specific performance or recovery of property, (4) attachment of assets, or (5) execution or enforcement of any judgment.
		6. Buyer is a “local public entity” as defined in Section 900.4 of the Government Code of the State of California.

## General Covenants. Each Party covenants that commencing on the Effective Date and continuing throughout the Contract Term:

* + 1. It shall continue to be duly organized, validly existing and in good standing under the Laws of the jurisdiction of its formation and to be qualified to conduct business in each jurisdiction where the failure to so qualify would have a material adverse effect on its business or financial condition;
		2. It shall maintain (or obtain from time to time as required) all regulatory authorizations necessary for it to legally perform its obligations under this Agreement; and
		3. It shall perform its obligations under this Agreement in compliance with all terms and conditions in its governing documents and any contracts to which it is a party and in material compliance with any Law.

## Prohibition Against Forced Labor. Seller represents and warrants that it has not and will not knowingly utilize equipment or resources for the construction, operation or maintenance of the Facility that rely on work or services exacted from any person under the threat of a penalty and for which the person has not offered himself or herself voluntarily (“**Forced Labor**”). Consistent with the business advisory jointly issued by the U.S. Departments of State, Treasury, Commerce and Homeland Security on July 1, 2020, equipment or resources sourced from the Xinjiang region of China are presumed to involve Forced Labor. Seller shall certify that it will not utilize such equipment or resources in connection with the construction, operation or maintenance of the Facility.

# ASSIGNMENT

## General Prohibition on Assignments. Except as provided below and in Article 15, neither Seller nor Buyer may voluntarily assign its rights nor delegate its duties under this Agreement, or any part of such rights or duties, without the written consent of the other Party. Neither Seller nor Buyer shall unreasonably withhold, condition or delay any requested consent to an assignment that is allowed by the terms of this Agreement. Any such assignment or delegation made without such written consent or in violation of the conditions to assignment set out below shall be null and void.

## Permitted Assignment; Change of Control of Seller. Seller may, without the prior written consent of Buyer, transfer or assign this Agreement to: (a) an Affiliate of Seller; or (b) subject to Section 15.1, a Lender as collateral. Any direct or indirect Change of Control of Seller (whether voluntary or by operation of Law) shall be deemed an assignment under this Article 14 and will require the prior written consent of Buyer, which consent shall not be unreasonably withheld.

## Permitted Assignment; Change of Control of Buyer. Buyer may assign its interests in this Agreement to an Affiliate of Buyer or to any entity that has acquired all or substantially all of Buyer’s assets or business, whether by merger, acquisition or otherwise without Seller’s prior written consent, *provided*, that in each of the foregoing situations, the assignee (a) has a Credit Rating of Baa2 or higher by Moody’s or BBB or higher by S&P, and (b) is a community choice aggregator or publicly-owned electric utility with retail customers located in the state of California; *provided*, *further*, that in each such case, no fewer than fifteen (15) Business Days before such assignment Buyer (x) notifies Seller of such assignment and (y) provides to Seller a written agreement signed by the Person to which Buyer wishes to assign its interests stating that such Person agrees to assume all of Buyer’s obligations and liabilities under this Agreement and under any consent to assignment and other documents previously entered into by Seller as described in Section 15.2(b). Any assignment by Buyer, its successors or assigns under this Section 14.3 shall be of no force and effect unless and until such Notice and agreement by the assignee have been received and accepted by Seller.

# LENDER ACCOMMODATIONS

## Granting of Lender Interest. Notwithstanding Section 14.2 or Section 14.3, either Party may, without the consent of the other Party, grant an interest (by way of collateral assignment, or as security, beneficially or otherwise) in its rights and/or obligations under this Agreement to any Lender. Each Party’s obligations under this Agreement shall continue in their entirety in full force and effect. Promptly after granting such interest, the granting Party shall notify the other Party in writing of the name, address, and telephone and facsimile numbers of any Lender to which the granting Party’s interest under this Agreement has been assigned. Such Notice shall include the names of the Lenders to whom all written and telephonic communications may be addressed. After giving the other Party such initial Notice, the granting Party shall promptly give the other Party Notice of any change in the information provided in the initial Notice or any revised Notice.

## Rights of Lender. If a Party grants an interest under this Agreement as permitted by Section 15.1, the following provisions shall apply:

* + 1. Lender shall have the right, but not the obligation, to perform any act required to be performed by the granting Party under this Agreement to prevent or cure a default by the granting Party in accordance with Section 11.2 and such act performed by Lender shall be as effective to prevent or cure a default as if done by the granting Party.
		2. The other Party shall cooperate with the granting Party or any Lender, to execute or arrange for the delivery of certificates, consents, opinions, estoppels, direct agreements, amendments and other documents reasonably requested by the granting Party or Lender in order to consummate any financing or refinancing and shall enter into reasonable agreements with such Lender that provide that the non-granting Party recognizes the Lender’s security interest and such other provisions as may be reasonably requested by the granting Party or any such Lender; *provided*, however, that all costs and expenses (including reasonable attorney’s fees) incurred by the non-granting Party in connection therewith shall be borne by the granting Party, and that the non-granting Party shall have no obligation to modify this Agreement or to reduce its benefits or increase its risks or burdens under this Agreement.
		3. Each Party agrees that no Lender shall be obligated to perform any obligation or be deemed to incur any liability or obligation provided in this Agreement on the part of the granting Party or shall have any obligation or liability to the other Party with respect to this Agreement except to the extent any Lender has expressly assumed the obligations of the granting Party hereunder; *provided* that the non-granting Party shall nevertheless be entitled to exercise all of its rights hereunder in the event that the granting Party or Lender fails to perform the granting Party’s obligations under this Agreement.

## Cure Rights of Lender. The non-granting Party shall provide Notice of the occurrence of any Event of Default described in Sections 11.1 or 11.2 hereof to any Lender, and such Party shall accept a cure performed by any Lender and shall negotiate in good faith with any Lender as to the cure period(s) that will be allowed for any Lender to cure any granting Party Event of Default hereunder. The non-granting Party shall accept a cure performed by any Lender so long as the cure is accomplished within the applicable cure period so agreed to between the non-granting Party and any Lender. Notwithstanding any such action by any Lender, the granting Party shall not be released and discharged from and shall remain liable for any and all obligations to the non-granting Party arising or accruing hereunder. The cure rights of Lender may be documented in the certificates, consents, opinions, estoppels, direct agreements, amendments and other documents reasonably requested by the granting Party pursuant to Section 15.2(b).

# DISPUTE RESOLUTION

## Governing Law. This agreement and the rights and duties of the parties hereunder shall be governed by and construed, enforced and performed in accordance with the laws of the state of California, without regard to principles of conflicts of law. To the extent enforceable at such time, each party waives its respective right to any jury trial with respect to any litigation arising under or in connection with this agreement.

## Dispute Resolution. In the event of any dispute arising under this Agreement, within ten (10) days following the receipt of a written Notice from either Party identifying such dispute, the Parties shall meet, negotiate and attempt, in good faith, to resolve the dispute quickly, informally and inexpensively. If the Parties are unable to resolve a dispute arising hereunder within the earlier of either thirty (30) days of initiating such discussions, or within forty (40) days after Notice of the dispute, either Party may seek any and all remedies available to it at Law or in equity, subject to the limitations set forth in this Agreement.

## Attorneys’ Fees. In any proceeding brought to enforce this Agreement or because of the breach by any Party of any covenant or condition herein contained, the prevailing Party shall be entitled to reasonable attorneys’ fees (including reasonably allocated fees of in-house counsel) in addition to court costs and any and all other costs recoverable in said action.

## **Venue**. The Parties agree that any litigation arising with respect to this Agreement is to be venued in the Superior Court for the county of San Mateo, California.

# INDEMNIFICATION

## Indemnification.

* + 1. Each Party (the “**Indemnifying Party**”) agrees to indemnify, defend and hold harmless the other Party and its Affiliates, directors, officers, employees and agents (collectively, the “**Indemnified Party**”) from and against all third-party claims, demands, losses, liabilities, penalties, and expenses (including reasonable attorneys’ fees) for personal injury or death to Persons and damage to the property of any third party to the extent arising out of, resulting from, or caused by the violation of Law or the negligent or willful misconduct of the Indemnifying Party, its Affiliates, its directors, officers, employees, or agents.
		2. Nothing in this Section 17.1 shall enlarge or relieve Seller or Buyer of any liability to the other for any breach of this Agreement. Neither Party shall be indemnified for its damages resulting from its sole negligence, intentional acts or willful misconduct. These indemnity provisions shall not be construed to relieve any insurer of its obligation to pay claims consistent with the provisions of a valid insurance policy.

## Claims. Promptly after receipt by a Party of any claim or Notice of the commencement of any action, administrative, or legal proceeding, or investigation as to which the indemnity provided for in this Article 17 may apply, the Indemnified Party shall notify the Indemnifying Party in writing of such fact. The Indemnifying Party shall assume the defense thereof with counsel designated by such Party and satisfactory to the Indemnified Party, *provided*, *however*, that if the defendants in any such action include both the Indemnified Party and the Indemnifying Party and the Indemnified Party shall have reasonably concluded that there may be legal defenses available to it which are different from or additional to, or inconsistent with, those available to the Indemnifying Party, the Indemnified Party shall have the right to select and be represented by separate counsel, at the Indemnifying Party’s expense, unless a liability insurer is willing to pay such costs.

If the Indemnifying Party fails to assume the defense of a claim meriting indemnification, the Indemnified Party may at the expense of the Indemnifying Party contest, settle, or pay such claim, *provided* that settlement or full payment of any such claim may be made only following consent of the Indemnifying Party or, absent such consent, written opinion of the Indemnified Party’s counsel that such claim is meritorious or warrants settlement. Except as otherwise provided in this Article 17, in the event that a Party is obligated to indemnify and hold the other Party and its successors and assigns harmless under this Article 17, the amount owing to the Indemnified Party will be the amount of the Indemnified Party’s damages net of any insurance proceeds received by the Indemnified Party following a reasonable effort by the Indemnified Party to obtain such insurance proceeds.

# INSURANCE

## Insurance.

* + 1. General. Seller shall comply at all times during the Contract Term with the requirements of Exhibit J.
		2. Subcontractor Insurance. Seller shall require all of its subcontractors to carry: (i) comprehensive general liability insurance in amounts equal to those set forth for Seller in Exhibit J; (ii) workers’ compensation insurance and employers’ liability coverage in accordance with applicable requirements of Law; and (iii) business auto insurance for bodily injury and property damage, in each case, in amounts equal to those set forth for Seller in Exhibit J. All subcontractors shall name Seller as an additional insured to insurance carried pursuant to clauses (f)(i) and (f)(iii). All subcontractors shall provide a primary endorsement and a waiver of subrogation to Seller for the required coverage pursuant to this Section 18.1(b).
		3. Evidence of Insurance. Within ten (10) days after execution of the Agreement and upon annual renewal thereafter, Seller shall deliver to Buyer certificates of insurance evidencing such coverage. These certificates shall specify that Buyer shall be given at least thirty (30) days prior Notice by Seller in the event of any material modification, cancellation or termination of coverage. Such insurance shall be primary coverage without right of contribution from any insurance of Buyer. Any other insurance maintained by Seller is for the exclusive benefit of Seller and shall not in any manner inure to the benefit of Buyer. Seller shall also comply with all insurance requirements by any renewable energy or other incentive program administrator or any other applicable authority.
		4. Failure to Comply with Insurance Requirements. If Seller fails to comply with any of the provisions of this Article 18, Seller, among other things and without restricting Buyer’s remedies under the Law or otherwise, shall, at its own cost and expense, act as an insurer and provide insurance in accordance with the terms and conditions above. With respect to the required general liability, umbrella liability and commercial automobile liability insurance, Seller shall provide a current, full and complete defense to Buyer, its subsidiaries and Affiliates, and their respective officers, directors, shareholders, agents, employees, assigns, and successors in interest, in response to a third-party claim in the same manner that an insurer would have, had the insurance been maintained in accordance with the terms and conditions set forth above. In addition, alleged violations of the provisions of this Article 18 means that Seller has the initial burden of proof regarding any legal justification for refusing or withholding coverage and Seller shall face the same liability and damages as an insurer for wrongfully refusing or withholding coverage in accordance with the laws of California.

# CONFIDENTIAL INFORMATION

## Definition of Confidential Information. The following constitutes “**Confidential Information**,” whether oral or written, and whether delivered by Seller to Buyer or by Buyer to Seller: (a) proposals and negotiations of the Parties in the negotiation of this Agreement; (b) the terms and conditions of this Agreement; and (c) information that either Seller or Buyer stamps or otherwise identifies as “confidential” or “proprietary” or words of similar import before disclosing it to the other. Confidential Information does not include (i) information that was publicly available at the time of the disclosure, other than as a result of a disclosure in breach of this Agreement; (ii) information that becomes publicly available through no fault of the recipient; (iii) information that was rightfully in the possession of the recipient (without confidential or proprietary restriction) at the time of delivery or that becomes available to the recipient from a source not subject to any restriction against disclosing such information to the recipient; and (iv) information that the recipient independently developed without a violation of this Agreement.

## Duty to Maintain Confidentiality. The Party receiving Confidential Information shall treat it as confidential, and shall adopt reasonable information security measures to maintain its confidentiality, employing the higher of (a) the standard of care that the receiving Party uses to preserve its own confidential information, or (b) a standard of care reasonably tailored to prevent unauthorized use or disclosure of such Confidential Information. Confidential Information may be disclosed by the recipient if and to the extent such disclosure is required (a) by Law, (b) pursuant to an order of a court or (c) in order to enforce this Agreement. The Party that originally discloses Confidential Information may use such information for its own purposes, and may publicly disclose such information at its own discretion. Notwithstanding the foregoing, Seller acknowledges that Buyer is required to make portions of this Agreement available to the public in connection with the process of seeking approval from its board of directors for execution of this Agreement. Buyer may, in its discretion, redact certain terms of this Agreement as part of any such public disclosure, and will use reasonable efforts to consult with Seller prior to any such public disclosure. Seller further acknowledges that Buyer is a public agency subject to the requirements of the California Public Records Act (Cal. Gov. Code section 6250 et seq.). Upon request or demand from any third person not a Party to this Agreement for production, inspection and/or copying of this Agreement or other Confidential Information provided by Seller to Buyer, Buyer shall, to the extent permissible, notify Seller in writing in advance of any disclosure that the request or demand has been made; provided that, upon the advice of its counsel that disclosure is required, Buyer may disclose this Agreement or any other requested Confidential Information, whether or not advance written notice to Seller has been provided. Seller shall be solely responsible for taking whatever steps it deems necessary to protect Confidential Information that is the subject of any Public Records Act request submitted by a third person to Buyer.

## Irreparable Injury; Remedies. Buyer and Seller each agree that disclosing Confidential Information of the other in violation of the terms of this Article 19 may cause irreparable harm, and that the harmed Party may seek any and all remedies available to it at Law or in equity, including injunctive relief and/or notwithstanding Section 12.2, consequential damages.

## Disclosure to Lender. Notwithstanding anything to the contrary in this Article 19, Confidential Information may be disclosed by Seller to any potential Lender or any of its agents, consultants or trustees so long as the Person to whom Confidential Information is disclosed agrees in writing to be bound by the confidentiality provisions of this Article 19 to the same extent as if it were a Party.

## Disclosure to Credit Rating Agency**.** Notwithstanding anything to the contrary in this Article 19, Confidential Information may be disclosed by either Party to any nationally recognized credit rating agency (e.g., Moody’s Investors Service, Standard & Poor’s, or Fitch Ratings) in connection with the issuance of a credit rating for that Party or its Affiliates, provided that any such credit rating agency agrees in writing to maintain the confidentiality of such Confidential Information.

## Public Statements. Neither Party shall issue (or cause its Affiliates to issue) a press release regarding the transactions contemplated by this Agreement unless both Parties have agreed upon the contents of any such press release.

# MISCELLANEOUS

## Entire Agreement; Integration; Exhibits. This Agreement, together with the Cover Sheet and Exhibits attached hereto constitutes the entire agreement and understanding between Seller and Buyer with respect to the subject matter hereof and supersedes all prior agreements relating to the subject matter hereof, which are of no further force or effect. The Exhibits attached hereto are integral parts hereof and are made a part of this Agreement by reference. The headings used herein are for convenience and reference purposes only. In the event of a conflict between the provisions of this Agreement and those of the Cover Sheet or any Exhibit, the provisions of first the Cover Sheet, and then this Agreement shall prevail, and such Exhibit shall be corrected accordingly. This Agreement shall be considered for all purposes as prepared through the joint efforts of the Parties and shall not be construed against one Party or the other as a result of the preparation, substitution, submission or other event of negotiation, drafting or execution hereof.

## Amendments. This Agreement may only be amended, modified or supplemented by an instrument in writing executed by duly authorized representatives of Seller and Buyer; *provided*, that, for the avoidance of doubt, this Agreement may not be amended by electronic mail communications.

## Time is of the Essence. The Parties agree that time is of the essence with respect each Party’s performance of its obligations under the Agreement.

## No Waiver**.** Waiver by a Party of any default by the other Party shall not be construed as a waiver of any other default.

## No Agency, Partnership, Joint Venture or Lease. Seller and the agents and employees of Seller shall, in the performance of this Agreement, act in an independent capacity and not as officers or employees or agents of Buyer. Under this Agreement, Seller and Buyer intend to act as energy seller and energy purchaser, respectively, and do not intend to be treated as, and shall not act as, partners in, co-venturers in or lessor/lessee with respect to the Facility or any business related to the Facility. This Agreement shall not impart any rights enforceable by any third party (other than a permitted successor or assignee bound to this Agreement).

## Severability

. In the event that any provision of this Agreement is unenforceable or held to be unenforceable, the Parties agree that all other provisions of this Agreement have force and effect and shall not be affected thereby. The Parties shall, however, use their best endeavors to agree on the replacement of the void, illegal or unenforceable provision(s) with legally acceptable clauses which correspond as closely as possible to the sense and purpose of the affected provision and this Agreement as a whole.

## Mobile-Sierra. Notwithstanding any other provision of this Agreement, neither Party shall seek, nor shall they support any third party seeking, to prospectively or retroactively revise the rates, terms or conditions of service of this Agreement through application or complaint to FERC pursuant to the provisions of Section 205, 206 or 306 of the Federal Power Act, or any other provisions of the Federal Power Act, absent prior written agreement of the Parties. Further, absent the prior written agreement in writing by both Parties, the standard of review for changes to the rates, terms or conditions of service of this Agreement proposed by a Party, a non-Party or the FERC acting *sua sponte* shall be the “public interest” standard of review set forth in United Gas Pipe Line Co. v. Mobile Gas Service Corp., 350 U.S. 332 (1956) and Federal Power Commission v. Sierra Pacific Power Co., 350 U.S. 348 (1956).

## Counterparts. This Agreement may be executed in one or more counterparts, all of which taken together shall constitute one and the same instrument and each of which shall be deemed an original.

## Facsimile or Electronic Delivery. This Agreement may be duly executed and delivered by a Party by execution and facsimile or electronic format (including portable document format (.pdf)) delivery of the signature page of a counterpart to the other Party, and, if delivery is made by facsimile or other electronic format, the executing Party shall promptly deliver, via overnight delivery, a complete original counterpart that it has executed to the other Party, but this Agreement shall be binding on and enforceable against the executing Party whether or not it delivers such original counterpart.

## Binding Effect. This Agreement shall inure to the benefit of and be binding upon the Parties and their respective successors and permitted assigns.

## No Recourse to Members of Buyer. Buyer is organized as a Joint Powers Authority in accordance with the Joint Exercise of Powers Act of the State of California (Government Code Section 6500, et seq.) pursuant to its Joint Powers Agreement and is a public entity separate from its constituent members. Buyer shall solely be responsible for all debts, obligations and liabilities accruing and arising out of this Agreement. Seller shall have no rights and shall not make any claims, take any actions or assert any remedies against any of Buyer’s constituent members, or the employees, directors, officers, consultants or advisors of Buyer or its constituent members, in connection with this Agreement.

## Change in Electric Market Design. If a change in the CAISO Tariff renders this Agreement or any provisions hereof incapable of being performed or administered, then any Party may request that Buyer and Seller enter into negotiations to make the minimum changes to this Agreement necessary to make this Agreement capable of being performed and administered, while attempting to preserve to the maximum extent possible the benefits, burdens, and obligations set forth in this Agreement as of the Effective Date. If a change to any Law occurs after the Effective Date, including any rule or requirement of WREGIS, that impacts the number or quality of Resource Adequacy Benefits or Green Attributes (including Renewable Energy Credits) available to Buyer from the Facility, then Buyer may request that Buyer and Seller enter into negotiations to make the minimum changes to this Agreement necessary to preserve to the maximum extent possible the benefits, burdens, and obligations set forth in this Agreement as of the Effective Date, it being understood that (i) Buyer is to receive the maximum amount of Resource Adequacy Benefits and Green Attributes available from the Facility and (ii) Seller’s ongoing compliance costs associated with the provision of Resource Adequacy Benefits and Green Attributes available from the Facility, among other things, are subject to the Compliance Expenditure Cap. Upon delivery of such a request, Buyer and Seller shall engage in such negotiations in good faith. If Buyer and Seller are unable, within sixty (60) days after delivery of such request, to agree upon changes to this Agreement or to resolve issues relating to changes to this Agreement, then any Party may submit issues pertaining to changes to this Agreement to the dispute resolution process set forth in Article 16. Notwithstanding the foregoing, (i) a change in cost shall not in and of itself be deemed to render this Agreement or any of the provisions hereof incapable of being performed or administered, or constitute, or form the basis of, a Force Majeure Event, and (ii) this Agreement shall remain in full force and effect, subject to any necessary changes, if any, agreed to by the Parties or determined through dispute resolution.

# CPUC MODIFIABLE STANDARD CONTRACT TERMS

## STC 2: Bioenergy Transactions**.**

1. For all electric generation using biomethane as fuel, Seller shall transfer to Buyer sufficient renewable and environmental attributes of biomethane production and capture to ensure that there are zero net emissions associated with the production of electricity from the generating facility using the biomethane.

2. For all electric generation using biomethane as fuel, neither Buyer nor Seller may make a marketing, regulatory, or retail claim that asserts that a procurement contract to which that entity was a party resulted, or will result, in greenhouse gas reductions related to the destruction of methane if the capture and destruction is required by law. If the capture and destruction of the biomethane is not required by law, neither Buyer nor Seller may make a marketing, regulatory, or retail claim that asserts that a procurement contract to which that entity was a party resulted, or will result, in greenhouse gas reductions related to the destruction of methane, unless the environmental attributes associated with the capture and destruction of the biomethane pursuant to that contract are transferred to Buyer and retired on behalf of the retail customers consuming the electricity associated with the use of that biomethane, or unless Seller's procurement contract with the source of biomethane prohibits the source of biomethane from separately marketing the environmental attributes associated with the capture and destruction of the biomethane sold pursuant to that contract, and such attributes have been retired.

(See: D.13-11-024)

## STC 4: Confidentiality. Section 10.11 of the Agreement is deleted in its entirety and is replaced with the following provision, irrespective of the election made by Seller on the Cover Sheet:

“Confidentiality: Neither Party shall disclose the non-public terms or conditions of this Agreement or any Transaction hereunder to a third party, other than (i) the Party’s employees, lenders, counsel, accountants or advisors who have a need to know such information and have agreed to keep such terms confidential, (ii) for disclosure to the Buyer’s Procurement Review Group, as defined in CPUC Decision (D.) 02-08-071, subject to a confidentiality agreement, (iii) to the CPUC under seal for purposes of review, (iv) disclosure of terms specified in and pursuant to Section 10.12 of this Agreement; (v) in order to comply with any applicable law, regulation, or any exchange, control area or ISO rule, or order issued by a court or entity with competent jurisdiction over the disclosing Party (‘Disclosing Party’), other than to those entities set forth in subsection (vi); or (vi) in order to comply with any applicable regulation, rule, or order of the CPUC, CEC, or the Federal Energy Regulatory Commission. In connection with requests made pursuant to clause (v) of this Section 10.11 (‘Disclosure Order’) each Party shall, to the extent practicable, use reasonable efforts: (i) to notify the other Party prior to disclosing the confidential information and (ii) prevent or limit such disclosure. After using such reasonable efforts, the Disclosing Party shall not be: (i) prohibited from complying with a Disclosure Order or (ii) liable to the other Party for monetary or other damages incurred in connection with the disclosure of the confidential information. Except as provided in the preceding sentence, the Parties shall be entitled to all remedies available at law or in equity to enforce, or seek relief in connection with, this confidentiality obligation.”

The following new Section 10.12 shall be added as follows:

“10.12 RPS Confidentiality. Notwithstanding Section 10.11 of this Agreement at any time on or after the date on which the Buyer makes its advice filing letter seeking CPUC Approval of the Agreement either Party shall be permitted to disclose the following terms with respect to such Transaction: Party names, resource type, delivery term, project location, and project capacity. If Option B is checked on the Cover Sheet, neither Party shall disclose party name or project location, pursuant to this Section 10.12, until six months after such CPUC Approval.”

The Cover Sheet of the Agreement shall be amended by adding to Article 10, Confidentiality, a new “Option B,” as follows:

 Option B RPS Confidentiality Applicable. If not checked, inapplicable”

 Option C Confidentiality Notification: If Option C is checked on the Cover Sheet, Seller has waived its right to notification in accordance with

Section 10.11 (v).”

(*See* D.04-06-014, Appendix A.)

## STC 5: Contract Term. The following provision shall be included as a standard term in the Confirmation(s) for the Transaction(s) entered into under the Agreement.

“Delivery Term: The Parties shall specify the period of Product delivery for the ‘Delivery Term,’ as defined herein, by checking one of the following boxes:

 Delivery shall be for a period of ten (10) years.

 Delivery shall be for a period of fifteen (15) years.

 Delivery shall be for a period of twenty (20) years.

 Non-standard Delivery shall be for a period of years.”

If the “Non-standard Delivery” contract term is selected, Parties need to apply to the CPUC justifying the need for non-standard delivery.

(*See*: D.04-06-014, Appendix A.)

## STC 7: Performance Standards/Requirements.

1. The following shall be included in the applicable post Commercial Operation Date performance standards/requirement provisions of the Agreement or Confirmation for “As Available” projects:

“Energy Production Guarantees

The Buyer shall in its sole discretion have the right to declare an Event of Default if Seller fails to achieve the Guaranteed Energy Production in any [12 month period] [or] [24 month period] and such failure is not excused by the reasons set forth in subsections (ii), (iii), or (v) of Section of this Agreement, “Excuses for Failure to Perform.”

Guaranteed Energy Production = MWh.”

1. The following shall be included in the applicable performance standards/requirement provisions, as “Excuses for Failure to Perform” in the Agreement or Confirmation for “As Available” projects:

“Seller shall not be liable to Buyer for any damages determined pursuant to Article Four of the Agreement in the event that Seller fails to deliver the Product to Buyer for any of the following reasons:

* 1. if the specified generation asset(s) are unavailable as a result of a Forced Outage (as defined in the NERC Generating Unit Availability Data System (GADS) Forced Outage reporting guidelines) and such Forced Outage is not the result of Seller’s negligence or willful misconduct;
	2. Force Majeure;
	3. by the Buyer’s failure to perform;
	4. by scheduled maintenance outages of the specified units;
	5. a reduction in Output as ordered under terms of the dispatch down and Curtailment provisions (including CAISO or Buyer’s system emergencies); or
	6. [the unavailability of landfill gas which was not anticipated as of the date this [Confirmation] was agreed to, which is not within the reasonable control of, or the result of negligence of, Seller or the party supplying such landfill gas to the Project, and which by the exercise of reasonable due diligence, Seller is unable to overcome or avoid or causes to be avoided; OR

insufficient wind power for the specified units to generate energy as determined by the best wind speed and direction standards utilized by other wind producers or purchasers in the vicinity of the Project or if wind speeds exceed the specified units’ technical specifications; OR

the unavailability of water or the unavailability of sufficient pressure required for operation of the hydroelectric turbine-generator as reasonably determined by Seller within its operating procedures, neither of which was anticipated as of the date this [Confirmation] was agreed to, which is not within the reasonable control of, or the result of negligence of, Seller or the party supplying such water to the Project, and which by the exercise of due diligence, such Seller or the party supplying the water is unable to overcome or avoid or causes to be avoided.]

The performance of the Buyer to receive the Product may be excused only (i) during periods of Force Majeure, (ii) by the Seller’s failure to perform or (iii) during dispatch down periods.”

1. The following shall be included in the applicable performance standards/requirement provisions as “Excuses for Failure to Perform” in the Agreement or Confirmation for “Unit Firm” projects:

“Net Rated Output Capacity. If the Net Rated Output Capacity at the Commercial Operation Date or at the end of the first twelve (12) consecutive months after the Commercial Operation Date [and every twelve (12) consecutive months thereafter] is less than MW, Buyer shall have the right to declare an Event of Default. For subsequent contract years, Buyer shall trigger an Annual Capacity Test to determine each year’s Net Rated Output Capacity by scheduling Deliveries from the facility for two consecutive weeks. Buyer shall provide Seller two (2) weeks notice of the Annual Capacity Test. For the second year and thereafter the Net Rated Output Capacity shall be the ratio of the sum of average hourly Energy Delivered for two

1. weeks divided by 336 hours (24 hours x 14 days). Energy Delivered shall exclude any energy greater than MW average in each hour. The resulting Net Rated Output Capacity shall remain in effect until the next Annual Capacity Test. The Net Rated Output Capacity shall not exceed the Contract Capacity of MW.

Additional Event of Default. It shall be an additional Event of Default if (i) the Availability Adjustment Factor is less than % for consecutive months, or (ii) Net Rated Output Capacity falls below MW. In no event shall the Seller have the right to procure Energy from sources other than the Facility for sale and delivery pursuant to this Agreement.”

1. The following shall be included in the applicable performance standards/requirement provisions of the Agreement or Confirmation for “Unit Firm” projects:

“Seller shall be excused from achieving the Availability Adjustment Factor for the applicable time period, in the event that Seller fails to deliver the Product to Buyer for any of the following reason:

* 1. during Force Majeure;
	2. by Buyer’s failure to perform; or,
	3. a reduction in Output as ordered under terms of the dispatch-down and Curtailment provisions (including CAISO or Buyer’s system emergencies.)
1. The following shall be included in the applicable performance standards/requirement provisions as “Excuses for Failure to Perform” in the Agreement or Confirmation for “Unit Firm,” “Baseload,” “Peaking,” and ”Dispatchable” Products:

“Seller shall not be liable to Buyer for any damages determined pursuant to

Article Four of the Agreement, in the event that Seller fails to deliver the Product to Buyer for any of the following reason:

1. if the specified generation asset(s) are unavailable as a result of a Forced Outage (as defined in the NERC Generating Unit Availability Data System (GADS) Forced Outage reporting guidelines) and such Forced Outage is not the result of Seller’s negligence or willful misconduct;
2. Force Majeure;
3. by the Buyer’s failure to perform;
4. by scheduled maintenance outages of the specified units; or, a reduction in Output as ordered under terms of the dispatch down and Curtailment provisions (including CAISO or Buyer’s system emergencies).”

The performance of the Buyer to receive the product may be excused only (i) during periods of Force Majeure, (ii) during periods of dispatch-down, or (iii) by the Seller’s failure to perform.”

(*See*: D.04-06-014, Appendix A.)

## STC 8: Product Definitions.

The following new Product Definition shall be added to Schedule P of the EEI Agreement:

**“ “**As Available” means, with respect to a Transaction, that Seller shall deliver to Buyer and Buyer shall purchase at the Delivery Point the Product from the Units, in accordance with the terms of this Agreement and subject to the excuses for performance specified in this Agreement.”

The “Unit Firm” Product Definition in Schedule P of the EEI Agreement shall be deleted in its entirety and replaced with the following:

“ “Unit Firm” means, with respect to a Transaction, that the Product subject to the Transaction is intended to be supplied from a specified generation asset or assets specified in the Transaction. The following Products shall be considered “Unit Firm” products:

“Peaking” means with respect to a Transaction, a Product for which Delivery Periods coincide with Peak Periods, as defined by Buyer.

“Baseload” means with respect to a Transaction, a Product for which Delivery levels are uniform for all Delivery Periods.

“Dispatchable” means with respect to a Transaction, a Product for which Seller makes available unit-contingent capacity for a Buyer to schedule and dispatch up or down at Buyer’s option.”

(*See*: D.04-06-014, Appendix A.)

## STC 9: Non-Performance or Termination Penalties and Default Provisions.

**DEFAULT PROVISIONS**

The following provisions are offered as “Default Provisions” for the Agreement:

Section 5.1 of the EEI Agreement shall be adopted in its entirety and included in the Agreement as follows:

“5.1 Events of Default. An ‘Event of Default’ shall mean, with respect to a Party (a ‘Defaulting Party’), the occurrence of any of the following:

* 1. the failure to make, when due, any payment required pursuant to this Agreement if such failure is not remedied within three (3) Business Days after written notice;
	2. any representation or warranty made by such Party herein is false or misleading in any material respect when made or when deemed made or repeated;
	3. the failure to perform any material covenant or obligation set forth in this Agreement (except to the extent constituting a separate Event of Default, and except for such Party’s obligations to deliver or receive the Product, the exclusive remedy for which is provided in Article Four) if such failure is not remedied within three (3) Business Days after written notice;
	4. such Party becomes Bankrupt;
	5. the failure of such Party to satisfy the creditworthiness/collateral requirements agreed to pursuant to Article Eight hereof;
	6. such Party consolidates or amalgamates with, or merges with or into, or transfers all or substantially all of its assets to, another entity and, at the time of such consolidation, amalgamation, merger or transfer, the resulting, surviving or transferee entity fails to assume all the obligations of such Party under this Agreement to which it or its predecessor was a party by operation of law or pursuant to an agreement reasonably satisfactory to the other Party;
	7. if the applicable cross default section in the Cover Sheet is indicated for such Party, the occurrence and continuation of (i) a default, event of default or other similar condition or event in respect of such Party or any other party specified in the Cover Sheet for such Party under one or more agreements or instruments, individually or collectively, relating to indebtedness for borrowed money in an aggregate amount of not less than the applicable Cross Default Amount (as specified in the Cover Sheet), which results in such indebtedness becoming, or becoming capable at such time of being declared, immediately due and payable or (ii) a default by such Party or any other party specified in the Cover Sheet for such Party in making on the due date therefore one or more payments, individually or collectively, in an aggregate amount of not less than the applicable Cross Default Amount (as specified in the Cover Sheet);
	8. with respect to such Party’s Guarantor, if any:
	9. if any representation or warranty made by a Guarantor in connection with this Agreement is false or misleading in any material respect when made or when deemed made or repeated;
		+ 1. the failure of a Guarantor to make any payment required or to perform any other material covenant or obligation in any guaranty made in connection with this Agreement and such failure shall not be remedied within three (3) Business Days after written notice;
			2. a Guarantor becomes Bankrupt; the failure of a Guarantor’s guaranty to be in full force and effect for purposes of this Agreement (other than in accordance with its terms) prior to the satisfaction of all obligations of such Party under each Transaction to which such guaranty shall relate without the written consent of the other Party; or

(v) a Guarantor shall repudiate, disaffirm, disclaim, or reject, in whole or in part, or challenge the validity of any guaranty.”

Section 5.1 of the Agreement, as provided above, shall be modified as follows:

Section 5.1(c) is amended by deleting the reference to “three (3) Business Days” and replacing it with “thirty (30) days;” and

Sections 5.1(b) and 5.1(h)(i) are amended by adding the following at the end thereof: “or with respect to the representations and warranties made pursuant to Section 10.2 of this Agreement or any additional representations and warranties agreed upon by the parties, any such representation and warranty becomes false or misleading in any material respect during the term of this Agreement or any Transaction entered into hereunder.”

The following new “Events of Default” shall be included in Section 5.1 of the Agreement, as amended:

Section 5.1 (i) is added as follows: “if at any time during the Term of Agreement, Seller delivers or attempts to deliver to the Delivery Point for sale under this Agreement electrical power that was not generated by the Unit(s)”; and

Section 5.1(j) is added as follows: “failure to meet the performance requirements agreed to pursuant to Section hereof.”

**NON- PERFORMANCE/TERMINATION PENALITES:**

The following modifications to Article One of the EEI Agreement are offered as “Non- Performance/Termination Penalties” for the Agreement:

The definition of “Gains” shall be deleted in its entirety and replaced with the following:

“Gains” means with respect to any Party, an amount equal to the present value of the economic benefit to it, if any (exclusive of Costs), resulting from the termination of a Terminated Transaction for the remaining term of such Transaction, determined in a commercially reasonable manner. Factors used in determining economic benefit may include, without limitation, reference to information either available to it internally or supplied by one or more third parties, including, without limitation, quotations (either firm or indicative) of relevant rates, prices, yields, yield curves, volatilities, spreads or other relevant market data in the relevant markets market referent prices for renewable power set by the CPUC, comparable transactions, forward price curves based on economic analysis of the relevant markets, settlement prices for comparable transactions at liquid trading hubs (e.g., NYMEX), all of which should be calculated for the remaining term of the applicable Transaction and include the value of Environmental Attributes.”

The definition of “Losses” shall be deleted in its entirety and replaced with the following:

“Losses” means with respect to any Party, an amount equal to the present value of the economic loss to it, if any (exclusive of Costs), resulting from the termination of a Terminated Transaction for the remaining term of such Transaction, determined in a commercially reasonable manner. Factors used in determining the loss of economic benefit may include, without limitation, reference to information either available to it internally or supplied by one or more third parties including without limitation, quotations (either firm or indicative) of relevant rates, prices, yields, yield curves, volatilities, spreads or other relevant market data in the relevant markets, market referent prices for renewable power set by the CPUC, comparable transactions, forward price curves based on economic analysis of the relevant markets, settlement prices for comparable transactions at liquid trading hubs (e.g. NYMEX), all of which should be calculated for the remaining term of the applicable Transaction and include value of Environmental Attributes.”

The definition of “Costs” shall be deleted in its entirety and replaced with the following:

“Costs” means, with respect to the Non-Defaulting Party, brokerage fees, commissions and other similar third party transaction costs and expenses reasonably incurred by such Party either in terminating any arrangement pursuant to which it has hedged its obligations or entering into new arrangements which replace a Terminated Transaction; and all reasonable attorneys’ fees and expenses incurred by the Non-Defaulting Party in connection with the termination of a Transaction.”

The definition of “Settlement Amount” shall be adopted in its entirety as follows: “1.56 “Settlement Amount” means, with respect to a Transaction and the Non-Defaulting Party, the Losses or Gains, and Costs, expressed in U.S. Dollars, which such party incurs as a result of the liquidation of a Terminated Transaction pursuant to Section 5.2.”

Section 5.2 of the Agreement shall be deleted in its entirety and replaced with the following:

“5.2 Declaration of Early Termination Date and Calculation of Settlement Amounts:

If an Event of Default with respect to a Defaulting Party shall have occurred and be continuing, the other Party (“Non-Defaulting Party”) shall have the right to (i) designate a day, no earlier than the day such notice is effective and no later than 20 days after such notice is effective, as an early termination date (‘Early Termination Date’) to accelerate all amounts owing between the Parties and to liquidate and terminate all, but not less than all, Transactions (each referred to as a ‘Terminated Transaction’) between the Parties, (ii) withhold any payments due to the Defaulting Party under this Agreement and (iii) suspend performance. The Non-defaulting Party shall calculate, in a commercially reasonable manner, a Settlement Amount for each such Terminated Transaction as of the Early Termination Date. Third parties supplying information for purposes of the calculation of Gains or Losses may include, without limitation, dealers in the relevant markets, end-users of the relevant product, information vendors and other sources of market information. The Settlement Amount shall not include consequential, incidental, punitive, exemplary, indirect or business interruption damages. The Non-Defaulting Party shall not have to enter into replacement transactions to establish a Settlement Amount.”

Section 5.3 through 5.5 of the Agreement shall be adopted in their entirety. For reference Section 5.3 – 5.5 are as follows:

“5.3 Net Out of Settlement Amounts. The Non-Defaulting Party shall aggregate all Settlement Amounts into a single amount by: netting out (a) all Settlement Amounts that are due to the Defaulting Party, plus, at the option of the Non-Defaulting Party, any cash or other form of security then available to the Non-Defaulting Party pursuant to Article Eight, plus any or all other amounts due to the Defaulting Party under this Agreement against (b) all Settlement Amounts that are due to the Non-Defaulting Party, plus any or all other amounts due to the Non-Defaulting Party under this Agreement, so that all such amounts shall be netted out to a single liquidated amount (the ‘Termination Payment’). If the Non-Defaulting Party’s aggregate Gains exceed its aggregate Losses and Costs, if any, resulting from the termination of this Agreement, the Termination Payment shall be zero.”

* 1. Notice of Payment of Termination Payment. As soon as practicable after a liquidation, notice shall be given by the Non-Defaulting Party to the Defaulting Party of the amount of the Termination Payment and whether the Termination Payment is due to the Non-Defaulting Party. The notice shall include a written statement explaining in reasonable detail the calculation of such amount and the sources for such calculation. The Termination Payment shall be made to the Non-Defaulting Party, as applicable, within two (2) Business Days after such notice is effective.
	2. Disputes With Respect to Termination Payment. If the Defaulting Party disputes the Non-Defaulting Party’s calculation of the Termination Payment, in whole or in part, the Defaulting Party shall, within five

(5) Business Days of receipt of Non-Defaulting Party’s calculation of the Termination Payment, provide to the Non-Defaulting Party a detailed written explanation of the basis for such dispute; provided, however, that if the Termination Payment is due from the Defaulting Party, the Defaulting Party shall first transfer Performance Assurance to the Non-defaulting Party in an amount equal to the Termination Payment.”

(*See*: D.04-06-014, Appendix A.)

## STC 12: Credit Terms.

Sections 8.1 through 8.3 of the EEI Agreement shall be adopted in their entirety for inclusion in the Agreement as follows:

“8.1 Party A Credit Protection. The applicable credit and collateral requirements shall be as specified on the Cover Sheet and shall only apply if marked as “Applicable” on the Cover Sheet.

* 1. Financial Information. Option A: If requested by Party A, Party B shall deliver (i) within 120 days following the end of each fiscal year, a copy of Party B’s annual report containing audited consolidated financial statements for such fiscal year and (ii) within 60 days after the end of each of its first three fiscal quarters of each fiscal year, a copy of Party B’s quarterly report containing unaudited consolidated financial statements for such fiscal quarter. In all cases the statements shall be for the most recent accounting period and prepared in accordance with generally accepted accounting principles; provided, however, that should any such statements not be available on a timely basis due to a delay in preparation or certification, such delay shall not be an Event of Default so long as Party B diligently pursues the preparation, certification and delivery of the statements.

Option B: If requested by Party A, Party B shall deliver (i) within 120 days following the end of each fiscal year, a copy of the annual report containing audited consolidated financial statements for such fiscal year for the party(s) specified on the Cover Sheet and (ii) within 60 days after the end of each of its first three fiscal quarters of each fiscal year, a copy of quarterly report containing unaudited consolidated financial statements for such fiscal quarter for the party(s) specified on the Cover Sheet. In all cases the statements shall be for the most recent accounting period and shall be prepared in accordance with generally accepted accounting principles; provided, however, that should any such statements not be available on a timely basis due to a delay in preparation or certification, such delay shall not be an Event of Default so long as the relevant entity diligently pursues the preparation, certification and delivery of the statements.

Option C: Party A may request from Party B the information specified in the Cover Sheet.

* 1. Credit Assurances. If Party A has reasonable grounds to believe that Party B’s creditworthiness or performance under this Agreement has become unsatisfactory, Party A will provide Party B with written notice requesting Performance Assurance in an amount determined by Party A in a commercially reasonable manner. Upon receipt of such notice Party B shall have three (3) Business Days to remedy the situation by providing such Performance Assurance to Party A. In the event that Party B fails to provide such Performance Assurance, or a guaranty or other credit assurance acceptable to Party A within three (3) Business Days of receipt of notice, then an Event of Default under Article Five will be deemed to have occurred and Party A will be entitled to the remedies set forth in Article Five of this Master Agreement.
	2. Collateral Threshold. If at any time and from time to time during the term of this Agreement (and notwithstanding whether an Event of Default has occurred), the Termination Payment that would be owed to Party A plus Party B’s Independent Amount, if any, exceeds the Party B Collateral Threshold, then Party A, on any Business Day, may request that Party B provide Performance Assurance in an amount equal to the amount by which the Termination Payment plus Party B’s Independent Amount, if any, exceeds the Party B Collateral Threshold (rounding upwards for any fractional amount to the next Party B Rounding Amount) (“Party B Performance Assurance”), less any Party B Performance Assurance already posted with Party A. Such Party B Performance Assurance shall be delivered to Party A within three (3) Business Days of the date of such request. On any Business Day (but no more frequently than weekly with respect to Letters of Credit and daily with respect to cash), Party B, at its sole cost, may request that such Party B Performance Assurance be reduced correspondingly to the amount of such excess Termination Payment plus Party B’s Independent Amount, if any, (rounding upwards for any fractional amount to the next Party B Rounding Amount). In the event that Party B fails to provide Party B Performance Assurance pursuant to the terms of this Article Eight within three (3) Business Days, then an Event of Default under Article Five shall be deemed to have occurred and Party A will be entitled to the remedies set forth in Article Five of this Master Agreement.

For purposes of this Section 8.1(c), the calculation of the Termination Payment shall be calculated pursuant to Section 5.3 by Party A as if all outstanding Transactions had been liquidated, and in addition thereto, shall include all amounts owed but not yet paid by Party B to Party A, whether or not such amounts are due, for performance already provided pursuant to any and all Transactions.

* 1. Downgrade Event. If at any time there shall occur a Downgrade Event in respect of Party B, then Party A may require Party B to provide Performance Assurance in an amount determined by Party A in a commercially reasonable manner. In the event Party B shall fail to provide such Performance Assurance or a guaranty or other credit assurance acceptable to Party A within three (3) Business Days of receipt of notice, then an Event of Default shall be deemed to have occurred and Party A will be entitled to the remedies set forth in Article Five of this Master Agreement.
	2. If specified on the Cover Sheet, Party B shall deliver to Party A, prior to or concurrently with the execution and delivery of this Master Agreement a guarantee in an amount not less than the Guarantee Amount specified on the Cover Sheet and in a form reasonably acceptable to Party A.
	3. Party B Credit Protection. The applicable credit and collateral requirements shall be as specified on the Cover Sheet and shall only apply if marked as “Applicable” on the Cover Sheet.
1. Financial Information. Option A: If requested by Party B, Party A shall deliver (i) within 120 days following the end of each fiscal year, a copy of Party A’s annual report containing audited consolidated financial statements for such fiscal year and (ii) within 60 days after the end of each of its first three fiscal quarters of each fiscal year, a copy of such Party’s quarterly report containing unaudited consolidated financial statements for such fiscal quarter. In all cases the statements shall be for the most recent accounting period and prepared in accordance with generally accepted accounting principles; provided, however, that should any such statements not be available on a timely basis due to a delay in preparation or certification, such delay shall not be an Event of Default so long as such Party diligently pursues the preparation, certification and delivery of the statements.

Option B: If requested by Party B, Party A shall deliver (i) within 120 days following the end of each fiscal year, a copy of the annual report containing audited consolidated financial statements for such fiscal year for the party(s) specified on the Cover Sheet and (ii) within 60 days after the end of each of its first three fiscal quarters of each fiscal year, a copy of quarterly report containing unaudited consolidated financial statements for such fiscal quarter for the party(s) specified on the Cover Sheet. In all cases the statements shall be for the most recent accounting period and shall be prepared in accordance with generally accepted accounting principles; provided, however, that should any such statements not be available on a timely basis due to a delay in preparation or certification, such delay shall not be an Event of Default so long as the relevant entity diligently pursues the preparation, certification and delivery of the statements.

Option C: Party B may request from Party A the information specified in the Cover Sheet.

1. Credit Assurances. If Party B has reasonable grounds to believe that Party A’s creditworthiness or performance under this Agreement has become unsatisfactory, Party B will provide Party A with written notice requesting Performance Assurance in an amount determined by Party B in a commercially reasonable manner. Upon receipt of such notice Party A shall have three (3) Business Days to remedy the situation by providing such Performance Assurance to Party B. In the event that Party A fails to provide such Performance Assurance, or a guaranty or other credit assurance acceptable to Party B within three (3) Business Days of receipt of notice, then an Event of Default under Article Five will be deemed to have occurred and Party B will be entitled to the remedies set forth in Article Five of this Master Agreement.
2. Collateral Threshold. If at any time and from time to time during the term of this Agreement (and notwithstanding whether an Event of Default has occurred), the Termination Payment that would be owed to Party B plus Party A’s Independent Amount, if any, exceeds the Party A Collateral Threshold, then Party B, on any Business Day, may request that Party A provide Performance Assurance in an amount equal to the amount by which the Termination Payment plus Party A’s Independent Amount, if any, exceeds the Party A Collateral Threshold (rounding upwards for any fractional amount to the next Party A Rounding Amount) (“Party A Performance Assurance”), less any Party A Performance Assurance already posted with Party B. Such Party A Performance Assurance shall be delivered to Party B within three (3) Business Days of the date of such request. On any Business Day (but no more frequently than weekly with respect to Letters of Credit and daily with respect to cash), Party A, at its sole cost, may request that such Party A Performance Assurance be reduced correspondingly to the amount of such excess Termination Payment plus Party A’s Independent Amount, if any, (rounding upwards for any fractional amount to the next Party A Rounding Amount). In the event that Party A fails to provide Party A Performance Assurance pursuant to the terms of this Article Eight within three (3) Business Days, then an Event of Default under Article Five shall be deemed to have occurred and Party B will be entitled to the remedies set forth in Article Five of this Master Agreement.

For purposes of this Section 8.2(c), the calculation of the Termination Payment shall be calculated pursuant to Section 5.3 by Party B as if all outstanding Transactions had been liquidated, and in addition thereto, shall include all amounts owed but not yet paid by Party A to Party B, whether or not such amounts are due, for performance already provided pursuant to any and all Transactions.

1. Downgrade Event. If at any time there shall occur a Downgrade Event in respect of Party A, then Party B may require Party A to provide Performance Assurance in an amount determined by Party B in a commercially reasonable manner. In the event Party A shall fail to provide such Performance Assurance or a guaranty or other credit assurance acceptable to Party B within three (3) Business Days of receipt of notice, then an Event of Default shall be deemed to have occurred and Party B will be entitled to the remedies set forth in Article Five of this Master Agreement.
2. If specified on the Cover Sheet, Party A shall deliver to Party B, prior to or concurrently with the execution and delivery of this Master Agreement a guarantee in an amount not less than the Guarantee Amount specified on the Cover Sheet and in a form reasonably acceptable to Party B.
	1. Grant of Security Interest/Remedies. To secure its obligations under this Agreement and to the extent either or both Parties deliver Performance Assurance hereunder, each Party (a “Pledgor”) hereby grants to the other Party (the “Secured Party”) a present and continuing security interest in, and lien on (and right of setoff against), and assignment of, all cash collateral and cash equivalent collateral and any and all proceeds resulting therefrom or the liquidation thereof, whether now or hereafter held by, on behalf of, or for the benefit of, such Secured Party, and each Party agrees to take such action as the other Party reasonably requires in order to perfect the Secured Party’s first-priority security interest in, and lien on (and right of setoff against), such collateral and any and all proceeds resulting therefrom or from the liquidation thereof. Upon or any time after the occurrence or deemed occurrence and during the continuation of an Event of Default or an Early Termination Date, the Non-Defaulting Party may do any one or more of the following: (i) exercise any of the rights and remedies of a Secured Party with respect to all Performance Assurance, including any such rights and remedies under law then in effect; (ii) exercise its rights of setoff against any and all property of the Defaulting Party in the possession of the Non-Defaulting Party or its agent; (iii) draw on any outstanding Letter of Credit issued for its benefit; and (iv) liquidate all Performance Assurance then held by or for the benefit of the Secured Party free from any claim or right of any nature whatsoever of the Defaulting Party, including any equity or right of purchase or redemption by the Defaulting Party. The Secured Party shall apply the proceeds of the collateral realized upon the exercise of any such rights or remedies to reduce the Pledgor’s obligations under the Agreement (the Pledgor remaining liable for any amounts owing to the Secured Party after such application), subject to the Secured Party’s obligation to return any surplus proceeds remaining after such obligations are satisfied in full.”

If the parties elect as being applicable on the Cover Sheet, the following new Section 8.4 shall be added to Article Eight of the EEI Master Agreement:

To secure its obligations under this Agreement, in addition to satisfying any credit terms pursuant to the terms of Section [8.1 or 8.2] to the extent marked applicable, Seller agrees to deliver to Buyer (the “Secured Party”) within thirty (30) days of the date on which all of the conditions precedent set forth in Section are either satisfied or waived, and Seller shall maintain in full force and effect a) until the Commercial Operation Date a [INSERT TYPE OF COLLATERAL] in the amount of $[ ], the form of which shall be determined in [the sole discretion of] [or] [by] Buyer and (b) from the Commercial Operation Date until the end of the Term [INSERT TYPE OF COLLATERAL]in the amount of $[ ], the form of which shall be determined [in the sole discretion of] [or][by] the Buyer. Any such security shall not be deemed a limitation of damages.”

(*See*: D.04-06-014, Appendix A.)

## STC 15: Contract Modifications.

The following provision of Section 10.8 of the EEI Agreement shall be adopted as follows:

“Except to the extent herein provided for, no amendment or modification to this Agreement shall be enforceable unless reduced to writing and executed by both parties.”

(*See*: D.04-06-014, Appendix A.)

## STC 16: Assignment.

“Assignment. Neither Party shall assign this Agreement or its rights hereunder without the prior written consent of the other Party, which consent shall not be unreasonably withheld; provided, however, either Party may, without the consent of the other Party (and without relieving itself from liability hereunder), transfer, sell, pledge, encumber or assign this Agreement or the accounts, revenues or proceeds hereof to its financing providers and the financing provider(s) shall assume the payment and performance obligations provided under this Agreement with respect to the transferring Party provided, however, that in each such case, any such assignee shall agree in writing to be bound by the terms and conditions hereof and so long as the transferring Party delivers such tax and enforceability assurance as the non-transferring Party may reasonably request.”

(*See*: D.04-06-014, Appendix A; D.08-04-009, Appendix A at 30).

## STC 18: Application of Prevailing Wage.

To the extent applicable, Seller shall comply with the prevailing wage requirements of Public Utilities Code section 399.14, subdivision (h).

(*See*: D.04-06-014, Appendix A.)

**EXHIBIT A**

**DESCRIPTION OF THE FACILITY**

**Facility Name:**

**Site Name:**

**Site Description:** **[*Insert assessor parcel numbers upon which Site is located.*]**

**Site Address:**

**GPS Coordinates:**

**Site Map: [*Insert map of Site*]**

**APNs:**

**County: [\_\_\_\_\_\_\_\_\_\_]** County

**CEQA Lead Agency:**

**Generation Technology:** **[*For solar, include manufacturer, type, model, and number of inverters and modules, and type of panel orientation (e.g., fixed-mount, tilt-angle, azimuth, single-axis tracker). For wind, include turbine manufacturer, type, model and number*.]**

**P-node/Delivery Point:** the PNode designated by the CAISO for the Facility at the **[\_\_\_\_\_\_\_\_\_\_\_\_]** Substation

**Point of Interconnection:**

**Description of Interconnection Facilities and Metering:** The Facility will use the following Interconnection Facilities and metering configuration, as depicted in the attached one-line diagram: **[*Insert description of metering, Interconnection Facilities, and other control equipment.*]**

**CAISO Queue Number:**

**One-Line Diagram:** **[*Insert one-line diagram showing electrical configuration of generation equipment, control equipment, and Interconnection Facilities.*]**

**Metering Diagram:**

**Additional Information:**

**EXHIBIT B**

**FACILITY CONSTRUCTION AND COMMERCIAL OPERATION**

1. **Construction of the Facility**.
	1. Seller shall cause construction to begin on the Facility by **[\_\_\_\_\_\_\_\_\_\_\_\_\_]**, (as such date may be extended by the Development Cure Period, the “**Guaranteed Construction Start Date**”). Seller shall demonstrate the beginning of construction through execution of Seller’s engineering, procurement and construction contract, Seller’s issuance of a notice to proceed under such contract, mobilization to site by Seller and/or its designees, and includes the physical movement of soil at the Site (“**Construction Start**”). On the date of the beginning of construction (the “**Construction Start Date**”), Seller shall deliver to Buyer a certificate substantially in the form attached as Exhibit H hereto.
	2. If Construction Start is not achieved by the Guaranteed Construction Start Date, Seller shall pay Daily Delay Damages to Buyer on account of such delay. Daily Delay Damages shall be payable for each day for which Construction Start has not begun by the Guaranteed Construction Start Date. Daily Delay Damages shall be payable to Buyer by Seller until the earlier of one hundred twenty (120) days after the Guaranteed Construction Start Date, or the date on which Seller reaches Construction Start of the Facility. On or before the tenth (10th) day of each month, Buyer shall invoice Seller for Daily Delay Damages, if any, accrued during the prior month and, within ten (10) Business Days following Seller’s receipt of such invoice, Seller shall pay Buyer the amount of the Daily Delay Damages set forth in such invoice. Daily Delay Damages shall be refundable to Seller pursuant to Section 3(b) of this Exhibit B. The Parties agree that Buyer’s receipt of Daily Delay Damages shall be Buyer’s sole and exclusive remedy for the first one hundred twenty (120) days of the delay in achieving the Construction Start Date on or before the Guaranteed Construction Start Date, but shall (x) not be construed as Buyer’s declaration that an Event of Default has occurred under any provision of Section 11.1 and (y) not limit Buyer’s right to declare an Event of Default pursuant to Section 11.1(b)(ii) and receive a Termination Payment or Damage Payment, as applicable, upon exercise of Buyer’s rights pursuant to Section 11.2.
2. **Commercial Operation of the Facility**. “**Commercial Operation**” means the condition existing when (i) Seller has fulfilled all of the conditions precedent in Section 2.2 of the Agreement and (ii) Seller has provided Notice to Buyer that Commercial Operation has been achieved. The “**Commercial Operation Date**” shall be the later of (x) **[\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_]** or (y) the date on which Commercial Operation is achieved.
	1. Seller shall cause Commercial Operation for the Facility to occur by **[\_\_\_\_\_\_\_\_\_]** (as such date may be extended by the Development Cure Period (defined below), the “**Guaranteed Commercial Operation Date**”). Seller shall notify Buyer that it intends to achieve Commercial Operation at least sixty (60) days before the anticipated Commercial Operation Date.
	2. If Seller achieves Commercial Operation by the Guaranteed Commercial Operation Date, all Daily Delay Damages paid by Seller shall be refunded to Seller. Seller shall include the request for refund of the Daily Delay Damages with the first invoice to Buyer after the Commercial Operation Date.
	3. If Seller does not achieve Commercial Operation by the Guaranteed Commercial Operation Date, Buyer shall retain Daily Delay Damages, as applicable, and Seller shall pay Commercial Operation Delay Damages to Buyer for each day after the Guaranteed Commercial Operation Date until the Commercial Operation Date. Commercial Operation Delay Damages shall be payable to Buyer by Seller until the Commercial Operation Date. On or before the tenth (10th) day of each month, Buyer shall invoice Seller for Commercial Operation Delay Damages, if any, accrued during the prior month. The Parties agree that Buyer’s retention of Daily Delay Damages and receipt of Commercial Operation Delay Damages shall be Buyer’s sole and exclusive remedy for the first ninety (90) days of delay in achieving the Commercial Operation Date on or before the Guaranteed Commercial Operation Date, but shall (x) not be construed as Buyer’s declaration that an Event of Default has occurred under any provision of Section 11.1 and (y) not limit Buyer’s right to declare an Event of Default under Section 11.1(b)(ii) and receive a Damage Payment upon exercise of Buyer’s default right pursuant to Section 11.2.
3. **Termination for Failure to Timely Achieve Construction Start or Commercial Operation**. If the Facility has not achieved Construction Start within one hundred twenty (120) days after the Guaranteed Construction Start Date, or Commercial Operation withinninety (90) days after the Guaranteed Commercial Operation Date, Buyer may elect to terminate this Agreement pursuant to Sections 11.1(b)(ii) and 11.2(a), which termination shall become effective as provided in Section 11.2(a).
4. **Extension of the Guaranteed Dates**. The Guaranteed Construction Start Date and the Guaranteed Commercial Operation Date shall be extended on a day-for-day basis (the “**Development Cure Period**”) for the duration of each of the following delays:
	1. a Force Majeure Event occurs; or
	2. Buyer has not made all necessary arrangements to receive the Energy at the Delivery Point by the Guaranteed Commercial Operation Date.

Notwithstanding anything in this Agreement to the contrary, the cumulative extensions granted under the Development Cure Period (other than the extensions granted pursuant to clause 4(b) above) shall not exceed one hundred eighty (180) days, for any reason, and, without limiting the provisions of Section 10.3, no extension shall be given to the extent that (i) the delay was the result of Seller’s failure to take all commercially reasonable actions to meet its requirements and deadlines; (ii) Seller failed to provide prompt written notice to Buyer of a delay due to a Force Majeure Event, but in no case more than thirty (30) days after Seller became aware of an actual delay (not including Seller’s receipt of generic notices of potential delays due to a Force Majeure Event) affecting the Facility, except that in the case of a delay occurring within sixty (60) days of the Guaranteed Delivery Commencement Date, or after such date, Seller must provide written notice within seven (7) Business Days of Seller becoming aware of such delay; or (iii) Seller failed, upon written request from Buyer, to provide documentation demonstrating to Buyer’s reasonable satisfaction that the delay was a result of a Force Majeure Event and did not result from Seller’s actions or failure to take commercially reasonable actions.

1. **Failure to Reach Guaranteed Capacity**. If, at Commercial Operation, the Installed Capacity is at least ninety-five percent (95%) of Guaranteed Capacity, but less than the Guaranteed Capacity, Seller shall have ninety (90) days after the Commercial Operation Date to install additional capacity such that the Installed Capacity is increased, but not to exceed the Guaranteed Capacity, and Seller shall provide to Buyer a new certificate substantially in the form attached as Exhibit G-2 hereto specifying the new Installed Capacity. In the event that the Installed Capacity is still less than the Guaranteed Capacity as of such date, Seller shall pay “**Capacity Damages**” to Buyer, in an amount equal to Two Hundred Fifty Thousand Dollars ($250,000) for each MW that the Guaranteed Capacity exceeds the Installed Capacity, and the Guaranteed Capacity and other applicable portions of the Agreement shall be reduced to an amount equal to the product of (a) the amount in effect prior to such adjustment, multiplied by (b) the ratio of the Installed Capacity as of such date to the original Guaranteed Capacity.
2. **Buyer’s Right to Draw on Development Security**. If Seller fails to timely pay any Daily Delay Damages or Commercial Operation Delay Damages, Buyer may draw upon the Development Security to satisfy Seller’s payment obligation thereof, and Seller shall replenish the Development Security to its full amount within five (5) Business Days after such draw.

**EXHIBIT C**

**[Intentionally Omitted]**

**EXHIBIT D**

**GUARANTEED ENERGY PRODUCTION DAMAGES CALCULATION**

In accordance with Section 4.7, if Seller fails to achieve the Guaranteed Energy Production during any Performance Measurement Period, a liquidated damages payment shall be due from Seller to Buyer, calculated as follows:

[(A – B) \* (C – D)]

where:

A = the Guaranteed Energy Production amount for the Performance Measurement Period, in MWh

B = the Adjusted Energy Production amount for the Performance Measurement Period, in MWh

C = Replacement price for the Performance Measurement Period, in $/MWh, which is the sum of (a) the simple average of the Integrated Forward Market hourly price for all the hours in the Performance Measurement Period, as published by the CAISO, for the Existing Zone Generation Trading Hub (as defined in the CAISO Tariff) for the Delivery Point,plus (b) $50/MWh.

D = the average Contract Price for the Performance Measurement Period, in $/MWh

No payment shall be due if the calculation of (A - B) or (C - D) yields a negative number.

Within sixty (60) days after each Performance Measurement Period, Buyer will send Seller Notice of the amount of damages owing, if any, which shall be payable to Buyer before the later of (a) thirty (30) days of such Notice and (b) ninety (90) days after each Performance Measurement Period.

**Additional Definitions:**

“**Adjusted Energy Production**” shall mean the sum of the following: Metered Energy + Deemed Delivered Energy + Lost Output – Excess MWh.

“**Lost Output**” means the sum of Energy in MWh that would have been generated and delivered, but was not, on account of Force Majeure Event, Buyer Default, or Curtailment Order. The additional MWh shall be calculated using an equation provided by Seller, as approved by Buyer in its reasonable discretion, to reflect the potential generation of the Facility as a function of Available Capacity, [***solar insolation and panel temperature***,] [***and wind speed*,**] and using relevant Facility availability, weather, historical and other pertinent data for the period of time during the period in which the Force Majeure Event, Buyer Default, or Curtailment Order occurred.

**EXHIBIT E**

**PROGRESS REPORTING FORM**

Within fifteen (15) days after the close of (i) each calendar quarter from the first calendar quarter following the Effective Date until the Construction Start Date, and (ii) each calendar month from the first calendar month following the Construction Start Date until the Commercial Operation Date, Seller shall provide to Buyer a written Progress Report in the form specified below.

Each Progress Report must include the following items:

Executive summary.

Facility description.

Site plan of the Facility.

Description of any planned changes to the Facility or the Site.

Gantt chart schedule showing progress on achieving each of the Milestones.

Summary of activities during the previous calendar quarter or month, as applicable, including any OSHA labor hour reports.

Forecast of activities scheduled for the current calendar quarter.

Written description about the progress relative to Seller’s Milestones, including whether Seller has met or is on target to meet the Milestones.

List of issues that could potentially affect Seller’s Milestones.

A status report of start-up activities including a forecast of activities ongoing and after start-up, a report on Facility performance including performance projections for the next twelve (12) months.

Progress and schedule of all agreements, contracts, permits, approvals, technical studies, financing agreements and major equipment purchase orders showing the start dates, completion dates, and completion percentages.

Pictures, in sufficient quantity and of appropriate detail, in order to document construction and startup progress of the Facility, the interconnection into the Transmission System and all other interconnection utility services.

Workforce Development or Supplier Diversity Reporting (if applicable). Format to be provided by Buyer.

Any other documentation reasonably requested by Buyer.

**EXHIBIT F**

**BUYOUT OPTION**

(1) Buyout Option. No later than ninety (90) days prior to the last day of each of (i) the tenth (10th) Contract Year of the Contract Term, (ii) the fifteenth (15th) Contract Year of the Contract Term and (iii) the twentieth (20th) Contract Year of the Contract Term, Buyer may deliver Notice to Seller indicating whether it elects to purchase the Facility. If Buyer elects to make a purchase, Buyer shall pay to Seller a “**Buyout Payment**” within thirty (30) days prior to the last day of such Contract Year equal to the Fair Market Value of the Facility as of such date, as determined pursuant to clause (2) below.

(2) Calculation of Fair Market Value. If Buyer provides Notice to Seller that it is contemplating exercising its rights under this Exhibit G, the Parties shall mutually agree upon an independent appraiser on or before the date that is sixty (60) days prior to the last day of (i) the tenth (10th) Contract Year of the Contract Term, (ii) the fifteenth (15th) Contract Year of the Contract Term, or (iii) the twentieth (20th) Contract Year of the Contract Term, if applicable. Such appraiser shall determine, at equally shared expense of Buyer and Seller, the fair market value of the Facility as of the date on which the Buyout Payment is to be paid, taking into account such items as deemed appropriate by the appraiser, which may include the resale value of the Facility, and the price of the Product (the “**Fair Market Value**”). In the event that Buyer and Seller cannot agree upon a single independent appraiser, each Party shall contract for an independent appraiser at its own expense, and the Fair Market Value shall be the simple average of the determinations of the two independent appraisers. On or prior to the date that is thirty (30) days prior to the last day of such Contract Year, the appraiser shall deliver its determination of Fair Market Value to each of Buyer and Seller. After the appraiser provides the Parties with its appraisal of Fair Market Value of the Facility, Buyer shall have thirty (30) days to decide whether to consummate its option to purchase the Facility. If Buyer does not provide Notice to Seller that Buyer intends to exercise its option to purchase the Facility within thirty (30) days of receipt of the Fair Market Value appraisal, Buyer shall be deemed to have not exercised its option to purchase the Facility.

(3) Passage of Title. Upon receipt of the Buyout Payment, the Parties shall execute all documents necessary to cause title to the Facility to pass to Buyer on an as-is, where-is, with-all-faults basis; *provided*, *however*, that Seller shall remove any encumbrances held by Seller with respect to the Facility.

**EXHIBIT G-1**

**FORM OF COMMERCIAL OPERATION date certifIcate**

This certification (“**Certification**”) of Commercial Operation is delivered by \_\_\_\_\_\_\_[*Licensed Professional Engineer*] (“**Engineer**”) to Peninsula Clean Energy Authority **(**“**Buyer**”) in accordance with the terms of that certain Power Purchase and Sale Agreement dated \_\_\_\_\_\_\_ (“**Agreement**”) by and between [*Seller*] and Buyer. All capitalized terms used in this Certification but not otherwise defined herein shall have the respective meanings assigned to such terms in the Agreement.

Engineer hereby certifies and represents to Buyer the following:

(1) Seller has installed equipment with a nameplate capacity of no less than ninety-five percent (95%) of the Guaranteed Capacity.

(2) The Facility’s testing included a performance test demonstrating peak electrical output of no less than ninety-five percent (95%) of the Guaranteed Capacity at the Delivery Point, as adjusted for ambient conditions on the date of the Facility testing, and such peak electrical output, as adjusted, was [peak output in MW].

(3) Authorization to parallel the Facility was obtained by the Participating Transmission Owner, [Name of Participating Transmission Owner as appropriate] on\_\_\_[DATE]\_\_\_\_

(4) The Participating Transmission Owner or Distribution Provider has provided documentation supporting full unrestricted release for Commercial Operation by [Name of Participating Transmission Owner as appropriate] on \_\_\_\_\_\_\_[DATE]\_\_\_\_\_.

(5) The CAISO has provided notification supporting the Facility’s Commercial Operation, inclusion in the Full Network Model and authorization to provide Ancillary Services, all in accordance with the CAISO tariff on \_\_\_\_\_\_\_[DATE]\_\_\_\_\_.

EXECUTED by **[**licensed professional engineer**]**

this \_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_\_, 20\_\_.

**[**licensed professional engineer**]**

By:

Its:

Date:

**EXHIBIT G-2**

**FORM OF installed Capacity certifIcate**

This certification (“**Certification**”) of Installed Capacity is delivered by [Licensed Professional Engineer] (“**Engineer**”) to PENINSULA CLEAN ENERGY AUTHORITY (“**Buyer**”) in accordance with the terms of that certain Power Purchase and Sale Agreement dated \_\_\_\_\_\_\_\_\_\_ (“**Agreement**”) by and between [*SELLER ENTITY*] and Buyer. All capitalized terms used in this Certification but not otherwise defined herein shall have the respective meanings assigned to such terms in the Agreement.

The initial Facility performance test under Seller’s EPC contract for the Facility demonstrated peak Facility electrical output of \_\_MW AC at the Delivery Point, as adjusted for ambient conditions on the date of the performance test (“**Installed Capacity**”).

EXECUTED by **[**licensed professional engineer**]**

this \_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_\_, 20\_\_.

**[**licensed professional engineer**]**

By:

Its:

Date:

**EXHIBIT H**

**FORM OF CONSTRUCTION START date certifIcate**

This certification (“**Certification**”) of the Construction Start Date is delivered by [SELLER ENTITY] (“**Seller**”) to PENINSULA CLEAN ENERGY AUTHORITY (“**Buyer**”) in accordance with the terms of that certain Power Purchase and Sale Agreement dated \_\_\_\_\_\_\_\_\_\_ (“**Agreement**”) by and between Seller and Buyer. All capitalized terms used in this Certification but not otherwise defined herein shall have the respective meanings assigned to such terms in the Agreement.

Seller hereby certifies and represents to Buyer the following:

1. the engineering, procurement and construction contract related to the Facility was executed on \_\_\_\_\_\_\_\_\_\_;
2. the limited notice to proceed with the construction of the Facility was issued on \_\_\_\_\_\_\_\_\_\_\_\_\_\_ (attached);
3. the Construction Start Date has occurred;
4. the precise Site on which the Facility is located is, which must be within the boundaries of the previously identified Site: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (such description shall amend the description of the Site in Exhibit A).

IN WITNESS WHEREOF, the undersigned has executed this Certification on behalf of Seller as of the \_\_\_ day of \_\_\_\_\_\_\_\_.

[SELLER ENTITY]

By:

Its:

Date:

**EXHIBIT I**

**FORM OF LETTER OF CREDIT**

*[Issuing Bank Letterhead and Address]*

IRREVOCABLE STANDBY LETTER OF CREDIT NO. [XXXXXXX]

 Date:

 Bank Ref.:

 Amount: US$**[XXXXXXX]**

 Expiry Date:

Beneficiary:

Peninsula Clean Energy Authority

**[Address]**

Ladies and Gentlemen:

On behalf of **[XXXXXXX]** (“Applicant”), we, **[insert bank name and address]** (“Issuer”) hereby issue our Irrevocable Standby Letter of Credit No. **[XXXXXXX]** (the “Letter of Credit”) in favor of Peninsula Clean Energy Authority, Address\_\_\_\_\_\_\_\_\_\_, for an amount not to exceed the aggregate sum of U.S. $**[XXXXXXX**] (United States Dollars **[XXXXXXX]** and 00/100), pursuant to that certain **[Agreement]** dated as of \_\_\_\_\_\_\_\_\_\_\_\_ (the “Agreement”) between Applicant and Beneficiary. This Letter of Credit shall become effective immediately and shall have an initial expiry date of \_\_\_\_\_\_\_\_\_\_ \_\_, 201\_ subject to the automatic extension provisions herein.

Funds under this Letter of Credit are available to you against your draft(s) drawn on us at sight, mentioning thereon our Letter of Credit No. **[XXXXXXX]** accompanied by your dated statement purportedly signed by your duly authorized representative, in the form attached hereto as Exhibit A, containing one of the two alternative paragraphs set forth in paragraph 2 therein.

We hereby agree with the Beneficiary that all drafts drawn under and in compliance with the terms of this Letter of Credit will be duly honored upon presentation to the Issuer in person, by courier or by fax at **[insert bank address]**. Payment shall be made by Issuer in U.S. dollars with Issuer’s own immediately available funds.

The document(s) required may also be presented by fax at facsimile no. (xxx) xxx-xxx on or before the expiry date (as may be extended below) on this Letter of Credit in accordance with the terms and conditions of this Letter of Credit. No mail confirmation is necessary and the facsimile transmission will constitute the operative drawing documents without the need of originally signed documents.

Partial draws are permitted under this Letter of Credit.

It is a condition of this Letter of Credit that it shall be deemed automatically extended without an amendment for a one year period beginning on the present expiry date hereof and upon each anniversary for such date, unless at least ninety (90) days prior to any such expiry date we have sent to you written notice by overnight courier service that we elect not to permit this Letter of Credit to be so extended, in which case it will expire on its then current expiry date. No presentation made under this Letter of Credit after such expiry date will be honored.

Notwithstanding any reference in this Letter of Credit to any other documents, instruments or agreements, this Letter of Credit contains the entire agreement between Beneficiary and Issuer relating to the obligations of Issuer hereunder.

This Letter of Credit is subject to the Uniform Customs and Practice for Documentary Credits (2007 Revision) International Chamber of Commerce Publication No. 600 (the “UCP”), except to the extent that the terms hereof are inconsistent with the provisions of the UCP, including but not limited to 36 of the UCP, in which case the terms of this Letter of Credit shall govern. In the event of an act of God, riot, civil commotion, insurrection, war or any other cause beyond Issuer’s control (as defined in Article 36 of the UCP) that interrupts Issuer’s business and causes the place for presentation of the Letter of Credit to be closed for business on the last day for presentation, the expiry date of the Letter of Credit will be automatically extended without amendment to a date thirty (30) calendar days after the place for presentation reopens for business.

Please address all correspondence regarding this Letter of Credit to the attention of the Letter of Credit Department at **[insert bank address information]**, referring specifically to Issuer’s Letter of Credit No. **[XXXXXXX]**. For telephone assistance, please contact Issuer’s Standby Letter of Credit Department at **[XXX-XXX-XXXX]** and have this Letter of Credit available.

**[Bank Name]**

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**[Insert officer name]**

**[Insert officer title]**

**DRAW REQUEST SHOULD BE ON BENEFICIARY’S LETTERHEAD)**

Drawing Certificate

**[Insert Bank Name and Address]**

Ladies and Gentlemen:

The undersigned, a duly authorized representative of Peninsula Clean Energy Authority, Address\_\_\_\_\_\_\_\_\_\_\_ as beneficiary (the “Beneficiary”) of the Irrevocable Letter of Credit No. **[XXXXXXX]** (the “Letter of Credit”) issued by **[insert bank name]** (the “Bank”) by order of **[XXXXXXX]** (the “Applicant”), hereby certifies to the Bank as follows:

1. Applicant and Beneficiary are party to that certain Agreement dated as of **[XXXXXXX]** (the “Agreement”).
2. Beneficiary is making a drawing under this Letter of Credit in the amount of U.S. $\_\_\_\_\_\_\_\_\_\_\_.

or

Beneficiary is making a drawing under this Letter of Credit in the amount of U.S. $\_\_\_\_\_\_\_\_\_\_\_, which equals the full available amount under the Letter of Credit, because the Bank has provided notice of its intent to not extend the expiry date of the Letter of Credit and Applicant failed to provide acceptable replacement security to Beneficiary at least thirty (30) days prior to the expiry date of the Letter of Credit.

1. The undersigned is a duly authorized representative of Peninsula Clean Energy and is authorized to execute and deliver this Drawing Certificate on behalf of Beneficiary.

You are hereby directed to make payment of the requested amount to Peninsula Clean Energy Authority by wire transfer in immediately available funds to the following account:

[Specify account information]

Peninsula Clean Energy Authority

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name and Title of Authorized Representative

Date\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**EXHIBIT J**

**INSURANCE**

**Liability Insurance**

To the fullest extent allowable by law, Seller shall purchase and maintain such insurance as will protect it from the claims set forth below which may arise out of or result from Seller’s operations under this Agreement whether such operations be by itself or by anyone directly or indirectly employed by them, or by anyone for whose acts any of them may be liable. Limits shall be all the Insurance Coverage and/or limits carried by or available to the Seller, the minimum limits as required herein.

**General Conditions**

Seller shall maintain completed operations liability insurance for the entire Contract Term plus the period of time Seller may be held legally liable for.

Seller shall maintain policies of insurance in full force and effect, at all times during the performance of the Agreement, plus any statute of repose or statute of limitations applicable to the jurisdiction where any work is performed.

All insurance companies shall have a Best’s rating of A-VII or better.

In addition, Seller shall provide Buyer with 45 days’ notice in case of cancellation or non- renewal, except 10 days for non-payment of premium.

Certificates of Insurance Acord Form 25 and all required Endorsements shall be filed with Buyer within (5) working days of execution of the contract and/or prior to commencement of any work performed.

If requested by the Buyer, Seller shall provide a certified and true copy of any or all policies.

Acceptance of the certificates or endorsements by the Buyer shall not constitute a waiver of Seller’s obligations hereunder.

If Seller fails to secure and/or pay the premiums for any of the policies of insurance required herein, or fails to maintain such insurance, Buyer may, in addition to any other rights it may have under this Agreement or at law or in equity, terminate this Agreement or secure such policies or policies of insurance for the account of Seller and charge Seller for the premiums paid therefore, or withhold the amount thereof from sums otherwise due from Buyer to Seller. Neither the Buyer’s rights to secure such policy or policies nor the securing thereof by Buyer shall constitute an undertaking by Buyer on behalf of or for the benefit of Seller or others to determine or warrant that such policies are in effect.

Seller shall be fully and financially responsible for all deductibles or self-insured retentions.

**Coverage Forms & Limits**

 **Seller’s Commercial General Liability** insurance shall be written on an industry standard Commercial General Liability Occurrence from (CG 00 01, 12/07) or its equivalent and shall include but not be limited to products/completed operations; premises and operations; blanket contractual; advertising/personal injury; independent Buyers.

Coverage shall be on an occurrence form with policy limits of not less than:

* $1,000,000 Each Occurrence Bodily Injury & Property Damage
* $1,000,000 Personal & Advertising Injury
* $2,000,000 General Aggregate to apply on a Per Project basis
* $2,000,000 Products/Completed Operations Aggregate

**Business Auto Liability** – Coverage shall be no less than that provided by Insurance Services Office, Inc. (ISO) form CA 00 01, written on an occurrence basis to apply to “any auto” or at a minimum “all owned, hired and non-owned autos”, with policy limits of not less than $1,000,000 per accident for bodily injury and property damage.

If applicable, Broadened Pollution for Covered Autos shall apply. This requirement may also be satisfied by providing proof of separate Pollution Liability that includes coverage for transportation exposures.

**Workers’ Compensation and (b) employers’ liability** – Sellers shall provide coverage for industrial injury to their employees (or leased employees as applicable) in strict accordance with the provisions of the State or States in which project work is performed or where jurisdiction is deemed to be applicable. Workers’ Compensation shall be provided in a statutory form on either a state or, where applicable, federal (U.S. Longshore & Harbor Workers Act, Maritime- Jones Act, etc.) basis as required in the applicable jurisdiction.

Such insurance shall be in an amount of not less than:

* Workers Compensation: Statutory
* Employers Liability
	+ $1,000,000 Bodily Injury by Accident – Each Accident
	+ $1,000,000 Bodily Injury by Disease – Total Limit
	+ $1,000,000 Bodily Injury by Disease – Each Employee

**Commercial Umbrella or Excess Liability Insurance** over Seller’s primary Commercial General Liability, Business Auto Liability and Employers Liability. All coverage terms required under the Commercial General Liability, Business Auto Liability and Employers Liability above must be included on the Umbrella or Excess Liability Insurance.

Coverage shall be written on an occurrence form with policy limits not less than:

* $5,000,000 Each Occurrence
* $5,000,000 Personal & Advertising Injury
* $5,000,000 Aggregate (where applicable, following the terms of the underlying)

**Pollution liability** – Seller shall provide evidence prior to the Construction Start Date of Pollution Liability; covering all operations necessary or incidental to the fulfillment of all contract obligations hereunder. Such insurance shall provide coverage for bodily injury, property damage (including loss of use of damaged property or of property that has not been physically injured), clean- up costs and remediation expenses (including costs for investigation, sampling, characterization, and monitoring), legal costs, defense costs, natural resource damage, transportation of pollutants on and off the project site, and non-owned disposal site liability if Seller’s scope of work (or Seller’s consultants) includes the responsibility of manifesting and disposing of contaminated material or waste from its activities. Coverage shall also extend to pollution conditions arising out of the Seller’s operations including coverage for sudden as well as gradual release arising from Seller’s operations including operations of any of its Seller’s or consultants. Such insurance shall provide coverage for wrongful acts, which may arise from all activities from the first point of Seller engagement and shall continue on a practice basis for not less than 36 months after completion, or the period of time Seller may be held legally liable for its work, whichever is longer. The retro date if any such coverage shall be prior to the commencement of Seller’s work.

Such insurance shall be in an amount of not less than $5,000,000 per claim or occurrence and $5,000,000 annual aggregate.

If Seller maintains Pollution Liability limits greater than what is required herein, such limits carried become what we require under this contract.

**Professional Liability and/or Errors & Omissions –** Seller shall provide evidence of Professional Liability insurance covering claims that arise from the actual or alleged errors, omissions or acts of the Seller or any entity for which the Seller is legally responsible, for the provision of all professional services necessary or incidental to the fulfillment of all contract obligations hereunder.

Such insurance shall be in an amount of not less than $2,000,000 each claim / $4,000,000 aggregate.

If Seller maintains Professional Liability limits greater than what is required herein, such limits carried become what we require under this Agreement.

The policy shall be effective from the date of commencement of all professional services in connection with the fulfillment of all contract obligations hereunder. The retroactive date in the current and future policies shall be prior to the commencement of all professional services. Coverage shall be maintained for a period not less than 36 months or the period of time Seller may be held legally liable for its work, (whichever is longer) following the completion of the work; or an extended reporting period of 36 months following completion of the work shall be purchased.

Coverages shall not include any exclusion or other limitations related to scopes of services or project type or construction type, or delays in project completion and cost overruns.

**Additional Insured / Primary-Noncontributory / Waiver of Subrogation Requirements** To the fullest extent of coverage allowed under applicable law, Buyer shall be named as additional insured on a primary and non-contributory basis for all required lines of coverage except Statutory Workers Compensation and Professional Liability, arising out of all operations performed by or for the Seller under this Agreement. Buyer shall accept General Liability Additional Insured forms CG 20 10 11/85, CG 20 10 10/01 & CG 20 37 10/01 or their equivalent.

Additional Insured status shall be for all limits carried, not limited to the minimum acceptable as required herein. Seller’s insurance shall be Primary as respects to Buyer and Owner, and any other insurance maintained by Buyer and Owner shall be excess and not contributing insurance with Seller’s insurance until such time as all limits available under the Seller’s insurance policies have been exhausted.

Additional Insured endorsements that contain comparative fault, vicarious liability or sole negligence limitations of the Buyer / Owner or any other party required by the contract, will not be accepted.

In the event that any policy provided in compliance with this Agreement states that the coverage provided to an additional insured shall be no broader than that required by contract, or words of similar meaning, the Parties agree that nothing in this Agreement is intended to restrict or limit the breadth of coverage or limits available.

The additional insured status shall remain in full force and effect for the Contract Term plus the applicable statute of repose, or the amount of time you are legally liable, whichever is longer.

It is further agreed that the additional insured coverage required under this Agreement shall not be subject to any Defense Costs Endorsements such as Form IL 01 23 11 13, allowing for the recovery of defense costs by the insurer if the insurer initially pays defense costs but later determines the claims are not covered.

Buyer reserves the right, in its sole and subjective discretion, to reject any Additional Insured forms that are deemed not equivalent to what is required herein.

**Waiver of Subrogation** – Seller shall provide a Waiver of Subrogation Endorsement naming Buyer for all lines of coverage.

**Additional Requirements**

**Property Insurance**

Seller shall procure and maintain, at the Seller’s own expense, Builder’s Risk, property and equipment insurance, including for any property stored off the Site, in transit or any of the Buyer’s property in the care, custody or control of Seller. Seller and Seller’s insurance carrier(s) hereby waive all rights of subrogation against Buyer for damage including loss of use.

Buyer neither represents nor assumes responsibility for the adequacy of the Builders Risk Insurance to protect the interests of the Seller. It shall be the obligation of the Seller to purchase and maintain any supplementary property insurance that it deems necessary to protect its interest in the Work, including without limitation off site stored materials and materials in transit.

Seller is solely responsible for loss or damage to its personal property.

**EXHIBIT K**

**FORM OF REPLACEMENT RA NOTICE**

This Replacement RA Notice (this “**Notice**”) is delivered by [ ], a [ ] (“**Seller**”) to Peninsula Clean Energy Authority, a California joint powers authority (“**Buyer**”) in accordance with the terms of that certain Power Purchase and Sale Agreement dated [\_\_\_\_\_\_\_\_\_\_] (“**Agreement**”) by and between Seller and Buyer. All capitalized terms used in this Notice but not otherwise defined herein shall have the respective meanings assigned to such terms in the Agreement.

Pursuant to Section 3.9(b) of the Agreement, Seller hereby provides the below Replacement RA product information (to be repeated for each unit if more than one):

|  |  |
| --- | --- |
| Name |  |
| Location |  |
| CAISO Resource ID |  |
| Unit SCID |  |
| Resource Type |  |
| Point of Interconnection with the CAISO Controlled Grid (“substation or transmission line”) |  |
| Path 26 (North or South) |  |
| LCR Area (if any) |  |
| Deliverability restrictions, if any, as described in most recent CAISO deliverability assessment |  |
| Run Hour Restrictions |  |
| Deliverability Period |  |
| Prorated Percentage of Unit Factor |  |
| Prorated Percentage of Unit Flexible Factor |  |
| Resource Category (MCC Bucket e.g., 1, 2, 3, or 4) |  |
| Flexible Capacity Category (e.g., 1, 2, 3, or N/A) |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Month** | **Unit CAISO NQC (MW)** | **Unit CAISO EFC (MW)** | **Unit Contract Quantity (MW)** | **Unit EFC Contract Quantity (MW)** |
| January |  |  |  |  |
| February |  |  |  |  |
| March |  |  |  |  |
| April |  |  |  |  |
| May |  |  |  |  |
| June |  |  |  |  |
| July |  |  |  |  |
| August |  |  |  |  |
| September |  |  |  |  |
| October |  |  |  |  |
| November |  |  |  |  |
| December |  |  |  |  |

[SELLER]

By:

Its:

Date:

Whereas, the following definitions apply to the terms in the above Replacement RA product information:

“**CPUC RA Filing Guide**” means the Filing Guide for System, Local and Flexible Resource Adequacy (RA) Compliance Filings published annually by the CPUC.

“**Deliverability Period**” means the period in which the unit has rights to deliver energy to the CAISO Grid.

“**Flexible Capacity Category**” means the category of Effective Flexible Capacity, as described in the CPUC RA Filing Guide, applicable to the unit.

“**LCR Area (if any)**” means the Local Capacity Requirement area, as used in the CPUC RA Filing Guide, applicable to the unit, if any.

“**Prorated Percentage of Unit Factor**” means the percentage of the Unit CAISO NQC that is designated as Unit Contract Quantity.

“**Prorated Percentage of Unit Flexible Factor**” means the percentage of Unit CAISO EFC that is designated as Unit EFC Contract Quantity.

“**Resource Category**” means the Maximum Cumulative Capacity category, as described in the CPUC RA Filing Guide, applicable to the unit.

“**Resource Type**” means the type of generating or storage resource.

“**Run Hour Restrictions**” means any restrictions on the ability of the unit to run during any hours of the day.

“**Unit CAISO EFC**” means the unit’s Effective Flexible Capacity, as described in the CPUC RA Filing Guide, as determined by CPUC and CAISO.

“**Unit CAISO NQC**” means the NQC (as defined in the CAISO Tariff) for the unit, as determined by CPUC and CAISO.

“**Unit Contract Quantity**” means the amount of Resource Adequacy Benefits to be provided to Buyer from the unit in the form of Replacement RA, not to exceed the Guaranteed RA Capacity.

“**Unit EFC Contract Quantity**” means the amount of Flexible Resource Adequacy Benefits to be provided to Buyer from the unit in the form of Replacement RA, not to exceed the Guaranteed RA Capacity.

“**Unit SCID**” means the unit’s “Scheduling Coordinator ID Code”, as defined in the CAISO Tariff.

**EXHIBIT L - 1**

**Annual Energy Forecast**

The following table is provided for informational purposes only.

Please provide the expected metered energy in Pacific Prevailing Time. For the Daylight Savings Day in March, the HE3 volume should be 0 MWh. For the Daylight Savings Day in November, the HE2 volume should represent two hours of generation.

|  |  |  |  |
| --- | --- | --- | --- |
| Date | Datetime (Hour Beginning) | Hour Ending | MWh |
| 1/1/2022 | 1/1/2022 0:00 | 1 |  |
| 1/1/2022 | 1/1/2022 1:00 | 2 |  |
| 1/1/2022 | 1/1/2022 2:00 | 3 |  |
| 1/1/2022 | 1/1/2022 3:00 | 4 |  |
| 1/1/2022 | 1/1/2022 4:00 | 5 |  |
| 1/1/2022 | 1/1/2022 5:00 | 6 |  |
| [insert additional rows] | … | … |  |
| 12/31/2022 | 12/31/2022 18:00 | 19 |  |
| 12/31/2022 | 12/31/2022 19:00 | 20 |  |
| 12/31/2022 | 12/31/2022 20:00 | 21 |  |
| 12/31/2022 | 12/31/2022 21:00 | 22 |  |
| 12/31/2022 | 12/31/2022 22:00 | 23 |  |
| 12/31/2022 | 12/31/2022 23:00 | 24 |  |

**EXHIBIT L - 2**

**Monthly Expected Available Capacity**

The following table is provided for informational purposes only.

Please adjust the table for the appropriate number of days in the month for each month of the year.

Monthly Forecast of Available Capacity (MW)

|  | 1:00\* | 2:00 | 3:00 | 4:00 | 5:00 | 6:00 | 7:00 | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 20:00 | 21:00 | 22:00 | 23:00 | 24:00 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Day 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [insert additional rows for each day of the month] |
| Day 26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 29\*\* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 30\*\* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 31\*\* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

\*All times are designated as “Hour-Ending [\_\_]”.
\*\*Include these rows if needed for each month.

**EXHIBIT L - 3**

**Monthly Expected Metered Energy**

The following table is provided for informational purposes only.

Please adjust the table for the appropriate number of days in the month for each month of the year.

Monthly Forecast of Metered Energy (MWh)

|  | 1:00\* | 2:00 | 3:00 | 4:00 | 5:00 | 6:00 | 7:00 | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 20:00 | 21:00 | 22:00 | 23:00 | 24:00 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Day 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| [insert additional rows for each day of the month] |
| Day 26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 29\*\* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 30\*\* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Day 31\*\* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

\*All times are designated as “Hour-Ending [\_\_]”.
\*\*Include these rows if needed for each month.

**EXHIBIT M**

**NOTICES**

| ***[SELLER’S NAME]***(“Seller”) | **PENINSULA CLEAN ENERGY, a California joint powers authority** (“Buyer”) |
| --- | --- |
| **All Notices:** Street: City: Attn: Phone: Email: | **All Notices:** Street: City: Attn: Phone: Email: |
| **Emergency Contact:**Attn: Phone:E-mail: | **Emergency Contact:**Attn: Phone:E-mail: |
| **Reference Numbers:**Duns:Federal Tax ID Number:  | **Reference Numbers:**Duns:Federal Tax ID Number:  |
| **Invoices:**Attn: Phone:E-mail: | **Invoices:**Attn: Phone:E-mail: |
| **Scheduling:**Attn:Phone:Email: | **Scheduling:**Attn:Phone:Email: |
| **Confirmations:**Attn:Phone:Email: | **Confirmations:**Attn:Phone:Email: |
| **Payments:** Attn:Phone:E-mail: | **Payments:** Attn:Phone:E-mail: |
| **Wire Transfer:**BNK: ABA: ACCT:  | **Wire Transfer:**BNK: ABA: ACCT:  |

1. This table reflects Seller’s Expected Energy by calendar month in the first Contract Year, as if the first Contract Year begins on January first. The first Contract Year may begin on another date, per the terms of this Agreement. [↑](#footnote-ref-2)